## Programme delivery
Targeted Intervention -Annual Evaluation Tool (Destination Migrant Interventions)
TI -Annual Evaluation Tool ( Destination Migrant Interventions)-2012
Program Delivery
Name of the TI NGO: Shree Siddhi Swaraj Khadi Gramodhyog Vikas Mandal | [5 empty] | State: District: | Ahmedabad, Gujarat
Sl. No. | Indicators | Target | Achievement | Key Questions | Methodology to be adopted | Assessment Scores |  |  | Score Resulted | Remarks
[6 empty] | 1 | 2 | 3
SECTION 1: BASIC SERVICES
OUT REACH
1 | Listing of registered high risk migrants ( that is migrants who have been resgistered in DIC register, who have been counseled, who have been treated for STI) are available and individual tracking is in place for services. It is expected that the project will reach out 5,000/10,000 ( as the case may be) in a project year (in 12 months) cumulative basis as proposed in the proposal | 5,000/10,000 in 12 months | Done | Whether the M&E officer is able to give an analysis of registered migrants? | Verify the master register, link the entries with DIC, Counseling and STI treatment register and tracking systems. | Updated line list is available at the TI level but not used for tracking project services. | Updated line list is available and used for tracking outreach level services only. | Updated line list is available and used for tracking all the project level services ( includes ICTC referrals ,ART uptake, source States). | 3 | Line list is updated
2 | Out reach plan in place at project level and Micro plan available for each congregration point/hotspots of the peer educator. The volume, timing and day of out reach activities are clear to the team. | No. of congregation points mentioned in the proposal |  | Verification of outreach plan and micro plan. | Interview with ORWs and PEs. Verification of micro plans and outreach plans. Check at least 50% of the planned sites - whether the out reach activities, health camps, street plays are organised as per the plan during last 2 months | Outreach and micro plan is not in place / or if in place but not in use. | Outreach and micro plan in place and the same is used by ORW only. | Outreach and micro plan in place and the same is used by ORW, counsellor / ANM and PE. | 2 | Outreach and microplan are in place and utilised by staff members but planning at PE level is conceren for the project.
3 | Percent of targeted high risk migrants reached by the project (As per contract) | 5,000/10,000 in 12 months | 13506 | Number of high risk migrants registered during the last 1 year. The same need to be evaluated against the target of 5000/10000/12000 high risk migrants | Verification of project proposal, Peer monthly reports, ORW field diaries, master register/ other related documents. | At least 30% of target reached with counseling, DIC & STI services during the contract period | 31-60% of target reached with counseling, DIC & STI services during the contract period | Above 60% of target reached with counseling, DIC & STI services during the contract period | 3 | More than 60 % taret achieved with 3 services
4 | Follow up of migrants tested HIV positive/ linked ART (30% is expected to be linked to ART among the positives ever detected by the project) | No. of migrants tested positive | 0 | No. of Migrants who were tested positive/ on ART contacted at least once in 3 months - take average of last 3 months. | Peer Diaries and peer monthly reports, ORW field diary/ICTC and master registers | At least 30% are contacted regularly and provided program services | 31-60% are contacted regularly and provided program services | More than 60% are contacted regularly and provided program services. | 1 | 13 HIV positive were linked to services. Of which 3 were followed at 6 months. 6 HIV positive are on ART. However, most them were pre Registered at ART through ICTC But no follow up has been observed in records.
5 | % of Migrants covered through hotspots / DIC level meetings.( it is expected that there are 3 DICs and at least 10 meetings are conducted per month in each DIC) | 40% of migrants are expected to be reached through DICs |  | Every month ORW / PE should conduct meetings at the DIC with the migrants, hold health camps and registering them. | DIC level meeting registers. PE / ORW dairies.Verify last three month registers. Meet at least 5 stakeholders and write details of their observations in all DIC sites in the qualitative reports | At least 20% of all registered high risk migrants during the last 3 months are from DIC | At least 30% of all registered high risk migrants during the last 3 months are from DIC | At least 40% of all registered high risk migrants during the last 3 months are from DIC | 1 | Average 300 migrants are visiting DIC monthly as per records but same has not been observed at DIC level. DIC level meeting is not conducted through out the year at any DIC.
6 | Field visit by ORWs ( Each ORW is expected to attend 50% of the out reach sessions of the peer educators under them). The ORWs are expected to record their observations, provide support to Peers. If the records maintained by 3 ORWs is not updated, mark '0' (Zero) | 50% of the outreach sessions of all peer educators are to be supervised by the respective ORW |  | ORW visiting the fields minimum 5 days in a week and providing supportive supervision to all the PEs of his/her areas for effective delivery of project services by PEs. Ensuring all the PEs have enough skills.Also check similarly regarding all ORWs. | ORW diaries, weekly staff meeting minutes, ORW movement plan/register | Atleast 30% of sessions planned by peers are attended by ORWs | Atleast 40% of sessions planned by peers are attended by ORWs | Atleast 50% of sessions planned by peers are attended by ORWs | 1 | On records 50% of sessions planned by peer are attended by ORWs, but has not been verified during PE interaction. PE are not in possition to spent time as per talk.
7 | Number of mid-media activities conducted during last 3 months ( 2 activities in case of TIs for 10,000-12,000 migrants and 1 acitivity in case of TIs for 5,000 migrants). The contents of the mid-media activity conducted by TI/ IEC division should focus on issues related to migration and HIV, should include stakeholders in planning process. | 2 activities in case of TIs for 10,000-12,000 migrants and 1 acitivity in case of TIs for 5,000 migrants |  | Whether the mid-media activities conducted by TI NGO/IEC division has included stakeholders in the planning and migrants/stakeholders are able to provide feedback. In case no mid-media planning score is '0' | Mid-Media register/report, ORW planning sheet, financial documents related to mid-media activities available with NGO | Stakeholders are not part of the planning process/ reports are not available/ financial documents are not tallying / not available | Stakeholders are part of the planning process/ reports are not available or reports are available but no finance documents are not tallying /not available | Stakeholders are part of the planning process, reports and financial documents tally as well as the feedback from the stakeholders corroborate the same. | 2 | stake holder was involved mid media activities. Due to delay in grant and expense restriction on mid media activities by ACS / NACO not major activities were conducted.
8 | Congregation events are organised by the project ( 2 times per quarter for migrant TIs covering 5,000/10,000/12,000 migrants). These events should be in line with festivals organised by the migrants/ employers and discusses issues related to migration and HIV | 2 times per quarter for migrant TIs covering 5,000/10,000/12,000 migrants | 3 events | Whether the congregation events are organised by the project are well planned, stakeholders and migrants have been part of the events | Event reports, related financial documents, discussion with stakeholders | Congregation events were organised but those were not part of the festivals/events of the employers/migrants | Congregation events reports / related financial documents are not available. | Both event reports and financial documents are available. Stakeholder and migrants feedback corroborate with the event details and issues. | 2 | 3 events were organized durind AIDS day week. Reports and financial documents are available. Planned Congregation events were not conducted, AMC ACS's letter to stop expenses on mid media and other activities is considered for giving score.
9 | Number of sessions organised by the ORWs/Peer Educators during last 3 months ( average to be taken for last 3 months). Per month each Peer is expected to conduct 20 sessions and ORW is expected to conduct 10 sessions. Each project should ensure that at least 80% of the planned sessions are actually conducted and 50% of them are linked with services of either DIC/Clinic/Counseling | 20 sessions by each Peer Educators and 10 sessions by each ORW |  | Whether the outreach plan of existing Peers and ORWs during last 3 months indicate that the team is able to achieve 80% of their planned sessions and 50% of these sessions were linked with services | Outreach plan, outreach diaries, honorarium sheet of the Peers ( peers are expected to be paid Rs.50/- per session they have conducted), service registers for DIC/Clinic/Counseling. Below 60% the score should be '0' | At least 60% of the out reach planned are actually conducted by the team. If 50% of these sessions are not linked to service, the score should be '0' | At least 70% of the out reach planned are actually conducted by the team. If 50% of these sessions are not linked to service, the score should be '0' | At least 80% of the out reach planned are actually conducted by the team. If 50% of these sessions are not linked to service, the score should be '0' | 1 | As per records, PEs conduct 20 IPC Sessions per month and out of which 50% are monitored by ORW but during field interaction It was observed that PEs are not able to spare much time for project activities and hence unable to do IPC as per target
CLINIC SERVICES
10 | Established health camp approach and any other linkages developed with government clinic and PP doctors. Verify the registers of PP doctors/ govt. STI services whether migrants are accessing services. | Health camp of 24-40 hours per month; linkages with government and PP clinics | 1 Doctor identified | Health camp of 24-40 hours of service provided per month; linkages with government and PP clinics developed over the last 3 months. | Observations based on NACO guidelines. Clinic, PPP registers and payment registers to be verified. Payment is given only for doctors engaged in health camps and not for PP doctors | At least 24-40 hours of clinical services through health camps provided | In addition to the health camps, the services of PP doctors are linked. | In addition to the health camps, the services of PP doctors, government STI services are being used by the project. | 1 | 18-20 camps are organised monthly as per records and doccumentaton, Field interaction with PE, doctor, stake holders and migrants are varries from the doccuments. Quality, Time, hours and place of health camps needs to be enhanced.
11 | Migrants counselled by counsellor /ANM | At least 30% of the targeted migrants | 4661 | All the migrants visiting the clinics or CAMPS needs to be counselled. | Counseling registers & Master register | Atleast 20% of registered as reflected in master register counselled by counsellor / ANM | 21-30% of registered as reflected in master register counselled by counsellor / ANM | Atleast more than 30% of registered as reflected in master register counselled by counsellor / ANM | 3 | 4661 counselled by counsellor (34.5%)
12 | Migrants who had STI have been followed up | 100% of STI cases need to be followed up | 307 | Percent of STI cases have to be followed up. The ANM/Counselor to ensure that the follow up are happening through the ORWs/ Peer Educators | MIS reports, Referral / clinic / STI registers, referral slips, Daily dairies of PE / ORW | At least 35% of STI cases have been followed up. | 36-50% of STI cases have been followed up. | Above 50% of STI cases have been followed up. | 3 | 307 migrants have followed out of 401.
13 | Percent of migrants tested for HIV | 100% of STI cases need to tested for HIV | 374 | No. of registered migrants tested for HIV | Referral registers,referral slips and PE dairies and ICTC data. Reconcile with existing ICTC where referrals are made from TI. If it is mobile ICTC check the date of camp and reconcile with SACS | Atleast 20% of the migrants trreated with STI are also tested for HIV | Atleast 21-30% of the migrants trreated with STI are also tested for HIV | Above 30% of the migrants trreated with STI are also tested for HIV. | 3 | 2186 (April 14 to March 15) tested for HIV (16.2%). 374 of 401 STI cases were refered and tested for HIV.
14 | Identified HIV positive cases from HRG were linked to ART during the contract period | 100% of HIV positive migrants identified by the project | 8 out of 13 identified | No. of migrants identified as HIV positive linked to ART centre during the contract period. | Verification of registers, general treatment register, referral slips/register | Out of total atleast 40% were linked to ART. | Out of total atleast 41-50% were linked to ART. | More than 50% were linked to ART | 2 | 13 HIV positive were linked to services. Of which 6 HIV positive are on ART. But no follow up has been observed in records.
COMMODITIES
15 | Condom outlets established by TI ( the out lets are expected to be identified by the project and further the same need to be managed by SMO in case the same is a SMO district. In case the district is not covered by SMO, the activities are to be done by TI from the revolving funds) | 20 outlets for TI with 10,000 migrants & 10 for TI with 5,000 migrants | 33 | Number of outlets established (20 is the target) of which 50% are non-traditional outlets. | Verify the condom stock register, make visit to at least 20% of the out lets through random sampling.These outlets should have visibility, accessible by the migrants. | 20% are non traditional outlets | 30% are non traditional outlets. | 50% are non traditional outlets. | 2 | 33 active condom outlets (25 non traditional and 8 traditional) out of indicator of 50.
16 | Social marketing activities managed by TIs in NON-SMO districts (the NGOs are expected to use revolving funds to socially marketed condoms, the accounts of the NGO need to show the amount generated from the social marketing) | Applicable in Non-SMO districts only | 33 | Amount of funds generated from the social marketing of condoms from the revolving funds | Verify the financial documents related to amount generated from the social marketing in case of non-SMO districts, in case of SMO districts the same need to be verified from the reports of SMO /Condom TSG (State). | 20% are non traditional outlets | 30% are non traditional outlets. | 50% are non traditional outlets. | 1 | 75% outlets are non traditionals. 80% Cost of SM Condom and Drugs were borned by NGO and not fully collected from benificiaries
17 | Avalability of STI drugs, with a buffer stock management in place. | No stock out for STI drug should happen |  | No. of times STI drugs, have been purchased during the contract period. Was there any stock-out of commodities reported during contract period. | Verfication of stock & disttribution register and vouchers. | Stock out of commodities were witnessed more than once during contract period. | No stock out was reported. But no buffer stock are maintained as part of tracking the stock. | No stock-out of commodities during last one year reported and buffer stock is being maintained. | 2 | However, No stock out observed during last one year, NGO needs to maintain buffer stock atleast for next 3 months.
SECTION 2: SUPPORT SERVICES
18 | Identified cases from migrants were linked for TB to DOT centre (RNTCP) during the contract period. It is expected that all migrants who have been detected positive need to be linked to TB programme or migrants who come with suspected TB symptoms of weight loss, evening rise of fever, cough more than 2 weeks etc. | 100% of the migrants with suspected TB symptoms need to be linked to RNTCP | 24 | No. of migrants linked to DOT centre during the contract period, detected for TB. | Verification of registers, general treatment register, referral slips/register | Out of total identified migrants with suspected TB symptoms/ with HIV positive detected atleast 60% were linked to TB programme. | Out of total identified migrants with suspected TB symptoms/ with HIV positive detected atleast 80% were linked to TB programme | Out of total identified migrants with suspected TB symptoms/ with HIV positive detected all were linked to TB programme | 3 | 24 Migrants were refered to DOT, out of which 1 is detected positive which was linked to DOTS. Treatment completed.
ENABLING ENVIRONMENT
19 | Advocacy meeting with key stakeholders ( employers, contractors, supervisors, mess managers, brokers, migrant leaders etc. who are related to migrants and their employment) |  |  | Advocacy meeting held with key stakeholders at various level with plan. | Verification of minutes, meeting registers and MIS reports | Advocacy meeting are conducted without plan | Advocacy meeting conducted at all levels as per plan without proper documentation and follow up | Advocacy meeting regularly conducted as per plan at all levels with proper documentation and follow-up | 3 | 25 advocacy meetings were conducted but follow up action after advocacy is needed at TI level
20 | Programme Management Committee in place | One for each project |  | Set up of project management team at TI level represented by members of migrant groups, stakeholders, employers | Advocacy activities or meeting register where in the project activities are recorded. In cases of no project management committee in place - Score shoule be '0' | The committee is in place but the members are not aware of their roles and no meeting has taken place. | The committee is in place but no contribution in terms of their support to the TI services is observed. | The committee is in place and the members have contributed in terms of resouces for TI services is observed. | 0 | Only list of PMC is available. No meeting has been conducted. Team does not have clarity on what is PMC.
COMMUNITY MOBILISATION
21 | Number of Peers from Source States (expected 40% of 15 peers (where target is 10000) and of 8 peers (where target is 5000) are from source states | 6 in case of Tis with 10,000 migrants, 4 in case of 5,000 migrants | On the day of evaluation only 6 PE were 3 month old. | Verify the records and peer outreach plans. These peers are expected to be at least more than 6 months with the project | Interview with peers to understand whether they are part of the programme since more than 6 months | At least 60% of the peers from the source States are more than 3 months | 61-80% of the peers from the source States are more than 3 months | More than 80% of the peers are from the source States are more than 3 months | 2 | 80% PE are from source state. Evaluation team were not able to communicate with PE. Only 3 PE were made available for interaction with evaluation team.
22 | Number of stakeholders (labour contractors, brokers) ar epart of peer profile. Atleast 5 peers (where target is 10,000), 3 (where target is 5000) are from stakeholders | 5 in case of Tis with 10,000 migrants, 3 in case of 5,000 migrants |  |  |  | At least 60% of the peers from the Stakeholders are more than 6 months | 61-80% of the peers from the source Stakeholders are more than 6 months | More than 80% of the peers are from the Stakeholders are more than 6 months | 1 | Evaluation team could interact with only 3 PE from which one was stake holders.
Community response to the Program Services
23 | Project is adhering to confidentiality norms. |  |  | Privacy in the clinic and information shared in the counseling sessions are maintained and not shared. | FGD with the 10-15 community members (suggested to conduct at the field). | Participants are not sure of confidentiality norms being adhered at the project level | Atleast 75% of the participants are satsfied with privacy and confidentiality at the project level. | More than 75% of the particiaptns are satsfied with privacy and confidentiality at the project level. | 2 | Around 70% Migrants interacted was satisfied with privacy and confedintiality
24 | Community perception on project services |  |  | Are the community members satisfied with the available services and services meet their demands. | FGD with 10-15 community members (suggested to conduct at the filed level). | Atleast 50% of the participants are convinced with the project services | 51%- 75% participants are satisfied with the project services. | More than 75% or of the participants are satisfied with the project services. | 1 | Around 50% Migrants interacted with Evaluation team were satisfied with the project services.
25 | Involvement of key stakeholders in programme monitoring |  |  | Ability of the project to involve stakeholders like police, civic officials, social development sector officials in addressing the issues relating to project services | One to one interaction with atleast 6 stakeholders of the project. (suggested to conduct at the filed). | Three stake holders participated in addressing the issues relating to project services | Four stake holders have said S/he has involved in addressing the issues relating to project services. | All the three stake holders have said that they involved in addressing the issues relating to project services. | 1 | List of stake holder is developed but their much involvement needs to increase at TI level
SECTION 1: BASIC SERVICES | [6 empty] | SECTION 1: TOTAL MARKS OBTAINED |  | 33
SECTION 2: SUPPORT SERVICES | [6 empty] | SECTION 2: TOTAL MARKS OBTAINED |  | 13
TOTAL SCORE | [8 empty] | 46

## Org. Capacity
TI -Annual Evaluation Tool ( Destination Migrant Interventions)
Organisational Capacity
Name of the TI NGO: Shree Siddhi Swaraj Khadi Gramodhyog Vikas Mandal |  |  | State: Gujarat District: Ahmedabad
Sl.No. | Indicators | Score Resulted "0" for No "1" for Yes | Mean of verification/observations | Remarks
1 | All project staff and PE positions have been filled as per project proposal | 1 | All NGOs contracted has to appoint the staff within three months from signing/ renewal of contract. Project proposal, appointment letters / staff attendance sheet during the last year (If a position has been vacated and not filled in within 2 months, give "0" mark for this indicator.) | 8 ORW, 1 M & E, 1 Counsellor, 1 PM, 15 PE.
2 | Staff turnover witnessed in the project during the contract period. | 0 | Attendance sheets /appointment letters. ( If there is more than 40% of project staff have resigned during the year then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | More than 40% staff resigned during the year. 11 ORW left project during last Six month of evaluation period.
3 | Peer Educator turnover witnessed in the project during the contract period | 0 | Payment slips/PE diaries/ORW diaries ( If there is more than 20% PEs during the contract period then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | 9 PE out of 15 PE joined in May-June 2015. 13 PW have lwft project during last 6 month of evaluation period.
4 | Ratio of peer educators ( A total 15 peer educatos in case of interventions targeting 10,000-12,000 migrants and 8 peer educators in case of interventions targeting 5,000-10,000 migrants). At least 40% of the peer educators should be from the source States, 30% are from the contractors, brokers. | 1 | These peer educator ratio is maintained for at least 6 months. The evaluation team should meet at least 50% of the peer educators in the field and verify their engagement with the project for more than 6 months. If the ratio is either not being maintained by the project, or if the ratio is there but the peer educators are less than 6 months - GIVE '0' mark in this indicator | 15 PL has been placed to cover 12000 migrants. Evaluation team could meet only 3 PE out of 15 during evaluation period.
5 | Ratio of ORWs A total 5 ORWs in case of interventions targeting 10,000-12,000 migrants and 2 ORWs in case of interventions targeting 5,000-10,000 migrants). | 1 | These ORWs are aware of their roles and responsibilities. The ORWs are given geographic responsibilities. Their records maintain that they supervise 50% of the sessions performed by the peer educators under them during field visits. If either of these indicators are not available, GIVE '0' mark in this indicator | 6 ORW are not trained.
6 | Job description given to each project staff | 1 | All project staff do have written job description or available at NGO level. Interview one from each group of staffs and peer educators whether they have a workplan aligning with their job description and the project targets. Whether the staffs during interview are able to provide details of these workplan, what they have achieved and what are the challenges. | Staff has only appointment order. Role and responsibility has not been given to staff but staff were able to describe their role and responsibility.
7 | Attendance/leave register maintained for the project staff | 1 | Examine the attendance register is in use /leave register available. Whether the number of leaves are in accordance with job description. | Yes, well maintained
8 | Induction training to PE and other staff has been completed by the project with support from SACS/ TSU/ STRC | 0 | Training registers/ induction training report | 6 ORW are not trained. Induction training of new PE have not been conducted.
9 | The project Director attended atleast 80% all the monthly meetings of the TI project duing the year. | 1 | Attendance of meeting registers and minutes of the meeting | Yes, average meeting per month attended but needs to make review meeting as planned meeting if possible at the end/ beginning of months.
10 | Assets purchased under project is codified/marked | 1 | Assets register and purchase voucher (All the assets purchased under the project) | Yes, well maintained
Total Score |  | 7

## Finance
TI - ANNUAL EVALUATION
Evaluation Tool for Finance
Name of the TI NGO: | [5 empty] | State: District:
Sl.No. | Indicators | Key Questions* | Methodology to be adopted | Score |  | Score Resulted "0" for No "1" for Yes | Explanation for score | Remarks
|  |  |  | 1 | 0
1 | Budget Utilization | What is the percentage of budget utilized against the release of fund on the proposed activities | Verification of vouchers, SOE, Bank book etc.. | Utilization should be of or above 60% against the release of fund from SACS | Less than 60% of the released fund | 1 | Budget has been completely utilized by the NGO. Bank book & vouchers have been verified but SOE has not been provided to us
2 | Pattern of expenditure | Whether the expenditure is as per approved budget in each head | Verification of vouchers, approved budget, SOE, Bank book etc.. | As per the approved budget or No but as per the approval from SACS. | No as per the approval. | 1 | Patter of expenditure are according to the approved budget.
3 | Bank Account | Whether a separate bank account maintained for the TI Project at the local bank | Verification of bank book and other related documents | Separate bank account in place for TI project in the project area | No separate account | 1 | Separate bank account is maintained for the TI Project which has been verified .
4 | Systems of Payment-Verification of Bills and Vouchers ( in case of book keeping is done by software, day wise prints of vouchers and ledgers should be available) | All payments made with proper bills and vouchers and are in place with proper approval. | Verification of vouchers and bills | Vouchers and bills are propoerly maintained and are all with approval. | Inadeqaute and no approval from PD of the TI. | 1 | All payments are made by taking the due approval & all bills are attached with the vouchers
5 | Systems of Payment-Mode of payments | Mode of payment- cash payment is Rs.5000/- as per revised direction from NACO. | Verification of bank account and vouchers | No cash transaction above Rs.5000/- | Cash transaction for the amount more than Rs.5000/- | 1 | yes no cash expense is of above Rs 5000/-
6 | Systems of Payment-Record keeping | All vouchers are printed and machine numbered Whether the ledger is maintained for vouchers | Verification of vouchers Verification of ledger | Vouchers are printed and machine numbered. Ledgers are maintained properly. | Not in place. | 1 | yes all vouchers have been printed and machine numbered.
7 | Systems of booking keeping maintenance | Whether cash book maintained/entry made on daily basis | Verification of cash book and interview of accountant | Cash book is updated | Not updated | 1 | Yes cash book has been maintained on daily basis
8 | Financial reporting-SOEs submitted as per operational guideline | Whether SOEs are submitted to SACS on time in the prescribed format. (refer Operational Guidelines for NGO/CBO PART-II-Annexure 'A' and 'B' | Verification of SOEs and interview of SACS official | SOEs are submitted on time and records for the same is avaialbe. | Irregualr in submission of SOEs. | 0 | SOE has not been provided to us during the audit
9 | Financial reporting-Mismatch between physical & financial reporting | Whether any mismatch between financial and physical progress reports | Verification of MIS reports and audit reports | Nil or Negligible mismatch | Huge level of mismatch observed and not justifiable | 1 | No mismatch was found between the MIS report and audit report of F.Y 2013-14 as Audit report of F.Y 2014-15 was not provided.
10 | Purchase of drugs for STD treatment (only in cases where the purchase has been approved by SACS) | Whether the guidelines on GMP followed? | Verify the drugs and guidelines for GMP/ purchased under Jan Ausadhi Yojana | As per GMP | Not followed and no genuine explanation for the relapse | 1 | The guidelines have been complied by the NGO.
11 | Compliance to SACS directions | Whether NGO has complied to the audit observations | Verify audit recommendation and action taken bassed on the report | NGO has given adeqaute attention to audit recommendations and actions were taken | No action from NGO side | 1 | Recommendations given by the auditors have been complied by the NGO.
12 | Cash in hand | What is the limit for cash in hand in the project. NACO direction is maximum Rs.5000/- | Verify cash book, cash box and interview with accountant and PD. | Normally below Rs.5000/- | No system and at majority of times cash balance is more than Rs.5000/- | 0 | Cash of more than Rs 5000 has been maintained by the NGO in the 2nd half of the financial year
13 | Procurement system in place | What is the procurement system for purchase of drugs/needles and syringes/fixed assets | Three quotations to be collected | Quotations are in place from three different parties and assessed. | No system in place. | 1 | yes quotations have been taken by the NGO before the order is placed. Which has been verified.
Total Score | [5 empty] | 11

## Scoring sheet
Name of the TI NGO: Shree Siddhi Swaraj Khadi Gramodhyog Vikas Mandal |  |  | State: Gujarat District: ahmedabad
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Qualifying Marks | Qualifying Percentage
Stage1
1 | Organisational Capacity | 10 | 10 | 8 | 80
2 | Finance | 13 | 13 | 9 | 70
Actual Marks ( calculated automatically from the evaluation sheet)
S. No. | Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Remarks
1 | Organisational Capacity | 10 | 7 | 70
2 | Finance | 13 | 11 | 84.6154
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S.No. | Particulars | No. of indicators Applicable for this TI | Max. Score | Weighted Max. Score | weightage score Obtained | Percent of Score derived
1 | BASIC SERVICES | 17 | 51 | 40.8 | 26.4 | 64.7059
2 | SUPPORT SERVICES | 8 | 24 | 12 | 6.5 | 54.1667
Total |  | 25 | 75 | 52.8 | 32.9 | 62.3106
Name of the Evaluator