## Organisational Capacity
TI-Evaluation Tool Truckers
Organisational Capacity
Name of the TI NGO:Naisargik ( The Organization for Natural Care ) |  |  | Intervention Category: A/B/C (please circle the required one) | State: Gujarat District: Ahmedabad
Sl.No. | Indicators | Score Resulted "0" for No "1" for Yes | Mean of verification/observations | Remarks
1 | All project staff and 70%PE positions have been filled as per project proposal | 1 | All NGOs contracted has to appoint the staff within three months from signing of contract. Project proposal, staff attendance sheet during the last year (If a position has been vacated and not filled in within 2 months, give "0" mark for this indicator.) | ORW position has been recently fallen vacant ( since beginning of this month i.e. June )
2 | Staff turnover witnessed in the project during the contract period. | 1 | Attendance sheets /appointment letters. ( If there is more than 50% of project staff(except PEs) have resigned during the year then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Only one position changed. Copunsellor promoted to Projaect manager after the person left.
3 | Peer Educator turnover witnessed in the project during the contract period | 1 | Attendance sheets /appointment letters. ( If there is more than 20% PEs during the contract period then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Currently about 2 Pes have left their positions and remain unfilled
4 | Job description given to each project staff | 1 | All project staff do have written job description or available at NGO level | Yes written job descriptions are available
5 | Peer Profile | 1 | More than 20% of all the Pes are truckers /ex truckers, helpers /ex helpers | Yes most arte truckers, helpers and transport related workers
6 | Attendance/leave register maintained for the project staff | 1 | Examine the attendance register is in use /leave register available | Attendance register is maintained and updated
7 | Orientation to PE and other staff has been completed | 1 | Training registers/ orientation training/PO visit report completed within 3 months of joining | PM and ORWs trained. Counsellor not trained
8 | The project Director attended atleast 60% all the monthly meetings of the TI project duing the year. | 1 | Attendance of meeting registers and minutes of the meeting | Yes maintained.
9 | Assets purchased under project is codified/marked | 1 | Assets register and purchase voucher (All the assets purchased under the project) | Asset register maintained. Could be improved further.
Total Score |  | 8
Name of the Evaluator

## Finance
TI - ANNUAL EVALUATION
Evaluation Tool for Finance
Name of the TI NGO:Naisargik ( The Organization foe Natural Care ) |  |  | Intervention Category: A/B/C (please circle the required one) |  | State: Gujarat District: Ahmedabad
Sl.No. | Indicators | Key Questions* | Methodology to be adopted | Score |  | Score Resulted "0" for No "1" for Yes | Explanation for score | Remarks
|  |  |  | 1 | 0
1 | Budget Utilization | What is the percentage of budget utilized against the release of fund on the proposed activities | Verification of vouchers, SOE, Bank book etc.. | Utilization should be of or above 60% against the release of fund from SACS | Less than 60% of the released fund | 1 | Budget has been utilized up to 72% by the NGO.
2 | Pattern of expenditure | Whether the expenditure is as per approved budget in each head | Verification of vouchers, approved budget, SOE, Bank book etc.. | As per the approved budget or No but as per the approval from SACS. | No as per the approval. | 1 | Expenditure are according to the approved budget.
3 | Bank Account | Whether a separate bank account maintained for the TI Project at the local bank | Verification of bank book and other related documents | Separate bank account in place for TI project in the project area | No separate account | 1 | Separate bank account is maintained for the TI Project which is verified .
4 | Systems of Payment-Verification of Bills and Vouchers ( in case of book keeping is done by software, day wise prints of vouchers and ledgers should be available) | All payments made with proper bills and vouchers and are in place with proper approval. | Verification of vouchers and bills | Vouchers and bills are propoerly maintained and are all with approval. | Inadeqaute and no approval from PD of the TI. | 1 | All payments are made by taking the due approval & all bills are attached with the vouchers
5 | Systems of Payment-Mode of payments | Mode of payment- cash payment is Rs.5000/- as per revised direction from NACO. | Verification of bank account and vouchers | No cash transaction above Rs.5000/- | Cash transaction for the amount more than Rs.5000/- | 1 | yes no cash expense is above Rs 5000/-
6 | Systems of Payment-Record keeping | All vouchers are printed and machine numbered Whether the ledger is maintained for vouchers | Verification of vouchers Verification of ledger | Vouchers are printed and machine numbered. Ledgers are maintained properly. | Not in place. | 0 | No Vouvhers are not Printed & are numbered manually
7 | Systems of booking keeping maintenance | Whether cash book maintained/entry made on daily basis | Verification of cash book and interview of accountant | Cash book is updated | Not updated | 1 | Yes cash book has been maintained on daily basis
8 | Financial reporting-SOEs submitted as per operational guideline | Whether SOEs are submitted to SACS on time in the prescribed format. (refer Operational Guidelines for NGO/CBO PART-II-Annexure 'A' and 'B' | Verification of SOEs and interview of SACS official | SOEs are submitted on time and records for the same is avaialbe. | Irregualr in submission of SOEs. | 1 | SOE has been provided till Jan After it Balance was negative & Hence No SOE Submitted after it
9 | Financial reporting-Mismatch between physical & financial reporting | Whether any mismatch between financial and physical progress reports | Verification of MIS reports and audit reports | Nil or Negligible mismatch | Huge level of mismatch observed and not justifiable | 1 | no mismatch was found between the MIS report and audit report in F.Y 2013-14 as Audit report of F.Y 2014-15 was not provided.
10 | Purchase of drugs for STD treatment (only in cases where the purchase has been approved by SACS) | Whether the guidelines on GMP followed? | Verify the drugs and guidelines for GMP/ purchased under Jan Ausadhi Yojana | As per GMP | Not followed and no genuine explanation for the relapse | 1 | Yes it has been Properly done.
11 | Compliance to SACS directions | Whether NGO has complied to the audit observations | Verify audit recommendation and action taken bassed on the report | NGO has given adeqaute attention to audit recommendations and actions were taken | No action from NGO side | 1 | Yes Adequate actions has been taken by the NGO.
12 | Cash in hand | What is the limit for cash in hand in the project. NACO direction is maximum Rs.5000/- | Verify cash book, cash box and interview with accountant and PD. | Normally below Rs.5000/- | No system and at majority of times cash balance is more than Rs.5000/- | 0 | Majorly the cash balance was more than 5000 rs as due to income gained.
13 | Procurement system in place | What is the procurement system for purchase of drugs/needles and syringes/fixed assets | Three quotations to be collected | Quotations are in place from three different parties and assessed. | No system in place. | 1 | Yes Proper quotations are found. | N.A.
Total Score | [5 empty] | 11
Name of the Evaluator

## Program Delivery
TI- Evaluation Tool Truckers
Programme Delivery
Name of the TI NGO:Naisargik ( The Organization for Natural Care |  |  |  |  | Intervention Category: A/B/C (please circle the required one)-B |  | State: Gujarat District: Ahmedabad
Sl No | Indicators | Target | Achievement | Key Questions | Methodology to be adopted | Assessment Scores |  |  | Scores Resulted | Remarks
[6 empty] | 1 (Poor) | 2 (Average) | 3 (Good)
Outreach
1 | Monthly outreach plan in place at project level available for each truckers halting point within the project area. i.e. one project area may have separate truck halting points and each require separate plan. |  | Plan done | Verification of outreach plan | Interview with ORWs and Pes whether they are able to explain the plan and its use.Mark 0 if outreach plan is not there for past 3 months | Outreach plan in place but ORW not able to explain | Outreach plan in place able to explain but not fully used by Team. | Outreach plan in place and the same is used by ORW, and PE. | 3 | Micro planning lacks strategic location focus.
2 | Percent of target truckers contacted by the project through IPC sessions (as per intervention wise contract per year) | 1,20,000 for A category, 40,000 for B category, 20,000 for C category. - Target is 40,000 | 55.24 % 22,096 | Number of estimated truckers contacted through IPC sessions conducted by Pes and ORWs at least once in a quarter during contract year as per contract agreement.1,20,000 for A category,40,000 for B category,20,000 for C category. | Verification of project proposal, performance indicators,Peer monthly reports, ORW field diaries/ other related documents. (Verification by CMIS/Monthly report, Outreach registers) | At least 40% of target truckers contacted through IPC sessions in a quarter during the contract period | 41-59% of target truckers contacted through IPC sessions in a quarter during the contract period. | More than 60% of target truckers contacted through IPC sessions in a quarter during the contract period. | 1 | The target population is not available thus affecting coverage
3 | Field Visit by ORWs | 5 days a week and 2 days for supervision for each ORW | Regular | ORW visiting the field minimum 5 days in a week and providing 2 day supportive supervision to all the PEs of his/her areas for effective delivery of project services by PEs to truckers . 60% ORWs are able to demonstrate IPC sessions/Health games. | ORW diaries, weekly staff meeting minutes, ORW movement plan/register,observations on field recorded in the diaries. If no field visit, score is '0' | Atleast 40% among the ORWs are able to demonstrate IPC sessions/Health games | Atleast 50% among the ORWs are able to demonstrate IPC sessions/Health game | All ORWs are able to demonstrate IPC sessions/Health game | 3 | One ORW is new
4 | Theme based street plays | 30/permonth for A category,10/monthfor B category,5/month for C category : Planned 18 as per directive | 15 done | Number of street plays organised against plan during last three months.30/permonth for A category,10/monthfor B category,5/month for C category | Review of Daily report (ORW), Mid-media /IPC report, BCC material distribution register, Monthly report (Quantitative and Qualitative), Review of scipt, Personal observation and interactions | At least 50% street play organised against planned | At least 51-80% street play organised against planned | 80% and above street play organised against planned | 2 | Done till December 2014 as per Amhedabad SACS directive.However, use of AV aids is low
5 | Quality of peer education by the Peers |  |  | Observation of atleast 2 IPC sessions and interaction with the peers | Review of IPC Charts.Personal observations and interactions with Peers | Less than 40% PEs interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration | 41-59% PEs interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration | 60% and above Pes interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration. | 2
Clinic and other Services
6 | Established static clinic and operates at flexible timings with required manpower, infrastructure and equipment/instruments |  |  | Set up of a static clinic (may also be of flexible timings) as per NACO guidelines (Doctor,Counselor/staff nurse),timings of atleast 3 hours a day, space for examination available, STI drugs availabilty. | Clinic observations based on NACO guidelines/ checklist.Observation and interaction with Doctor,counselor//Staff nurse. | Static clinic set up without proper clinical equipment, non availabilty of STI drugs. | Static clinic set up with proper clinical equipment but non availabilty of STI drugs as per guidelines. | Static clinic set up with proper clinical equipment, Availabilty of STI drugs with proper stock keeping | 2 | 2 hours per camp - 20 in a month
7 | Quality of clinical services provided by the static/satelite clinics |  |  | Clinical services provided with confidentiality, patients are counseled on condom use, follow up plan is discussed. | Observations of the services, feedback from the truckers and stakeholders. | Confidentiality is not maintained, follow up plan is not discussed | Confidentiality is maintained, other factors are compromised. | All basic requirements are met. | 2 | Confidentality is maintained only in the static and a few of the outreach health camps
8 | Operates satelite clinics, as extension of static clinics around neighbouring establishments accessible by truckers |  |  | Operates satellite clinic (as per NACO guidelines) around neighbouring establishments .3-6 satellite locations in A category site,3 atellite locations in B category, Not applicable in C category site. | Clinic observations based on NACO guidelines/ checklist. Clinic schedules prominently displayed at transporters/brokers premises. | Satellite clinic non operational | Satellite Clinic operational but less than 3 locations | Satellite clinic operational and in 3-6 locations . | 2 | Clinics done as health camps
9 | Truckers tested in ICTC (HIV testing) | 100% of STI cases need to tested for HIV | Tested 54 : 100 % | Percent of truckers registered for STI treatment were tested for HIV testing | Couseling and referal registered/CMIS, verification of referral slips signed by ICTC counselor | Below 30% of referred to ICTC have actually tested in ICTC | 31-39% of referred to ICTC have actually tested in ICTC | Above 40% of referred to ICTC have actually tested in ICTC | 2 | It appears that not all cases are detected and tracked
10 | STI counseling sessions | 100% of STI cases need to be counseled | Counseled 54 : 100% | Project Counselor is adequately trained and performs STI counseling | Counseling Register, Personal interaction and observations during the counseling session | Below 50% of the STI clients are exposed to STI counseling | 50-80% STI clients in the clinic are exposed to STI counseling | 80% and above STI clients are exposed to STI counseling. Counselor adheres to all steps | 2 | Current Project Counsellor not adequately trained
11 | Co-Branding of Khushi/Khushi-Suraksha clinics and IEC/BCC materials |  |  | Clinic walls have colour combination of Yellow and Blue. IEC/BCC materials ar displayed with logos of Khushi/Suraksha and Khushi | Personal observations | Clinic not functional | Clinic functional without Khushi/Suraksha Branding (Wall colours and logos) | Clinic functional with Khushi/Suraksha branding (wall colours and logos) |  | Not applicable
12 | Clinic footfalls in the clinics (15% of coverage for A category and 25% of coverage for B&C category of the outreach coverage - indicator no.2) | 15% of coverage for A category and 25% of coverage for B&C category of the outreach coverage - indicator no.2): | 660 which is 26.4% | The clinic footfalls observed during last 3 months ( average of 3 months) to be taken | Verification of clinic cards, patient register, medicine dispensing register, cash book | Less than 15% in A, 25% in B &C | 15% in A, 25% in B&C | More than the benchmark | 2 | The total coverage is low. However there is coverage of the existing available truckers
13 | STI footfalls among the clinic footfalls (10% of the foot falls - indicator 12) : 660 planned | 10% of the foot falls - indicator 12 | 81.8 % ( 54 out of 66) | The STI footfalls observed during last 3 months ( average of 3 months) to be taken | Verification of clinic cards, patient register, medicine dispensing register, cash book | Less than 10% of the above indicator | 10% of the above indicator | More than 10% of the above indicator | 2
Condom Management
14 | Coordination with the SMO to provide information on condom availablity, demand, avaiability and display of IEC on condoms. In case of non-SMO districts the NGOs are expected to manage social marketing |  |  | Joint planning, field visits and reviews held with SMO | Meeting minutes and Joint visit reports with SMO. Feedback from the out let holders, SMO supervisors of the area. | Joint reviews, planning and field visits with SMO/ TSG POs done for less than 6 months | For 6-10 months, Joint reviews, planning and field visits with SMO/ TSG POs | Joint reviews, planning and field visits with SMO/TSG POs done for more than 10 months | 1 | Some joint visits have been done with PSI but overall it is poor performance
15 | Traditional and non-traditional outlets for condom social marketing | At least 80% of the out lets should be non-traditional | 61.6% | Percent of traditional and non-traditional outlets for condom social marketing in the operational area | Daily dairies , Weekly and monthly reports, SM Condom register | Below 50% of the functional TO and NTO available as per the target | Between 50-80% functional TO and NTO available as per the target | 80% and above functional TO and NTO available as per the target | 2 | Firstly the total planned outlets is about 60 % and then still the no. of NTO is not achieved
16 | Condoms sales through the TO and NTO | At least 80% of the condom sales through outlets | PSI data not avilable | Percent of condoms sold through the TO and NTO in the oprational area | Daily dairies, , Weekly and monthly reports, SM Condom register | Below 50% condom sale recorded as per the target | Between 50-80% condom sale recorded as per the target | 80% and above condom sale recorded as per the target | 1 | Achieved 04.44 % for overlall achievement but PSI data is not there
17 | STI Drugs -commodity-drug management, availability, stock out. |  |  | Whether NGO purchases drugs using 3 competitive quotations, medicines dispensed to the truckers at no-profit basis, receipts are maintained. | Medicine stock register, Cash Book, bills, receipts. In case of stock outs and no procument score is '0' | Medicines procured with out quotations/ no receipts maintained for dispensing | Medicines procured with proper quotations but no receipts maintained for dispensing | Medicines procured with proper quotations and receipts maintained for dispensing | 3
SECTION 2: SUPPORT SERVICES
Enabling Environment
18 | Involvement of different stakeholders in the project activities through constitution of Local Advisory Committee ( A committee comprised of members from brokers, associations, owners, other stakeholders of the project area) |  |  | ` | Verification of the LAC Register and interaction with LAC members(Byelaw if available) .LAC not constituted, then score is '0'. | LAC constituted but meetings not held in last 6 months. | LAC constituted meetings are held but members are not aware of their role. | LAC constituted and members updated on the project activities in the meetings in last 3 months | 0
Community response to the Program Services
19 | Project is adhereing to confidentiality norms |  |  | Confidentiality is maintained for the counseling sessions | FGD with the 10-15 truckers (suggested to conduct at the field). | Participants are not sure of confidentiality norms being adhered at the project level | Atleast 50% of the participants are satsfied with privacy and confidentiality at the project level. | More than 50% of the particiaptns are satsfied with privacy and confidentiality at the project level. | 1 | However, quality of Counseling is inadequate
20 | Community perception on project services |  |  | Are the truckers satisfied with the available services and services meet their demands. | FGD with 5-10% brokers/transporters/truckers (suggested to conduct at the filed level). | Atleast 40% of the truckers are convinced with the project services | 41%- 60% truckers are satisfied with the project services. | More than 60% or of the truckers are satisfied with the project services. | 2
21 | Adequate supply of commodities (condoms) |  |  | Condoms through Social Marketing provided by the Project | FGD with 10-15 community members (Suggested to conduct at the filed) | at least 50 % respondents reported that they are getting the condoms as and when they demand. | 51-75% respondents reported that they are getting the condoms as and when they demand. | More than 80% or of the respondents reported that they are gettingthe condoms as and when they demand. | 1
22 | Involvement of key stakeholders in program monitoring |  |  | Ability of the project to involve key stakeholders in addressing the issues relating to project activities and providing support to the project team | One to one interaction with atleast 3 stakeholders of the project. (suggested to conduct at the filed). | At least 1 stake holders participated and provided support in project activities | At leat 2stake holders participated and provided support in project activities | More than 2 stake holders participated and provided support in project activities | 2
23 | Involvement of Counselor |  |  | The counsellor should be sensitive while addressing issues relating to truckers. | FGD with the 10-15 community members (suggested to conduct at the field level). | Atleast 50% respondents reported that they are satisfied with the counselor/ANM | 51 to 75% respondents reported that they are satisfied with the counselor/ANM | More than 75% or of the respondents reported that they are satisfied with the counselor/ANM | 1
SECTION 1: BASIC SERVICES | [5 empty] | SECTION 1: TOTAL MARKS OBTAINED |  |  | 32
SECTION 2: SUPPORT SERVICES | [5 empty] | SECTION 2: TOTAL MARKS OBTAINED |  |  | 7
TOTAL SCORE | [8 empty] | 39
Name of the Evaluator

## Score sheet
Scoring Sheet Truckers
Name of the TI NGO: Naisargik ( The Organization for Natural Care |  |  | State:Gujarat |  | District:Ahmedabad
Calculation of score for stage 1
| Particulars | Maximum no. of indicators | Max. Score | Qualifying Marks | Qualifying Percentage
Stage1
1 | Organisational Capacity | 9 | 9 | 7 | 80
2 | Finance | 13 | 13 | 9 | 70
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Qualified/Not Qualified |  | Remarks
1 | Organisational Capacity | 9 | 8 | 88.8889
2 | Finance | 13 | 11 | 84.6154
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S NO | Particulars | No. of indicators Applicable for this TI | Maximum Score | Maximum weighted Score | Score obtained | Weighted score obtained | Percent of Score derived
1 | Basic services | 17 | 51 | 40.8 | 32 | 25.6 | 62.7451
2 | Support services | 6 | 18 | 9 | 7 | 3.5 | 38.8889
Total Marks |  | 23 | 69 | 49.8 | 39 | 29.1 | 58.4337
Name of the Evaluator