Evaluation Reporting format – C                                                   Annexure C

Confidential

EXECUTIVE SUMMARY OF THE EVALUATION

Profile of the evaluator (s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Prasanth. V | 94465 24414 prabold2000@gmail.com |
| Mr. Akhil | 70259 42761 akhilprakashmsw@gmail.com |
| Officials from SACS/TSU (as facilitator) | Mr. Jeeva, FO, TSU, 85890 31458 |

| Name of the NGO | IRCS, Wayanad |
| --- | --- |
| Typology of the target population: | FSW |
| Total population being covered against target: | 1080 |
| Dates of Visit: | Feb 8 – 9, 2016 |
| Place of Visit: | Mananthavady, Wayanad |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 88.5 | A | Very Good | Recommended for continuation and more focus has to be given community mobilisation |

Specific Recommendations:

- It is better to have a written administrative and HR system

- Recruit atleast one ORW from community as the project completed almost 13 years

- The risk assessment of counselors has to be shared with the concerned ORWs and plan accordingly

- Counseling follow ups has to be documented in a qualitative way

- Wrong entries in form A & B must be cleared

- CBO initiatives are to be given more importance

- Planned efforts should be taken for advocacy activities and use the goodwill of NGO

- Reports must be prepared in tune with the linkage of documents

- Regular verification of documents by the PM is essential

- Analysis should be conducted based on data available with the project

- In planning community participation has to be increased

- Social marketing of condoms must be given proper attention and the rolling fund can be transferred to CBO and CBO can take the profit

- Advocasy with the LSGs should be strengthened

- Suggesting to document the number of demo condoms separately

- Use the advantage of one staff who is a LSG member

- Linkage with JWALA project will be more useful

- Increase community participation

- KSACS can direct NGO to utilise the TA fund which was not using as the 2 posts are vacant. In such a situation the other ORWs can use that fund as the project area is so wide.

- It is good to have a ICTC at Panamarom

- Quality and quantity of inhouse training programs should be enhanced

| Name of the evaluators | Signature |
| --- | --- |
| Mr. Prasanth. V |  |
| Mr. Akhil |  |