Annexure C

Reporting form C

Confidential

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Helvis vazhapully | 9400780202 helvisv@gmail.com |
| Shiju Samson | 9745591965 shijumonranni@gmail.com |
| Officials from SACS/TSU (as facilitator) | Mr. Prajeesh Kumar |

| Name of the NGO: | District Jilla Punchayath- Malapuram |
| --- | --- |
| Typology of the target population: | FSW |
| Total population being covered against target: | 981 |
| Dates of Visit: | 10-2-2016, 11-2-2016 |
| Place of Visit: | Malapuram, Kavungal |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for continuation of TI with specific monitoring. |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- Observed the Fund shortage which directly influences program delivery - The project needs to give focus on appointing all vacant positions to avoid overload or overlapping of work.(1 –ORW) - Project need to give focus on age of PE s corresponding to new HRGs identified - The involvement of Board members of Dist Jilla Punchayath may contribute NGO’s role in TI or P D ‘s involvement. - Project need to focus more on “New HRGs”. (Identified as undisclosed sex work in remote area) - Project needs improve the achievement on HIV testing ( last year found less) - Community participation must be improved in TI project and CBO as the TI completed its 8 year. - Effort needs to be put forth for documentation by giving more importance to qualitative report and computerized documents

Name of the evaluators	Signature

| Helvis vazhapully |  |
| --- | --- |
| Shiju Samson |  |