Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to KSACS for each TI evaluated with a

Copy to NACO)

JAWARLAL MEMORIAL

SOCIAL WELFARE AND PUBLIC COOPERATION CENTRE ALAPUZHA

Introduction

Background of Project and Organization

Jawaharlal Memorial Social Welfare & Public Cooperation Centre is a social welfare voluntary organization registered in the state of Kerala under Travancore-Cochin Literary, Scientific and Charitable Societies Registration Act 1960 as No.K19/70. The registered office of the organization is at Thalayolaparambu, Kottayam District. Jawahar Centre implemented KSACS Targeted intervention programmes from 1999 to Oct. 2006 at Thalyolaparambu Panchyath, Vaikom Municipality and Mulakulam Panchyath successfully. Since November 2006 onwards Jawahar Centre is implementing KSACS Targeted intervention programmes among female sex workers in Alappuzha District.

Name and address of the Organization

Jawaharlal Memorial Social Welfare & Public Cooperation Centre

Thalayolaparambu P.O., Kottayam, Kerala – 686605

Phone: 04829 – 236175, 0477 - 2126222

E-mail: jawaharcentre@yahoo.com

Chief Functionary:

Ms.T.P Anandavally, Project Director.

Year of establishment

Established in the year 1989, as a society under KSR Act 1960

Year and month of project initiation:

This project was initiated in Novembr1st 2006

Evaluation team

Sree.Helvis vazhapully

Sree.Ajith.V.C

Time frame

3rd    – 4th, Feb. 2016

Profile of TI

(Information to be captured)

- Target Population Profile: -FSW

- Type of Project: - Core

- Size of Target Group(s):- 1404

- Sub-Groups and their Size:-No

Home Based – 588

Street Based – 816

Target Area

Alapuzha District.

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

Jawaharlal Memorial Social Welfare and Public Cooperation Centre is a well known Non Governmental Organization since 1987 in Kottayam District at Talayolaparambu. As a Non Governmental organization in social service sector, it extended their service in two districts in kerala. To the project Management of FSW TI project, organization developed a support system to the successful running of the project. Project Director has active involvement in the TI project. As Director of the project who has available for the monthly meetings, and monitoring almost all activities in the project.  Other Office-bearers of the organization are extended need base support to the program. Main operational area of the TI project is Alapuzha Municipal area. In addition to this   project having two sub-centers located at Haripad (mavalli madam ,Near Dhanappadi) and Cherthala (Xray Junction,)

Organizational Capacity

Human resources:

The human resources of the NGO maintain approved   staff strength in the project.

Staff consists of the following

designations:

Project Manager -1

ANM – 1

M&E Officer cum Accountant- 1

Outreach Workers- 6

Peer Educators – 20

The organization is fully committed to smooth running of the project, and it has given sufficient authority to the concerned project manager to initiate necessary action for the achievement of the target of the TI project. All the staff personnel in the project have basic knowledge on each component of the TI Program.

Staff Details

| Sl. No | Designation | Name | Qualification | From | To |
| --- | --- | --- | --- | --- | --- |
| 1. | Project Director | Ms.T.P Anandavally | President- JMSWPCC | June 2008 | Continuing |
| 2. | Project Manger | Maneesh c | M S W | March 2015 | Continuing |
| 3. | ME&A | Pradeepa | B.com | Nove 2013 | Continuing |
| 4. | Nurse | Sushamol | GNM | MAY 2015 | Continuing |
| 5. | ORW | Mrs. Ayisha Murali | PDC, Diploma in Nursing | June 2008 | Continuing |
| 6. | ORW | Mrs .Suma Devi | BA | June 2008 | Continuing |
| 7. | ORW | Mr. Gireesh Mohan | BA | July 2013 | Continuing |
| 8. | ORW | Mr. Sajeev | BA | Nove 2014 | Continuing |
| 9. | ORW | Mr. Arun Kumar | B.com | Nove 2014 | Continuing |
| 10. | ORW | Mr.Pavan Thomas | Plus Two | Sept 2014 | Continuing |

Capacity building:

Average staff in the project has two –three years experience in the project. So all the staff in the project have basic knowledge on component of the TI Program. The NGO has conducted induction training for the new Staff and PEs and it is one-day trainings on TI components. The Staff of the TI has received trainings from KSACS, STRC, TSU and on project components. ie, counseling, and TI trainings. The project conducting in-house training programs also along with the monthly staff meetings. The focus of these trainings was project components, Formats, data Analysis etc.

Infrastructure of the organization

The NGO has assured the necessary infrastructure support in the Project unit. The TI project has sufficient infrastructure including rented premises for conduct of the TI program. The DIC cum Project office located in the centre of the city with adequate space for office and Drop in Centre. The Office is situated within one kilometer radius of KSRTC bus stand and city centre and is easily accessible for HRGs and the TI has all the basic infrastructure and all are maintaining properly.

The DIC  is arranged in three spacious rooms behind the Office building with Toilet and kitchen facility, Space for resting , keep their belongings, mobile charging facilities are also available. IEC materials and condoms are available in the DIC.

Recreation facilities such as magazines, drawing and painting facilities, cooking utensils etc are also available. In addition to this, the TI has two DIC‘s at Cherthala and Harippad localities also.

Documentation and Reporting

The Jawahar FSW TI project maintains reporting formats as prescribed by KSACS. For the verification documents are available at TI level. The project maintaining the formats prescribed by the NACO but its quality to be improved up to certain extend. First and primary data collected the by the PE s/ORWs from the field were not properly write down in the field Dairy. Most of the ORWs daily reports end with single sentences only. It may be subjected to the loss of data / error when these data transfer to the Formats and reports. So reporting system need to be improved with quality. The monthly project reports (SMIS, STI-MIS) submitted to KSACS are and giving copy to the TSU.

III.Program Deliverables Outreach

Line listing of the HRG by category.

HRGs were registered with the mechanism of HRG master register / line listing. But a master file is not available with the complete line listing of HRGs.  Line listing is available with the project and that is provided to the ORWs/ PE s based on ratio. ORWS are keeping the line list as per their Target population. PE/ORW line list is the base of categorization and service planning. Mater sheet is computerized and coded. Dropout is recorded in the master sheet but need to re-structure the current target population is a must. But verification of the line list indicated that certain information must be re-validate or the real numbers to be captured properly.

Micro planning in place and the same is reflected in Quality and documentation.

The PEs and all ORWs regularly prepare the monthly plan at the end of the month. Usually it contains the details of place to be visit, Target of HRG to be contacted, due list and RMC/STI service delivery, condom supply. But it is mere process of monthly target base distribution of project plan. Category base and spot analysis not reflecting on project implementation plan. Micro planning is done as per the actual need of the community for particular month. So the quality of planning and documentation needs to be improved.

Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

As per the numbers presented by the project, they have achieved a little over 100%. Their target is 1400 FSWs whereas they have active population of 1404 as on April 2015 to Jan-2016 period. But project reported only 68 % HRGs are contacted regularly and providing any of the program services.

Outreach planning - quality, documentation and reflection in implementation

Outreach planning is based on project sites (Spot /PCU level) and population and category of HRGs in the site, PEs and ORWs panning their outreach planning weekly base in month. It contain site base service plan. Once in six months conducting PLOP but need more clarity on PLOP tool and its application. Spot analysis, contact Mapping, site load mapping and opportunity gap analysis etc not reflecting on outreach planning. The cross verification of Form– B to C, C-1 certain mismatch was identified .So the outreach planning quality and documentation needs to improve.

Regular contacts

ORWs have conceptual clarity about regular contacts.  And also peers are aware of the regular contacts and are able to report on the same on a monthly basis. They are also providing the information about the service delivery the HRGs in monthly base. The HRGs articulated that they getting services and commodities like condom as regular supply, ICTC referrals, STI service, counseling etc. Out of the   total contact of 1404 HRGs project provide regular contacts to 965 (68% )   When documents verified found 2% disparity in  regular contacts and the same should be clarified.

Documentation of the peer education

The peer educators maintain their daily diaries. Out of them 20 peer workers 4 of them are illiterate they maintaining the field dairy by the  help of ORWS( Format –B also).The PEs daily dairy contains only information regarding date and place visited and name of the HRGs met and kind of service given. And similarly PEs Maintain the number of condoms distributed to the HRGs during their daily field visit. When verified the Peer workers dairy no unanimity was found. Peer dairy as means of first and primary data collection channel from HRGs its quality of data entry to be improved. Maintaining format –B is considering as primary data for MIS through C,C-1.etc.

Quality of peer education- messages, skills and reflection in the community

PE selection method of the project is need to be re – strategized. When compare to the average age of HRG group, towards the age group of the PE is found very high that is 35 to 45 ranges. Some of them (PE s) are found age 50 years or above.  During the FGD with HRGs an average age found 25 to 30 years. This age representation is not found in the peer group. Some of the PEs was 6 to 7 years of experience and the growth was almost stagnated.  Proper peer rotation must be maintained.

During discussion with PEs they were able to explain about HIV, STIs, linkage with different services like clinics, ICTC and ART. They were comfortable in explaining about the four ways in which HIV spreads and about condom distribution. They also mentioned the follow up on RMC once in 3 months and ICTC once in 6 months. They also know the importance of correct and constant follow-up ICTC.  They were able to relate the risk factors to services or condom usage but need clarity on risk and vulnerability classifications according to the micro-plan. Documentation to be improved at all levels starting from PEs for better assessment and service delivery.

Supervision- mechanism, process, follow-up in action taken etc

The project has developed its own system for the supervision and monitoring of proposed activities .project manager, ME&A are taking the major role in monitoring of the entire outreach activities. The monitoring or supervision is on weekly and monthly basis, analysis of target achievement and feedback is being given to the project manager and discussed in the review and planning meeting. At least one field visit is made to each ORW’s site and combined field visits are also planned. Though they have maintained the details of activities and the places visited, the documentation does not contain details on the actual type of supervision done, feedback/suggestions provided in field level but not documented. The process of supervision also needs to be strengthened and proper documentation and follow up also needs to be done.

IV. Services

- Availability of STI services - mode of delivery, adequacy to the needs of the community.

The project having STI management system in place but currently it is more dependent on Govt. Clinics. For the female sex workers, Static clinic in the project was functioned in previous years. In connection with the STI Care services, the project adopted the strategies such as intervention through Govt: clinic, referral to existing governmental and non-governmental health care system. The project staff having a good networking with governmental health care system. General Hospital, Aleppy, T D Medical College, Vandanam, Women and Child Hospital, Beach, Aleppy, PHC Manamcherry, CHC Chettikade, PHC Kalavoor, Aleppy, Medicare clinic, Palathuruthy,  Taluk Hospital, Chertala,  PHC Thanirmukom, General Hospital Kayamkulam etc

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Currently there is no clinical facility alone with the FSW-TI. So STI cases are referred to the nearest government clinic which is nearest to target area. In this network with Govt. Hospitals, all STI clinical service is made available to the HRGs.   As Govt .Hospital basic standards for STI clinic was maintained by the hospital and assure the Privacy. Stock register for STI Medicine and VDRL Kits is maintained but observed short of stock in many occasions during the last phase.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

STI Treatment is provided to HRGs based on the assessment by the doctors where the HRGs are referred. Grey, green and white kits were seen to be widely used for symptomatic cases and those who are provided STI drugs are also followed – up in a week’s time as they will visit the hospital after one week. Similarly ICTC referral is also done periodically and followed up by the ORWs through the PEs. HRGs are referred to ICTCs and PHCs.  But the ORWs are referring the HRGs to the centers for testing and collect the referral slips. Whenever any reactive case identified they are immediately referred to the ART centre.

So far, the project has referred three HRGs for TB diagnosis and one identified as TB positive.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

Treatment register, referral slips are maintained for RMC, STI and ICTC. Patient wise referral slips maintains. Based on the due, overdue list,  the ORWs give referral slips to the STI clinic/ICTC.  RMC and STI referral information is available in the referral slips maintained by project which is updated in Form – F register. The counselor updates the Form F register and from that updates Form H register. Last year no STI Cases were reported.  Stock register for STI Medicine and VDRL Kits is maintained. Procurement of medicine endorsed by KSACS guide line and supporting documents filed.

Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Condoms are distributed through staff and PEs and Condom out let / depot or social marketing in the project. The TI project ensures the regular supply of condom to the HRG population through direct channels and Non-traditional outlets includes petty shop, comfort stations, Brothels of house based SW’s, house boats, lodges, Autos etc are used for condom supply. The project has also brainstormed on the need to have alternative condom distribution mechanism with the PEs and this need to be initiated to make PEs understand the need to create alternative mechanism. The project finds difficult to keep condoms in the stake holder’s houses of the house based sex, alcohol intake of HRGs and difficult clients. The monitoring of condoms limited to monitoring distribution/availability through the PE’s and outlets.

No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

As a Condom programming, project ensuring the availability, accessibility and to ensure the correct and consistent usage of condoms, the project is supplying free, social marketing (Direct and indirect distribution). The following are the methods for monitoring of condoms:-

Monitoring distribution/availability through the PE’s and Monitoring through condom dept,  high risk HRG’s individual tracking through PE’s.

According to the consolidated data available with the project they have achieved around 94% of their project’s condom demand in 2015-16, and around 95% up to October in the year 2014-15. The supply is shown as per the weekly demand. Total requirement of condom is 110063. Supply of condom is 103804. Free condom-85257,  social marketing 18547. The project finds difficult to house based sex workers, So project initiated to suitable strategy for the condom programming among house based   HRGs which is congenial to the this group.

There is no disparity in maintenance of the condom stock register with the physical stock.

Information on linkages for ICTC, DOT, ART, STI clinics.

ICTC referral is done periodically and followed up by the ORWs through the PEs. HRGs are referred to ICTC.   Whenever any reactive cases are identified they are immediately referred to the ART centre. In the cross verification in the ICTC register PID numbers for some of the referrals are tally with project referrals. No disparity is found in the ICTC referrals. Till now the project has referred three HRGs for TB sputum test and one case identified as TB positive.

Referrals and follows up

ICTC referrals are mostly done by ORWs to the concerned centers. The project team gives the referral slips to individual HRGs in the field and asked to come to the nearest centre. Regarding RMC and STI referrals, the ORWs give referral slips based on need HRG undergo RMC or STI testing. The HRGs attend the clinics on different dates which are documented in the referral slips.

V. Community participation

Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents.

It is reported that during the last one year, the major part of community participation was happened through community committees, CBO and other events. No events conducted by the project mainly for the reason of financial constrains. But community based CBO named Swanthwanatheeram conducts few welfare programs like school kit distribution program to the school students by the support of the Project. This program creates an opening to community that they addressing other issues than HIV. So that CBO also support the enabling environment to the project and it shows the happiness of HRGs in social issues.

VI. Linkages

Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages with ICTCs, STI clinics and ART centers found good and the outreach team having good rapport with the linkages available to program. HRGs are referred to the centre individually. Project established very good net working system with all govt. Hospitals and clinics for STI management program in the project area or district level target sites surrounding the project spots.

Percentages of HRGs tested in ICTC and gap between referred and tested.

Verification of ICTC referral / tested data for the period April 2015 to Jan 2016 indicates that out of 1404 HRGs in line list referred, 917 were tested for HIV in first time 66%.and 162 in second time 16%.Eventhouh the ICTC referrals and testing rate is satisfactory wide gap is found the second time testing. Project to be rectified this gap in future.

Support system developed with various stakeholders and involvement of various stakeholders in the project.

The project conducted networking and advocacy programs with the existing power structure includes health care, Police, NGO’s etc.  During the AIDS day campaign, the project could gain support from Rotary club, railway office at Alappuzha etc. The results of the environment support programs were ended in community empowerment, increased sustainability, increased community ownership, and reduced marginalization, strengthened services and systems.  But project need to keep a verifiable reports or documentation in this regard.

VII. Financial systems and procedures

- System Planning:  Existence and adherence to NGO-CBO guidelines/any approved systems by SACS/NACO supporting official communication.

The Jawahar TI has made proper planned for financial approval. KSACs written policies are followed as guidelines of financial management. Project has made well communication in writing with KSACS officials. And communications are being made with program officer also.

- Systems of Payments - Existence  and  adherence of payments endorsed by SACS/NACO availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of setting of advances before making further payments.

The Jawahar TI has maintained accounts system,  Project have  the practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers as per the guide line of KSACS/NACO  Competitive rates to be obtained by inviting quotations for  purchasing the fixed assets like computer etc.

- Systems of Procurement- - Existence  and  adherence of systems and mechanism of procurement as endorsed by SACS/NACO adherence of WHO-GMP practices for procurement medicines, systems of quality checking.

System of Procurement is endorsed by the guide line of KSACS, Competitive rates to be obtained by inviting quotations for purchasing the fixed assets like computer, condom   Purchase etc.

- Systems of documentation- Availability of bank accounts (maintained jointly, reconciliation made monthly basis), audit reports.

The Jawahar TI has maintained bank Account with signing authority of Project Director.  Practice of maintain reconciliation statement on monthly basis, The Financial Audit has been made by for the financial year 2015-16 with KSACS was found no disparities. Above the 5000 rupees payments are made by account payee cheque. Bills and vouchers were properly filed.PE incentives and Staff personnel salary also paid by cheque. Financial management of the project is transparent and good (Only once the bill paid y cash is more than Rs.5000/ during the community event)

VIII. Competency of the project staff

Project Manager

Mr. Maneesh C, Project manager received training by STRC but having only ten months experience in FSW- TI field, the knowledge about the NACO TI, FSW TI proposal and performance indicator is very minimum. As a project manager he is not working with a specific monitoring plan, the team working along with him oriented to work with outreach implementation plan. He maintains a visit plan on each working day. The manager is not familiar with the Proposal or any guideline which adherence to the NACO-TI. Daily diary maintains but with minimum details. Computerization and management of data needs improvement and there are many differences in monthly reports and SMIS/CMIS. Conduct review meetings in week/ monthly and documenting the same without ensuring project director’s recommendations. Monitoring of the project is limited to oral instructions only. Coordination with all kind of staff members is visible. Verification of project documents limited to initials, Network with linkages, other NGOs and other TI project also found minimum. Knowledge on NACO Operational Guideline must be improved immediately if he is continuing with the project. Advocacy initiatives are not reached up to needs and not documented properly. P M needs specific training for TI management.

ANM/Counselor

ANM, Ms.Sushamol, GNM having only 8 months experience in FSW-TI, she started her HRG counseling career in TI only. Clarity on risk and vulnerability found good but less clarity on risk assessment and other harm reduction strategies. Counselor as such trying to do the STI, follows up and safe sex or condom use motivational counseling’s also. STI counseling register maintain properly. Maintenance and updating of data and registers related to clinic found good.

Counselor need improvement or trained in the following areas.

- Training on STI counseling BCC strategies.

- Training on NACO guidelines and TI proposal.

- Training on quality reports and documentation.

M & E A

MEA  Ms.Pradeepa B.com, working from 2013 onwards with the project. She was experienced in accounting and administrative structure but need improvement in monitoring and evaluation techniques and systems. Daily diary maintains but with minimum details. Computerization and management of data needs improvement and there are many differences in monthly reports and SIMS/STI-MIS. Review meetings in week/ monthly and documenting the same with minimum details only and Monitoring of the project is limited to oral instructions only evaluation part need to re defined in project level.MEA must ensure the coordination with all kind of staff members and reports is visible but need more clarity on it. Verification of project documents limited to note down numbers to SMIS and other documents. Need training on M&E system, Data analysis and management.

ORWs

ORW’s knowledge about target on various indicators for their PEs is found good. Currently ORWs working with implementation plan. Outreach plan for each hot spot not in place but need more clarity on micro planning and outreach plans, Orientation on Hotspot analysis and other tools are found but not done in last year, conducting the weekly review meeting with peer educators in the field but it was not documented properly. Knowledge on HIV, STI, ART & ICTC is satisfactory. Need more clarity on STI managements, providing support to PEs in field level activities but not documented properly. Form-D need to be defined All documents and formats of PEs are up dating by ORWs only but with the consultation of P E s. ORWs need more clarity on Qualitative reports, Format-D, ORW’s level program planning. Community mobilization and collectivization components need to be strengthened. There are disparities found between Form B and form C, C-1. Quarterly risk and vulnerability should be analyze and needs to be document in detail.

During the evaluation, it is observed that few experienced ORWs are very reluctant to submit their reports and formats to M & E for preparing MIS/SIMS  in time, the same was reflected in M & E work during the review. So that NGO may take appropriate disciplinary action to ensure professional discipline in the project.

This evaluation team strongly recommends staff appraisal with scientific tool.

Peer educators

There are about 20 peer educators in the project currently. All the PEs in the project has basic knowledge on HIV and its transmission and other component like condom /crisis / community mobilization etc. of the TI Program. But need clarity on risk and vulnerability classification, IPC and BCC tools.  The PEs is rational to the typology but not matching with age of HRGs. PE s articulated that typical street based sex workers operating in the field. Age representation of PE is not cop-up with average age of Target population. Certain PE has 6 to 7 years experience in the project. PEs turnover is not properly maintained by project.

Project needs to consider the age of PE s to the community’s age or below 30 years.(at least 50 % needed)

Outreach activity in Core TI project

Jawahar as a senior FSW TI Project, outreach activity in core TI program is not compromise the age and growth of the project. When Interact with PE team and ORWs, the output of the outreach activities not reflect or heightens the achievements in the service uptake in the field. Outreach plan is not reviewed properly with plans. Monitoring of outreach is based on weekly / monthly review and analysis the entire team needs orientation and clarity on micro plan. PLOP not done properly and tools found mismatch with other ORWs among the team. Clarity on Form- B, C and C-1 to staff and PEs are very low.

The project’s outreach plan to be strengthened as the evaluation team found gaps in their outreach plan. The team needs to improve their planning and monitoring method with quality feedback and documentation during their visits.

X. Services(Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs)

JAWAHAR - TI project contracted to cover wide area in Alapuzha district. The service uptake of project found satisfactory among HRGs interacted during the evaluation. HRGs articulated during the FGD show the acceptance of TI among FSWs. the interacted service providers are also aware of their presence in the intervention. The team visited ICTC, STI Clinic as part of evaluation, they informed about the regular visit from the project office and referrals done by them. Project established a close relationship with Linked /ferral centers. The feasibility of, ICTC, STI Clinic and documents, the referral slips kept with the centre’s signature and seal.

XI. Community involvement.(How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc)

FSW community participation in project activity is through CBO memberships, PEs and few members in the different community committees. CBO membership is observed good but need to accommodate new members too. the process for considering community’s views in program planning is still very minimum. NGO’s technical support to the CBO should be strengthening to the overall development of community as well as CBO. The community team initiates few programs independently but it is limited.

The PE s involvement in program delivery is visible through format –B and DIC meeting, Most of the community committees are not meeting regularly to achieve its objectives.  As an NGO completed its ten year in the TI should be re-structured its community participation in all program components. PEs is found to be implementing the project activities after obtaining the community opinion. Communities have also informed about getting sort of government services.

CBO

“ Swanthanatheeram” the CBO formed and registered in 2007 and operates 2 bank accounts in two nationalized banks and secretary and treasurer are assigned for operating bank tractions. One account is exclusively for the small scale savings called “CHITTY”.  The governing body of santhwanatheeram consists of 11 executives of which 5 are being elected through election. The executive body consists of 5 office bearers and six nominated executive members. The CBO was formed with only nine members and presently a membership of 991 but it’s not visible in activities.

XII. Commodities

Condom Programming:

Condom programming is one of the major components of the project. For the effective condom program and for ensuring the availability, accessibility and to ensure the correct and consistent usage of condoms, the project is supplying free, social marketing (Direct and indirect distribution)

Condom distribution:

| REQUIREMENT 110063 | DISTRIBUTION |  | TOTAL 103804 | % 94% |
| --- | --- | --- | --- | --- |
|  | FREE | SM |  |  |
|  | 85257 | 18547 |  |  |

Project periodically conducts the condom demand analysis for avoiding the gap between demand and supply.

XIII. Enabling environment

Networking and advocacy programs:

The project conducted networking and advocacy programs with the existing power structure includes health care, Police, NGO’s etc.  During the AIDS day campaign, the project could gain support from Rotary club, railway office at Alappuzha etc.

The evaluation team strongly suggests re-structuring the advocacy policy and programs in the limelight of issues aroused from local population leads to the friction at DIC and Office.

The project needs to keep verifiable reports and documentation towards the advocacy and networking programs.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

Project initiated certain social protection scheme for the welfare of Target community.

- Savings schemes,

- Income Generation Programs ( Soap powder Production and Marketing, Floor/toilet cleaner Production and Marketing, Dress Materials Marketing)

- Personality development programs.

- Legal aid support through FSW-TI

- Other Social entitlement programs support given for taking Election ID , Ration cards, Bank account etc.

XV. Best Practices if any

Nil