Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

Background of Project and Organization

Socio Economic Unit Foundation was established in 1987-88 following the plan of operation prepared by a joint Indo-Dutch-Danish Mission in 1984 to integrate social inputs in the rural water supply and sanitation with community participation in the State of Kerala. It became Socio-Economic Unit Foundation in 1996 under Societies Act and extends its area to other States. SEUF is an agency accredited by the Government of Kerala to take up Water and Sanitation programme, Capacity Building trainings, Gender initiatives and Solid Waste Management. It has its head office at Trivandrum, regional offices at Kozhikode, Thrissur, Kottayam and Alappuzha and project offices at Kannur, Kollam, ernakulam and Pathanamthitta.

Name and address of the Organization 	: Socio Economic Unit Foundation

Chief Functionary			:  President

Year of establishment 			: 1978

Year and month of project initiation	: 2010

Evaluation team 			: Sri. Domi J (Team leader)

Smt. Renjith Abraham (co-evaluator)

Time frame 				: February 12-13, 2016

Profile of TI

Target Population Profile		: FSW

Type of Project: 			: Core

Size of Target Group(s) 		: 1400

Sub-Groups and their Size 	: Street Based –550					  House Based-   1161

Target Area 	:Attingal, Nedumangad, Varkala, Thiruvananthapuram

SEUF started implementing FSW Suraksha project since November 2010 in Trivandrum. The intervention covers 4 sites and the targeted population is 1400. The sites covered under the intervention are Trivandrum Corporation, Nedumangadu , Attingal , and Varkala Muncipalities. Looking back into the history of the project we can easily understand that FSW intervention in Trivandrum city was initiated by SOMA in 1998.  After running the intervention for about 8 years SOMA handed over the mantle to the Mythri Vanitha Sangam, CBO of FSWs formed and groomed by SOMA, in December 2006.  Mythri has been implementing the project with a target of 2870 FSWs until September 2010. Owing to managerial issues concerning the CBO they were not able to run the project smoothly after September 2010 and KSACS contracted SEUF to take charge of the project from November 2010. SEUF continues to implement the project in this phase too with a population of 1400 FSWs, also focusing on the CBO strengthening process.

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Project Director attends the meeting.  The project office cum DIC cum clinic has been shifted to the new office Pattom at Thiruvananthapuram City is convenient.  PD shares a good vision on the project and has a good outlook on the HRGs

II. Organizational Capacity

1. Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community and a large staff turnover

Out of 6 ORWs required, 5 are on board and one who left the project isn't replaced because of the direction from KSACS. Also, 20 PEs are onboard against the required 23. Three PEs are not replaced because of the directions from KSACS and TSU.  All positions except those directed by the SACs in the project are filled.  One ORW and 3 PE positions have been reduced due to the financial measures.  None of the PEs belong to below 30 age group.

Morale of all the category of staff including the PEs is very low due to the delay in salary disbursal.  All of them strongly expressed dissatisfaction and helplessness over the plight meted out to the TI staff and PEs in this regard.

The team is of the opinion that the current salary structure is grossly insufficient and does not meet the requirements of the job, the risk involved and the qualification.

2. Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

All staff have attended the induction training by STRC. All the PEs seem empowered enough to undertake the peer education and other capacity building of the HRGs.

3. Infrastructure of the organization

Infrastructure provided by the KSACS is well codified, labeled and maintained.  The office building is accessible for the community members.  The office has computer, and other peripherals with internet access.  The office is spacious with sufficient ventilation and other physical amenities.

4. Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

Good.  Dynamic Line listing has been updated.  All registers as per SACs protocols are kept by the project.  Statutory reports are also sent regularly.  SACS may send formal communication in case of any re fixing of the target of the project.

Monthly meeting minutes are descriptive enough, ORW diaries are also descriptive enough to reflect the work under gone. Other registers of STI, ICTC testing with slips are systematically recorded and cross matched.

PE diaries are mostly filled by the ORWs themselves.  This may lead to mal practices in terms of the services given

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Line list showing the level of risk in colour codes available in the project.  Categorization in terms of house based and street based is also done.  Risk based categorization is also done systematically.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

Not applicable

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

Not applicable

- Micro planning in place and the same is reflected in Quality and documentation.

Micro planning is present but at times they are not used by the ORWs.  Micro planning is done for every week in the weekly meetings where ORWs take stock of the condom supply, due HRGs for ICTC, STI etc.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

The target of 1400 is already contacted and registered in the project.  Ten have dropped out and 70 new identifications added. Now the project addresses 1460 HRGs.

Overall not only quantity, but quality of coverage is also good; except for the counseling services.

- Outreach planning – quality, documentation and reflection in implementation

Outreach planning by ORWs is good.  Outreach planning is done weekly.  It is well reflected in the ORW and PE diaries.

- PE: HRG ratio, PE: migrants/truckers

1:60 maintained.  Current ratio is 1460/20= 73.  The ratio increased as 3 PEs have been cut and new identification (70) in the year.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

Only 1395 out of the 1460 HRGs are regularly contacted. 95.6 percentage contacted. Counseling is the single services not reached by most of the HRGs.  Condoms, ICTC, STI check up are the highest in uptake.    The achievement is the result of the active PEs and ORWs.  There was no complaint from the community regarding the supply of condoms or STI treatment.

23 HRGs still not contacted with ICTC/ STI/ counseling.

- Documentation of the peer education

Documentation of the PEs is heavily supported by the ORWs.  PEs don’t do it independently.

- Quality of peer education- messages, skills and reflection in the community

PEs are long standing.  Community is largely aware of the essentials, Community’s skill in condom use are also up to the mark.

11. Supervision- mechanism, process, follow-up in action taken etc

Few ORWs show good standards in putting down the achievement of the PEs and do good follow up.  But others need to improve on it.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

The main mode of STI services is through Govt. Hospitals.  1255 out of the 1460 (target 1120 for ten months) have been tested for VDRL.  Services seem to be adequate. But the counseling services are affected because they do not meet the project counselor since they attend the clinics in Hospitals.  The counselor could provide services to only 498 HRGs.

There must be more linkage with the Pulari clinics and the TI.  There are only two Pulari clinics in the vast district like Thiruvananthapuram.  So the HRGs, even new contacts do not receive proper counseling by a professional counselor or receive presumptive treatment. The untrained doctors in the Govt. Hospitals naturally refuse to provide treatment to the asymptomatic HRGs.  Effective advocacy with the Govt. Doctors seem to the only way but practically doctors do not take any advice by non medicals on prescription.

Pulari counselor may be directed to counsel the HRGs when they attend the Pulari clinics in the Hospitals.  Project level STI clinic is not used optimally.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Location is good.  Clinic in the DIC is not utilized optimally.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

There were 70 new identifications in the period; 21 has symptoms and were treated timely in the Govt Hospitals.  Out of the 49 asymptomatic New HRGs only 4 have received PT.  The doctors in the Pulari clinics are not trained in the SACS protocol.

Among all HRGs 39 were VDRL positive and they were given treatment.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

Documents available.  Slips had the ID number of the GRGs and were verified with the ICTC and Pulari.  The slips are collated ORW wise and month wise.  Medicines were not procured during the period.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

There are 23 outlets maintained. 20 PEs work as nontraditional outlets. Only 3 outlets are traditional.

This is grossly insufficient to cater to the demand.  The project need to take more initiative in external relations and linkages to connect the position the project for effective service delivery.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

132630 condoms distributed against the target of 121580.  Outlet-wise distribution data available.  Entries in the condom register do not tally; outgo is more than the total condom received.  Even SM condoms do not tally.  Money for the SM condoms have not been collected throughout the year. According to the project manager, they will the cut from the TA of the PEs; but as the TA not disbursed for the last few months, they were unable to recover it.  No money has been collected on this account so far.

- Information on linkages for ICTC, DOT, ART, STI clinics.

There is effective linkage between the centres.  Linkage with the ICTCs is good.  No case of TB has been detected among the HRGs.  General awareness has been given to the PEs and staff on the signs and symptoms of TB.  All the 7 existing HIV Positives are linked to the ART.  All the STI cases provided treatment either in the Govt. Hospital or at the project level.

- Referrals and follow up

Referral is good and documents maintained.  ORW keep a good track of the due services in the weekly project level meetings and they are being shared with the PEs in the field every week.  Referral slips show that the system is working and follow up is made on all due services.

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

350 HRGs are members of CBO named ‘Maithri’.  The CBO lost the initial enthusiasm to organize get together of the members.  CBO has taken some IGP activities like soap making; none are working well.

Although the community members are aware of the need to have a CBO and IGP activities, due to internal squabbles among the members, they are not even able to meet.  Annual elections are due for some years.

The project needs to motivate the CBO to organize more events and collectivization and conduct regular elections.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

CBO leadership does not have any participation in the project activities.  There are a lot of improvement in this respect to mobilize the CBO members; group formation, development and management. The TI staff need to initiate fresh actions for strengthening the CBO.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

There is effective linkage between the centres.  No case of TB has been detected among the HRGs.  General awareness has already been given to the PEs and staff on the signs and symptoms of TB.  All the 7 existing HIV Positives are linked to the ART.  All the STI cases provided treatment either in the Govt. Hospital or at the project level.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

1437 of the 1460 target were tested at least once in the ICTC.  835 were tested once, and 602 tested twice. 23 have not been tested so far.  Given that, the test kits were not available for around two initial months, the performance is good.   In the rest of the two months, the untested 23 HRGs need to be tested as priority action.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Crisis management committee is very well in place.  The committee has attended all the cases that come up to them in the period. Project manager takes a lead role to meet the Police officials in cases of harassment.

However the support system seems to be weaker considering the good will of the NGO and legacy of the project.  The interruptions in funds for mobilization efforts seems to have affected the general visibility and built up.

VII. Financial systems and procedures

Financial systems and procedures

  - Systems of planning: Existence and adherence to NGO-CBO guidelines/any approved systems endorsed by SACS/NACO-supporting official communication.

The execution of activities and money expends are in per with the plans which strictly adhere to the system endorsed KSACS

  - Systems of payments- Existence and adherence of payments endorsed by SACS/ NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

The organization follows the system endorsed by KSACS i.e., they maintain printed and serialized vouchers, approval systems, stock register is maintained and kept updated and no issues has been found related to the settlement of advances.

  - Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/ NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

Procurement of medicines has not been made from external agencies. Also, during the period no incidence of procurements happened.

  - Systems of documentation-Availability of  bank accounts (maintained jointly, reconciliation made monthly basis), audit reports

Separate bank account is available for the project and reconciliation has been made monthly. The documentation system prevailing is good and satisfactory. Audit reports are documented and recommendations are taken into consideration.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

As per KSACS requirement.  The project manager has initiative and leadership.  The project has a quarterly and monthly plan finalized in the monthly meetings.  Data are computerized. Review meetings conducted periodically.  Advocacy initiatives are generally need based.  Project has not done power analysis and does not have an advocacy plan based on that.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

The counselor possesses considerable knowledge and is skilled. The performance is up to the mark. She may improve with more experience in the project.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

For ANM, adequate abscess management skills.

Not applicable

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

ORWs are experienced.  They are aware about the issues of all their individual HRGs. The performance of some ORW from the community was also exceptionally good in terms of knowledge, planning, maintenance of registers.

All the ORWs have hotspot wise outreach plan for every month.

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

The team could meet all the 20 PEs in place and the 3 PEs dropped.  They possess fairly good level of knowledge, attitude and skill for carrying out their task.  They are particularly well knowledgeable about the symptoms of STIs, service centres and facilitates.

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

Not applicable

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritise the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to  manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

Not applicable

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

Not applicable

VIII i. M&E officer

Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant Tis are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

She is able to provide information and also knowledgeable about the relevance of the concepts.  Keeps the dynamic line list updated.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

The outreach in the project is generally good.  They plan along with their ORWs for the hotspot meetings, identification of people who have not availed any services etc.  Outreach sessions are conducted but not according to the plan. Stakeholders are aware of the sessions.  The evaluation team feels that the more than the sessions, the IPC with the PE/ ORW create more awareness.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stakeholders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

Not applicable

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs

ICTC uptake is 1437, STI clinic footfall is 1255 and 1147 got regular medical check up against the target of 1460.

Quality of service is doubtful as most of the HRGs are not counseled at the project level or at the ICTC/ Pulari.  However the HRGs are well aware of the need to use condoms, periodic ICTC/ STI testing, regular medical checkup etc.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

Some of the CBO leaders are too empowered that they are not able to work as team.  Collectivization efforts by the CBO is very disappointing. CBO election may be conducted to further strengthen the organization.

Participation of the community in planning is very low, no monitoring by the community in the implementation or advocacy measures.  Activities are largely project driven.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Condom requirement analysis done in April 2015. Demand gap analysis done in January 2015 lately.  Hot spot level planning done. Social Marketing Condoms have around 5 percent uptake compared to the free condoms.  There is a lot of scope for improvement in the maintenance of Condom register. There are mismatches. Mismatches found even in the entries of Social Marketing condoms.

Scope for improvement in the sale of social marketing condoms.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Power analysis not done.  The advocacy plan and implementation report suggest that they are not just need based but are crisis driven. There are no planned exercises for advocacy.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

Nil

XV. Best Practices if any

Nil

Sd/-

Domi. J

Team Leader, Evaluation Team

For SEUF, Thiruvananthapuram