Annexure: B

Reporting Format-B

SINDRP FSW Project, Thiruvananthapuram

- Introduction

1. Background of Project and Organisation

SINDRP is an Voluntary Organization formed in the year 1982 by a group of like minded people experienced, and integrated in development work among the marginalized poor. SINDRP is working with many community development programmes in collaboration with various funding agencies especially Central Social Welfare Board & State Social Welfare Board.  SINDRP is registered with Government of Kerala under the Societies Registration Act XII/1955. It also registered under the foreign contribution Regulation Act of Govt. of India. The society shall act as facilitating agency and enable the disadvantaged, marginalized and neglected rural masses to be empowered to act as subjects of developmental process by way of capacity building, to accurse skill for women to equip themselves (livelihood opportunities, health support and educational support services.

SINDRP is implementing the TI in Thiruvananthapuram since 2002. During the initial phase, the project addressed sex workers, other risk groups like construction coolie labourers, client groups like auto/ taxi drivers, truckers and MSMs. During the 2008-09 phase the intervention was limited to FSWs and MSMs with a population of 2750 FSWs and 575 MSMs. From 2009 onwards the project was addressing only FSWs. The current population is 1250.

2. Name and address of the Organization:

SINDRP FSW project

Angelo Building

Poovar Road

Neyyattinkara

Thiruvananthapuram

0471 2223990

sindrpsuraksha@gmail.com

3. Chief Functionary:   Rev. S. Satya Das, Project Director

4. Year of establishment: 1982

5. Year and month of project initiation: February 2002

6. Evaluation team:

Sathikumari.P

Raghi Bhaskar

7. Time frame: 2 Days

1 st & 2nd of February 2016

B. Profile of TI

1. Target Population Profile: FSW

2. Type of Project:  Core

3. Size of Target Group(s):

Target based on their proposal 2014-2016 is 1500. In 2014-2016 they have cut short the population into 1250. Now the registered population is 1307 including  57 new identification.

4. Target Area

- Neyyattinkara-Balaramapuram

- Parassala

- Vellarada

- Malayinkeezhu-Kattakada

- Poovar-Vizhinjam

C. Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The NGO members are involving in the project activities especially in advocacy programmes. Project Director himself involving in program monitoring. Project Director is representing for the NGO and he has attended all the monthly meetings of projects. PD is involving in day to day activities and monitoring of the project. Advocacy activity by the NGO found good and visible.

2. Organizational Capacity

- Human resources

All positions except the post of project manager have been filled. Currently the project team consists of

M& E cum accountant-1

Nurse -1

Outreach workers-5

The organization has HR policy & the appointment letters were issued along with the detailed job descriptions to the staff of the project. The attendance register was found in place and leave file maintained and majority of the leave letters are there. NGO gives induction training to new staffs immediately after recruitment.. The conceptual clarity of staff especially ORWs should be improved. The ratio between ORW-PE-HRG is maintained as per the norm. In the absence of Manager, M&E cum accountant is taking overall management of the programme and sometimes this leads to compromise the roles and responsibilities of M &E.

- Capacity building

Training register and training reports are maintained by the project. During 2014-2015 the project conducted training for the new PEs. Apart from that team gets training from KSACS/STRC. They opined that recently the number of capacity building programme by KSACS/STRC has reduced. There is no followup training at the project level.

c. Infrastructure of the Organization

Visibility and access of the project office is good. It is located near to the main bus stand and it makes easy access to the office. The office is placed in the 1st floor of the building. The 2nd floor functions as the DIC and is exclusively for the community. Recreation facility such as television is there. Day time HRGs come and take rest in the DIC. Sufficient furniture is there and someone is provided by the NGO. Office is pasted with IEC materials, concepts/definitions and indicators.

d. Documentation and reporting

Most of the formats are adhered to NACO guidelines. ORWs are maintaining the field diaries with minimum details. Absence of Project Manager has affected the cross verification of documents. The M &E is not cross checking the reports and the team is not able to identify any trace of corrective measure taken by the supervisory staff towards the improvement of reports. Some of the documents have signed by M&E but there is no action taken markings are visible in any of the formats or reports. There are mismatches between Form B and Form C, HRG master register in place and need updation. All the new HRGs registered are not entered and all the dropouts are not marked in the HRG master register. Positive HRG files are in place, but there is no follow up .Monthly review meeting & weekly review meeting reports are available. Service tracking sheet insisted by TSU is available in the project. Lack of clarity in filling formats is visible among ORWs and technical inputs from support agency are needed.

Program Deliverables Outreach

Line listing of the HRG by category.

Line listing of the HRGs are available but periodical updating needs. All the new contacts registered and dropout details are not entered in the master register.

Micro / Outreach and project planning

The project prepares PLOP in quarterly basis as out reach plan and form B is used for micro planning. There are some confusion in planning of risk and vulnerability among ORWs. Service tracking sheet is used for giving outreach services and the same is using to track the services. Condom requirement analysis is done on quarterly basis. The Nurse gives dues and over dues based on tracking sheet. There is no power analysis/stakeholder analysis and advocacy plan and the staff are  unaware about the plans in advocacy level.

Coverage of target population

1307 HRGs registered against the target of 1250.

PE/HRG ratio:

There are 21 PEs maintaining a ratio of 1:40 on an average

Regular contacts

According to the PEs the regular contact is only 50-60% of the total registered HRGs. The project document shows more than 90% regular contact and is not genuine.

Documentation of the peer education

Majority of the PEs is doing documentation Format – B with the help of ORWs only. So once they completing with the help of ORWs during the weekly PE review meeting, the same was entrusting to ORWs only. Few PE s are maintaining field diary.

Quality of peer education-

There are 20 PEs in the project and the knowledge about the program service is good. PEs are experienced, sensitive, skilled and motivated.  However majority of them are not able to explain risk and vulnerability. Majority have no clarity on form B. out of the 21 PEs only 4 comes under the age group below 30. According to the project house based sex workers are more compared to street based,but the ratio of PEs maintained for house based is less.

Supervision

Regular review meetings (weekly & monthly) and field monitoring are the major mechanisms for supervision. There are regular field visits done by the ORWs to supervise the PEs work.  ORW’s field work with PEs is documented in the form –D. The feedback mechanism should be documented in all level and it may be used to develop field level strategies for better output. The data validation system at M&E level is lacking and cross verification system should be placed. Supervision at managerial level is lacking due to the absence of project manager. Currently the field visits of ORWs are 4 days/week and that should be raised by 5 days/week.

Services:

Availability of STI services:

.

There is no project clinic and PPPs in the project. The project depend government STI health care systems for STI referrals. Confidentiality and privacy lacks in STI clinics for physical examination due the rush in the govt system. One ANM is working in the project for coordinating clinic level activities. Referral for syphilis screening is also with the govt system. There are 1194 individuals undergone STI screening once and 976 undergone STI screening twice. There is 2 STI cases identified in the project and there is no followup of STI cases. Out of 57 new contacts PT has given to 33 HRGs. Project stocks PT medicine but according to the Nurse the PT has given from the Govt system. The project maintains all the clinic related documents according to NACO guideline.

ICTC services:

Project maintains good rapport with the ICTC centers. They are referring HRGs to different ICTCs in their area. The project is having 4 ICTCs in nearby areas and it enables the HRGs to have the testing easier. The project is able to test 950 HRGs at least one time in this year. 358 HRGs have undergone ICTC testing twice. ICTC Referral slips are maintained at the project level.

Counseling services:

Total counseling given by the Nurse is 694 and there is no follow up sessions. It is observed that every year the ANM used to fill fresh counseling sheet for every HRGs. So it is not possible to track the behaviuor change/risk reduction of the individual. No followup counseling to STI cases. There is no follow up of positive HRGs. According to ANM and M&E the positives are not willing to take project services.

Condom services:

The project maintains 108 condom outlets in their area. 160479 free condoms and 3996 social marketing condoms were distributed. The project is able to achieve 100% of target in condom distribution. .PCU wise condom gap analysis in place. It is also observed that the volumes of clients/number of encounter and condom distribution are not matching, for that they conveyed that the remaining condoms are brought by the clients itself. There is demand for social marketing where as the distribution is less. During this period, the project purchased only 3996 condoms where as there is no supporting bill to substantiate the claim of the purchase.

Financial systems and procedures:

- Systems of Planning:

The systems and procedures are going through as per financial manual of KSACS.

- Systems of Payments:

The cash payments more than 5000 were settled by cheques. Vouchers are printed, serially machine numbered and signed by accountant and project director. File Registers are all separately maintained. Each payment is made as per the budget. Monthly expenditure statements are sent to KSACS through the submission of SOEs from the project on time. Vouchers are properly kept in the box file.

- Systems of procurement :

The NGO has its own procurement system. Project not purchased any assets during the     year.

- Systems of documentation :

Cash book maintained in daily basis. Bank account is jointly operated by the project director and NGO secretary. Bank reconciliation made on monthly basis and SOEs are submitting in time. Cash book of condom social marketing is not updated. It needs updation on 2011 onwards. There were no supporting bills for the social marketing condom purchase.

Competency of project staff

  - Project Manager

Post vacant.

  - Accountant cum M&E

She is experienced in TI as an ORW accountant and M&E in the same project.  Earlier the accountant cum M&E was worked as ORW and accountant in this project. So she knows the work very well. She is maintaining financial documents in a proper way and knows the guidelines. In the absence of project manager she has been taken the role of acting project manager. This leads to compromise the responsibilities such as cross verification and updation of documents.

  - ANM

The project has provision for one ANM. She maintains confidentiality and 100% of HRGs are satisfied with her. In the absence of counsellor post, she is doing risk reduction counselling. She has good rapport with the service providers and her overall work is appreciable.

  - ORWs:

Conceptual clarity especially on risk and vulnerability should be improved. Out of the 5 ORWs, 2 are from the community and one community member is above 6 years of experience as ORW. The ORWs have good rapport with the local community especially the community ORWs. Input sessions needed  for updating their knowledge.

Community participation.

Project has a registered CBO with 536 members. The CBO executives don’t know their roles and responsibilities and there is no ownership feeling. SHGs are formed under the CBO, but the activities are not live. There are community committees for DIC, STI and condom. The activities of CBO should be strengthened. Involvement of HRGs in planning and managing the project is only minimal, it should be increased. Community consultative meetings should be encouraged.

.

Enabling environment

Power analysis not done.  There is no plan for advocacy. Only need based advocacy meetings conducted. Current year project has conducted 2 advocacy meetings with Grama panchayat. The project is having a strong referral system for HIV test, syphilis screening and STI screening. . Advocacy activity by the NGO found good and visible.

Crisis committee has formed and the issues are addressed by the committee. During the year 2 crisis are handled by the project

Best Practices if any

Not found during the review period