Reporting Format-B								Annexure: B

Structure of the Detailed Reporting format

### (To be submitted by Evaluators to SACS for each TI evaluated with a copy NACO)

Introduction

- Background of Project and Organisation

SNEHA is a voluntary organization working for the marginalized section of the society especially women and children. It is registered under the Society’s Registration Act 1860.  SNEHA started HIV intervention program in 2001 among the high-risk sexual behaviour people residing at Vatakara, Koyilandy Municipalities and Perambra town with the help of Kerala State AIDS Control Society. SNEHA started to implement the Suraksha project (Targeted Intervention) among FSW s independently as a NGO from 2006 onwards.

Name and address of the Organization:

Sneha Suraksha Project, 30/578, G Das Building, JT Road, Vadakara-633101

- Chief Functionary: Prince M George

- Year of establishment:2006

- Year and month of project initiation:2006

- Evaluation team: Ameer Hassan and Amjith

- Time frame: April 2014 to January 2016.

### Profile of TI

  - Target Population Profile: FSW

  - Type of Project:  Core

  - Size of Target Group(s):822

  - Sub-Groups and their Size: Street based FSW’s:456, House based 356

  - Target Area: Vadakara, Koilandi , Payyoli, Peranmbra

### Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The NGO started at 2006, the NGO has 12A and FCRA registration. The last ten years the Organization is working for the FSW’s in Vadakara. NGO was more focusing on the advocacy for the sex workers and through the advocacy the NGO attain healthy environment for the proper functioning of the project.

### Organizational Capacity

  - Human resources: The project has a Project Manager, MEA and two ORW’s. The absence of Counsellor and one ORW affecting the proper functioning of the project. Project Manager overall monitor the project and ORW’s monitor the work of peer educators.

  - Capacity building: All staffs are trained during the last two years and concerned documents are updated. The project conducted 4 in-house training for the peer educators.

  - Infrastructure of the organization: The project has sufficient infrastructure.

  - Documentation and Reporting: Documents are prepared based on the guideline of  KSACS and all documents are available. The project has timely getting proper feedback from the DAPCU and TSU.

### Program Deliverables Outreach

- Line listing of the HRG by category.: Line list properly updated

- Micro plan: The project prepared effective micro plan but 5 peer educators are illiterate so its affect the preparation of micro plan.

- Coverage of target population: One of the barrier in the project is 30% gap of regular contact. These population received the service through one time contact.

- Outreach planning – quality, documentation and reflection in implementation: The project overall planning was not effective but in the case of outreach the project has proper planning. Lack of stakeholders/peer educator’s poor participation is major challenges to prepare a plan.

- PE: HRG ratio: The project keep the 1:60 population ratio in the PCU unit.

- Regular contacts: The project has 30 percentage gap in the regular contact. The project has high number of home based sex workers so it reflect in the regular contact of the project.

- Documentation of the peer education: Five peer educators are illiterate so they cannot properly document their work.

- Quality of peer education:  The peer educators are providing quality services but illiteracy of peer educators are affecting their work.

- Supervision: The project manager has overall supervision in the project. ORW’s are supervise the field.

### Services

- Availability of STI services: The project has no clinic service and PPP facility during the last year but the project linked with the government hospitals for the STI services.

- Quality of the services: The project has all equipment in the clinic but not functioning.

- Quality of treatment in the service provisioning: The project has proper linkages with ICTC, DOT and ART centers.

- Documentation: The project maintained referral registers and hospital slips for the supporting of referral services.

- Availability of Condoms: The project distributing free and social marketing condoms. Now the free condoms are available in the project.

### Community participation

- Collectivization activities: The project formulated 5 community committees but they are not capable to provide the services. The CBO members  are not understand their role and responsibility and not developed the ownership feelings.

- Community participation in project activities- Community participation is poor.

### Linkages

- Linkages established: The project has good linkages with other service centers.

- Percentages of HRGs tested in ICTC and gap between referred and tested: 78 % of the HRG’s received ICTC service during the last year.

### Financial systems and procedures

  - Systems of planning:The project follow the financial system as per the guideline of KSACS.

  - Systems of payments: The project keep the vouchers with machine numbered and properly attached bills for supporting.

  - Systems of procurement- During the period the project not purchased any items except condoms.

  - Systems of documentation: The project has proper financial documents. Bank book are regularly updated.

### Competency of the project staff

VIII a. Project Manager

The Project Manager working in the organization from last three years and he has another three years’ experience in other social development projects. He qualified MSW. The project manager prepared project implementation plan but it’s not connected with the project components. The weekly and monthly meetings minutes updated. The project manager conducting group visit in the filed based on the problem areas.

VIII b. ANM/Counselor

Now the counsellor post is vacant from December 2015.

VIII c. ORW

The project has two ORW’s. First ORW working in the project from last five years. She has the knowledge about the project components and project services. But in her areas 45 % of the population need to be difficulty to meet so she need different strategy for outreaching.

The second ORW joined in the project from last four years. She qualified MA Economics. Her outreach work planned based on the PLOP tools. She supervised 7 PE’s. She has proper knowledge about the project components and activities.

VIII d. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

The peer educators all are between the age group of 30-40 so its good representation from the population. Five peer educators have the problems related with reading and writing so its reflect on the Form B filling. 80% peer educators are active, energetic and sufficient knowledge about the project activities. Average all peer educators have 50% individual contact so they using community mobilization and group activities for the service provide to clients.

VIII e. MEA

MEA joined in the project from last two years she qualified M.Com. She has knowledge about the project components.

### Services

The project achieved more than 90% achievement in core service areas. In the interaction with the stakeholders their response was not qualitatively received this services.

### Community involvement

The majority community members are not revealed their sexual behavior so they cannot come in the community mobilization activities and involvement in the project.

### Commodities

The project prepared demand calculation for condom distribution. For implementing condoms they developed free condom outlets and direct distribution channel.

### Enabling environment

The project formed a project advisory committee and conducted various advocacy programmes. The majority advocacy programme was not based on the proper planing so the project need a plan for the advocacy  programme

- Social protection schemes / innovation at project level HRG availed welfare schemes, social  entitlements etc.

During the last year the projct taken  the new initiatives for the social entitlement of the communities.

- . Best Practices if any

No best practice.