| Annexure:A ReportingFormatA (ScoreoneachcomponentforeachTI)(SubmittedbySACSto NACO) Confidential Name of SACS Date ofReporting |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SNo | Name of CBO | TI typology | Location(e.g.City,town,villagename) | DateOfEvaluation | Marks obtained by each NGO |  |  |  | Recommendations |  |  |
|  |  |  |  |  | ProgramDelivery | Finance | Organizational capacity | Total marks |  |  |  |
| 1 | Sangamithra | FSW | Thrissur | 4th and 5th Feb. 2016 | 67(83.4%) | 12(92.3%) | 13 (92.9%) | 92 | Recommended |  |  |

ReportingFormat-B								Annexure: B

Introduction

- Background of Project and Organisation:

Sangamithra is a community based organization (CBO) registered under Travancore Cochin Literacy Scientific and Charitable Societies Registration Act 1955 (Reg. No.R578/2006) on 27th September 2006. The organization is working with the mission of protecting the human rights of marginalized women and children. Sangamithra is the implementing agency of “Suraksha Project”, a Project of Kerala Government funded by Kerala Sate AIDS Control Society.

- Name and address of the Organization: Sangamithra, Corporation A- block Building,26/1, Patturaikkal, Thrissur-680022

- Chief Functionary: Mrs. Chandralekha CV

- Year of establishment: 2006

- Year and month of project initiation: 2006

- Evaluation team: Ameer Hassan and Nikhil KS

- Time frame: April 2014 to January 2016

### Profile ofTI

  - Target Population Profile: FSW

  - Type of Project: Core population

  - Size of Target Group(s):1395

  - Sub-Groups and their Size: Streat based: 1335, Home based: 60.

  - Target Area: Thrissur, Guruvayoor, Kunnamkulam, Chalakkudy, Kodungallur

### Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The CBO body consists of seven members all are understand the functioning and structure of the CBO. They conducting monthly meeting and analyze the project activities. For the welfare of the community members they implemented various activities.

### OrganizationalCapacity

  - Human resources: Staffing pattern: Project Manager-1, ANM-1, M.E.A-1, ORW-5, Peer educaters-23.

  - Supervision structure and adherence: The Manager overall monitoring the project under the directions of Director. The outreach monitoring and supervision of PE’s conducted by the ORW. The clinic and referral system managed by the ANM.

  - Role and commitment to the project: All staffs are committed to the project.

  - Capacity building: All staffs are trained and quality maintained. The project keeping proper documentation for the project.

  - Infrastructure of the organization: The organization has sufficient space in Corporation building and infrastructure are sufficient for the functioning of the project.

  - Documentation and Reporting: The project documented as per the guideline of NACO/KSACS. All documents as per the criteria of NACO maintained in the project. The project staffs sent their reports timely.

### Program Deliverables Outreach

- Line listing of the HRG by category: The project registered 1395 FSW’s and keeping the updated line list.

- Micro plan: The project maintained micro plan but only few PE’s involved in the preparation of micro plan.

- Coverage of target population: The project has registered 1395 population including 60 home based HRG’s. The remaining HRG’s belong to the street based category. Based on the target the 76 percentage of the population covered as regular contact.

- Outreach planning: The project has five ORW’s and except two ORW’s are capable to effectively implement the outreach work. The ORW’s documented very well but PE’s participation is poor.

- PE: HRG ratio: The project keeping the 60:1 ratio in the project.

- Regular contacts: The project has only 76 percentage regular contact. Due to lack of fund availability the project removed 13 peer educators so its affect the regular contact of the project.

- Documentation of the peer education: The project keeping proper documentation of the peer education.

- Quality of peer education: Majority peer educators are above the 30 years so it affect the coverage of the new population.

### Services

- Availability of STI services: The last year the project not regularly running the STI clinic in the project office, only conducted three health camps in the project clinic. The project has four PPP clinics but due to insufficient fund not properly done the PPP clinic.

- Quality of the services: The project has sufficient space for clinic services, now a room arranged for clinic purpose but not functioning.  The project has network with government hospitals for the STI screening.

- Quality of treatment in the service provisioning: The project has good linkages and availability of ICTC, STI and DOT centers but the project need to be maintain the more quality of the services. The project identified four positive cases but only one positive referred to TB centre.

- Documentation: The project available all concerned documents of clinic services as per the guideline of NACO.

- Availability of Condoms: The project now available the condoms but few months they have faced the lack of availability. The project with the support of sponsors supplying the social marketing condoms.

- No. of condoms distributed: The project using free condom and social marketing outlet strategy. 81% of the HRG’s receiving condom service from the project.

- Information on linkages for ICTC, DOT, ART, STI clinics: The project has proper linkages with all ICTC’s in the project areas but need more attention in DOT and Pulari STI center.

- Referrals and follows up: 94.19 percent of HRG’s received the HIV testing services

### Communityparticipation

- Collectivization activities:  The project developed 5 community committees including 37 persons. 422 persons attended the general body meeting of the CBO.

- Community participation in projectactivities- level and extent of participation, reflection of the same in the activities and documents: The CBO initiated community strengthening activities through different programmes thus the communities participated the project activities. Especially aged FSW’s are more participated the activities of the project.

### Linkages

- Linkages established: The project has effective linkages with the ICTC centers but need more linkages with the Pulari Centre.

- Percentages of HRGs tested in ICTC: 94.19 percentage of the population had tested.

- Support system: The last year the project conducted 35 individual and group advocacy with the various stakeholders. The stakeholders of health providers are effectively linked but the project facing problems from the police.

### Financialsystemsand procedures

  - Systems of planning: The project follow the financial system as per the guideline of KSACS/NACO.

  - Systems of payments: The project keep the proper bills and vouchers, all vouchers are numbered by machine with the approval of director.

  - Systems of  procurement: The last year the project only purchased social marketing condoms but not taken the quotations

  - Systems of documentation: The financial documentations are properly maintained and auditing finished during the last year. The bank book updated regularly.

### Competency ofthe projectstaff

VIIIa.ProjectManager

The project Manager qualified MSW and he has five years experience in the social development projects. From last one year he joined in the project. He has proper planning and idea about the project components.

VIIIb. ANM/Counselor

The ANM newly joined and she passed Diploma in Nursing and she has three years’ experience in hospital setting. She is aware about the project activities

VIIId. ORW

The project has six ORW’s but due to financial crisis one post not filled. Remaining five ORW’s three are experienced and skilled in the outreaching. All ORW’s are prepared outreach plan based on the outreach tools. Three ORW’s have the good knowledge about the project components and services.

VIII e.Peereducators

Most of the peer educators are aged and only represent the aged population. Five peer educators are illiterate so they cannot do the proper planning and documentation work. The peer educators have the basic knowledge of the project components.

VIIIi.MEA

The project has a MEA he qualified MSW and finished one year in the project. He has proper knowledge about the project activities.

### Services

The project effectively providing all basic services to the HRG’s. To provide the services the project adopted different strategies like community events. In the field visit as part of evaluation we observe that the majority of the HRG’s are aged they need welfare services. So the sex workers in younger age not receiving the service properly.

### Community involvement

The project not conducted any meeting or programmes  for enhance the  community participation and not shared the project activates with the community members.

### Commodities

Free and social marketing condom service effectively implementing in the project.

### Enabling environment

### The project have good linkages with the secondary stakeholders.

- Social protection schemes /innovation at project level HRG availed welfare schemes, social entitlements etc.

Provided Tailoring machine  to HRG’s : 10- funded by SBT

Prime minister insurance scheme -16 stakeholders received

Nutritional food provided 3 Positive HRG’s initiated with CBO

The 96 children’s of the HRG’s received the School kit through  the sponsorship and Cash prize provided two students passed SSLC

- . Best Practices ifany

The project developed a mobile ICTC: Through the advocacy with the District hospital, Trissur, Guruvayoor Devaswam Board hospital, Cooperative hospital, Trissur availed the ambulance service. The three ICTC’s are linked in the mobile ICTC. Thus 38% percentage of ICTC testing done through the mobile ICTC.

Day observation: The project conducted seminars and various programmes in the following days and empowered the community.

Environmental day

TB Day

World health day

Independence day

Gandhi Jayanthi

Women’s day