Reporting Format-B								Annexure: B

Structure of the Detailed Reporting format

Introduction

Background of Project and Organization

Snehitha is a community based organization (CBO) of female sex workers in Kottayam district, registered under Travancore Cochin Literary Scientific, and Charitable Societies Registration Act (Reg. No. K.392/2006). Snehitha has been implementing TI intervention 2010 covering 3 sites in Kottayam district with a population of 862 (2015-2016)

| Kottayam | 304 |
| --- | --- |
| Changanacherry & Pala | 261 |
| Vaikom & Ettumanoor | 297 |

The targeted intervention in this area was implemented by an NGO named CARB (Centre for Advanced Research in Behavior) from the year 2004, as a composite intervention covering MSMs and FSWs. After the scaling up process based on the findings of Participatory Site Assessment (PSA) was done in 2006, the MSM component was handed over to Lasyakairali in 2008. CARB continued to implement TI among the FSWs till 2010. Later, in 2010, the TI project for the FSWs in Kottayam district was handed over to Snehitha, the CBO that was developed for the FSWs by CARB.

- Name and address of the Organization

Snehitha Suraksha Project,Mullankuzhiyil Building, SH Mound, Chavittuvary,

Kottayam

- Chief Functionary:Nisha KC

- Staff in position:

| S. No. | Name | Gender | Designation | Qualification | Previous Experience (Years) | Date of joining |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aby Jose | M | Project Manager | MSW | 5 years | 03-05-2010 |
| 2 | Vinu Vijay | M | MEA | B.com | 5 years | 13-09-2010 |
| 3 | Nil | NA | Counselor/ANM | NA |  |  |
| 5 | Syamala John | F | ORW-1 | 8th | 5 years | 03-05-2010 |
| 6 | Lekha Ashokan | F | ORW-2 | PDC | 3 years | 15-10-2012 |

- Year of establishment:2006

- Year and month of project initiation:2010

- Evaluation team: Ameer Hassan and Nithin

- Time frame: From April 2014 to January 2016

### Profile of TI

  - Target Population Profile: FSW

  - Type of Project:  Core population

  - Size of Target Group(s):862

  - Sub-Groups and their Size: Street based:621, Home based:241

  - Target Area: Kottayam district

### Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The interaction with the office bearers they are not involved the CBO activities in the last year. The last two year the CBO conducted only three meetings and not effective involvement in the activities of the project development.

### Organizational Capacity

Human resources:

  - Staffing pattern: The project has a project manager, two ORW’s and 10 peer educators are present. The counsellor and one ORW post are vacant in the project. All other staffs are experienced but last one year staffs involvement is less compare with previous period.

  - Capacity building: The project manager last two years attended three training, Accountant cum and M&E Officer attended three training programmes, one ORW participated in refresher training. Another ORW not attended the training in the last two years. Four peer educators attended the in -house training programme. Flip chart and condom demo used and basic services focused in the peer educators training programmes.

  - Infrastructure of the organization: The project has sufficient infrastructure in the project.

  - Documentation and Reporting:  The project maintained their documents as per the protocol of KSACS, almost all documents are available in the project. The project has individual tracing system for find out the STI and ICTC due and overdue.

### Program Deliverables Outreach

- Line listing of the HRG by category: The project updated their line list as per the format o NACO.

- Micro planning in place and the same is reflected in Quality and documentation: the project has micro plan maintained by the ORW’s. But peer educators involvement is not effective in the preparation of the micro plan so it’s not linked with the quality output.

- Coverage of target population: The project covered the targeted population but most of the representation from the street based, comparatively home based contact was less so the project need different strategy for attain the home based sex workers. The project reported 72 % of regular contacts during the last year but in the field visit as part of evaluation only 4 HRG’s were visible.

- Outreach planning: The project has not effective outreach plan. Now two ORW’s cover the whole district areas so they cannot effectively conducting the outreach. In the outreach plan they didn’t use PLOP tools so their work is not systematic.

- PE: HRG ratio: The project keep the 1:60 ratio in the project.

- Regular contacts: Due to staff turn over the last two years the project regular contact was less.

- Documentation of the peer education: Through the support of ORW’s the documents of peer education was updated but peer educators age and education not supportive for the documentation purpose.

- Quality of peer education: almost all peer educators are aged, and represented from the street based. Majority of the peer educators not capable to doing the documentation work and cover the new populations.

- Supervision: Project Manager over all supervise the project and ORW’s implement the programme with the support of peer educators.

### Services

- Availability of STI services: The first phase the project was monthly regular clinic services and 7 PPP doctors but last year the project has no effective clinic services and no linkages with PPP doctors. Now the project has linkages with the government hospitals for the STI services.

- Quality of the services and infrastructure: Project has sufficient infrastructure but not providing quality based services. Last one year the project clinic not properly functioning and the clinic is 4 KM distance from the town. From April 2015 to October 2015 the STI kit not available in the project.

- Quality of treatment in the service provisioning: The project has network with the Pulari Centre in District Hospital, Kottayam and for the purpose of STI screening the project linked with the government hospitals. Most of the stakeholders are not satisfied the STI services from the government hospitals due to lack of acceptance of doctors in the government settings.

- Documentation: The project keep the referral register and OP card from the concerned hospital. But not keep the network register and referral slip in the clinic.

- Availability of Condoms: Now the project available the social marketing and free condoms. The project using the strategy of direct distribution and outlets for the distribution purpose.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts: Now the project distributed the condom as per the requirement and 89 % of the HRG’s receiving condom service from the project.

- Information on linkages for ICTC, DOT, ART, STI clinics.: the project has proper linkages with the ICTC, ART, DOT centers but STI services need to be improvement. In the ICTC centers the project not collecting the referral slips systematically. As part of evaluation visited ICTC and STI centers in District hospital at Kottayam but the project reporting numbers was not matched.

- Referrals and follows up: The project has referral system but absence of Counsellor affecting the referral system and follow-up services.

### Community participation

- Collectivization activities: During the last year the project not conducting any community events and CBO level programmes. The project has formulated 9 community committees but not maintain the quality.

- Community participation in project activities: The project and CBO not taken the more initiatives for the community participation.  Most of the CBO members are inactive and not involved the CBO activities. In project service areas lack of community participation reflected on the services.

### Linkages

- Assess the linkages established with the various services providers: The project has linkages with the ICTC Centers and government hospitals for the STI linkages.

- Percentages of HRGs tested in ICTC and gap between referred and tested: The last year the project has tested 80% of the population but second time test was only 32%.

- Support system: The project not developed any support system with the stakeholders.

### Financial systems and procedures

  - Systems of planning: The project following the financial system as per the criteria of KSACS.

  - Systems of payments: All financial documents are clear and updated properly. All vouchers are numbered with machine and keep the proper bills. The programme bills are matched with the programme.

  - Systems of procurement: During the project period the project purchased condoms for social marketing, it was as per the criteria of the KSACS.

  - Systems of documentation: Bank accounts are updated and not get the audit report on last audit.

### Competency of the project staff

VIII a. Project Manager

The Project Manager working in the project from last 5 years, before that he had two years experience as Counsellor in the TI intervention. He qualified MSW. The Project Manager not prepared monthly/quarterly report properly. Based on the PO visit report he prepared the action taken report. But in the advocacy areas the plan is not effective.

VIII b. ANM/Counselor

The ANM/Counselor post is vacant from last year.

VIII c. ORW

The project has two ORW’s one from community and another one from non-community. The community ORW’s working from last 5 years before that two years she was working as peer educator. She is capable to do the work. But wide areas affecting her outreach.

Second ORW from non-community she is working from last three years and she also qualified the ANM course thus she can give the clinical services to the project. She is skilled the project indicators and outreach plan.

VIII d. Peer educators

The most of the peer educators are aged so they don’t represent the young sex workers. Majority peer educators are illiterate so they cannot do the proper documentation work. The peer educators have wage idea about the project services.

VIII e. MEA

The M& E cum Account working from last three years in the project, he qualified B.Com. He is experienced another three years other than the project. He is skilled the project indicators and reporting system of the project

### Services

The Project period especially last year the project services not effective and not reached the HRG’s.

### Community involvement

The project has no any plan for the community involvement so its affect the community participation   for the project work.

### Commodities

The project prepared condom demand calculation and as per the demand the project distributing condom through social marketing and free condoms.

### Enabling environment

During the last year the project not focused any advocacy programmes. So it’s affecting the proper service providing system. Likewise the community participation was poor in the advocacy area of the project.

- Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- Income generation Programme (Jewellary Making) is done by the CBO.

- Four of the stakeholders got Ration card.

- 8 of the HRGs obtained ADHAR card who otherwise do not have any domicile addresses

- 4 of the FSWs obtained Ration Card who otherwise do not have any domicile addresses

- 10 HRGs motivated to involve themselves in MGNREGA (Mahathma Gandhi National Rural Employment Guarantee Act).

- Project provides day care for female sex workers with the support of CBO.

- Thrift saving scheme initiated for the benefit of HRGs and resulted in increased drop in at DIC

- . Best Practices if any

No any best practice

### Confidential	Reporting Form C

## Annexure

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Ameer Hassan | 9605020888 |
| Nithin | 9544671967 |
| Officials from SACS/TSU (as facilitator): Pappu | 9747008042 |

| Name of the NGO: | Snehitha |
| --- | --- |
| Typology of the target population: | FSW |
| Total population being covered against target: | 862 |
| Dates of Visit: | 8th and 9th February 2016 |
| Place of Visit: | Kottayam |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 62.3 | B | Good | Recommended for continuation |

Specific Recommendation:

- During the last year the TI has just average performance in   majority of core indicators because the financial crisis and lack of staffs motivation.

- Restructure the lack of motivated staffs

- All peer educators are aged so select the younger sex workers as peer educators

- Restructure the CBO

- Form the support groups

- Enhance the community collectivization programmes

- Arrange a day time shelter home for sex workers in Kottayam town

Name of the evaluators	Signature

| Ameer Hassan |  |
| --- | --- |
| Nithin |  |