Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organization

Swantham Social Service Society is a Community based Organization registered as a charitable organization under Societies Registration Act XII of 1955.  The CBO has 791 FSWs as members. Swantham Social Service Society has been implementing TI intervention since the year 2006, covering 4 sites with a population of 950.

Along with TI, the CBO is running a P&R for the homeless and old sex workers and income generation programmes like catering unit, candle making, production of phenol, soaps and detergents.  The CBO implements TI in Ernakulam,Palluruthy, Aluva, Thripunithura

| Name and address of the Organization | Swantham Social service Society |
| --- | --- |
| Chief Functionary | Ms. Mary K.V, President |
| Year of establishment | 2003 |
| Address of the project office | House no.350/550/ koonamthai,edapally-24 |
| Project Director | Mary KV |
| Year and month of project initiation | November 2006 |
| Evaluation team | Ms.Shefeena P.S Ms. Laiji |
| Time frame | 12th and 13th February 2016 |

Profile of TI

| Target Population Profile | FSWs |
| --- | --- |
| Type of Project | Core |
| Size of Target Group(s) | 950 |
| Sub Groups and their size | 912- SSW-429HSW-460,LBS-23 |
| Target Area | Ernakulam,Palluruthy,Aluva, Thripunithura |

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The Swantham Social Service Society is a CBO of FSWs. The goal of the organization is to work for the welfare and development of female sex workers in the District through relevant approaches like training, education and motivation for collective leadership. Since from the humble beginning on 23rd July 2003, the Society has been implementing various welfare programmes for the benefit of downtrodden female sex worker community in the District.  The present executive board is active and they are monitoring the project activities and supporting the programme by mobilizing funds to run the programme.

II.	 Organizational Capacity

- Human resources:

All staff are placed except cousellor/ANM. These two were resigned from the project and vacancy was not filled as per the direction of KSACS. Staff are active and have sound knowledge on TI programme. They are clear about the roles and responsibilities and have a food relationship with CBO. Their attitude towards the target population is also good.  Good team work between CBO and Staff members can see in the project. Positive attitude of the Staff towards CBO helped the executive board became active. Even though fund shortage is there, all staff were worked in the project and supported to run the programme.

- Capacity building:

Most of the staffs are trained by STRC/KSACS and in house trainings were also organized by the project to enhance the skill of ORWs in programme implementation. Provide more orientation to the ORWs regarding CBO concept.

- Infrastructure of the organization

CBO is implementing the project but they do not have any other infrastructure.  The CBO has a separate room in the office for its meetings and records. The income generating programmes are also carried out in the Project and which have motivates the stakeholders to visit DIC. All Infrastructures are purchased as part of TI intervention

- Documentation and Reporting:

Documentation system maintained in the project is as per SACS/NACO guidelines. CMIS and other allied documents maintained well. All documents were available in the project for verification. But there was mismatching of data in the formats and presentations. Project presented that they had achieved 943 out of the target 950, but as per formats it is 912. So the project needs to focus more on quality documentation and reporting.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category

The line list data entry is 943 and drop out cases are not deleted from the list. But in the formats it was deleted. Data is not properly tallying with the data of ORWs revealed at the time of review.

2. Micro planning

Out reach plan and micro plan are in place. But as per the dairy of ORWs, the field visits were only 10-12 days in a month. Project has to increase the field visits so as to provide maximum services to the HRGs.

3. Coverage of target population (sub-group wise): 912 FSWs were covered against the target of 950. Project has a coverage of Street based FSW 	:429, House based:460,Lodge based:	23.

4. Outreach planning

Out reach plan is prepared by the project and it is documented. Weekly and monthly reviews were also done in the project. The ORWs do the outreach planning.  Most of the PES are from the Street based Sex workers they have HBS and SBS are in their list. So project has to be identify the PEs are from HSB that helps to identify more HRGS from HBS and can provide maximum services to them

5. PE: HRG ratio

16 PEs: 912 HRGS: 1: 57HRGs. Even though fund problems, All PES were participated in the meeting and have an ownership feeling for the programme.

6. Regular contacts

Project is having regular contact with 818 FSWs out of 912 contacted. PES are very active and they have regular contacts with the HRGS and ORWs are supporting them to achieve the targets. During review the team had met only 6 HRGs. The data presented in the review meeting  by ORWs have lots of mismatching

7 . Documentation of the peer education

PEs with the support of ORWs maintained the reporting formats. Some PES were able to answer the correct number of referrals and names of the HRGS referred and it was not tallied with the formats.

8. Quality of peer education

All PEs are trained ones and experienced and have enough knowledge on TI components.  Most of them are in the age group of above 45 and majority are street based Sex workers. There are 16 PEs in the project and evaluation team met all the PES. PEs are able to contact new FSWs in the age group-24-29 and 5 were participated in the interaction as part of evaluation process. While discussing with HRGS many of them were not aware about who is there PE and which PCU list they belongs. Project needs to train the PES regarding the PCU list, how many HRGs in their list belongs. It was observed that none of the PEs were replied the correct number of HRGs in their list and the sub groups. During interaction with HRGs revealed that most of the time clients brought condom and free condoms are not good to use. Only 43% know the exact demo of condom. So the usage of condoms needs to be tracked properly

9. Supervision

The overall supervision of the programme is done by the manager .Monthly review meetings were conducted and discussed various issues regarding project activities action taken accordingly. There was some mismatching observed in CMIS reports and actual data in the formats. ORWs should present the data in the review meetings  and correct the numbers as per field data and also focus more on to improve the quality of data collection in the field and do tally with formats. Provide proper feed back to the PEs regarding the services whom to be give.

IV. Services

- Availability of STI services

Due to fund shortage project was run the clinic at office. It had affected the RMC among HRGS. Only 13% of the HRGs were attended RMC.  80% of the HRGs attended First time STI screening and 5% were second time and 000.1 % for third time. Project is depending Pulari, Government hospitals, PHCs for STI services. Project has identified 60 New HRGS in the reporting period and 51 were given PT treatment

- Quality of the services-

As part of the advocacy and good contact with PPP doctor visited to office and conducted PTcampaign.

- Quality of treatment in the service provisioning- The project is depending government hospitals for the STI treatment and conducted follow up of all the infected cases. Project could identify 72 STI cases and provided counseling. Even though the Counsellor was not there and component is managed by PM.

- Documentation-

Project has maintained all documents as per the NACO guidelines. Due to lack of fund the project was able to provide the drugs through the sample medicines collected from PPP doctors. Clinic register, network card, referral slips are all maintained in the project.

- Availability of Condoms-

Due to fund shortage the project was focused more on distribution of Free condoms are distributed through PEs/outlets, ORWs.  PEs are satisfied with the availability of free condoms. The project established 12 traditional and 4 non - traditional outlets in the project area.

As per the interaction with HRGS, the clients are not interested in free condoms and they  brought other condoms and they put the condoms themselves. Project has identified 2 classical STDs and 70 other symptomatic cases. Project has to develop proper condom tracking mechanisms to identify the condom usage among HRGs.

- No. of condoms distributed-

Against the requirement of 190000 condoms the project was able to supply 210018.  The project provided only 20018 social marketing condoms. Revolving fund was utilized for project activities.

- Information on linkages for ICTC, DOT, ART, STI clinics :

All the project staff /PEs have the information on the linkages ICTC, DOT, ART. HRGs are using the services

- Referrals and follows up

818 HRGs were referred to ICTC and one new HIV positive cases were identified and was linked with Pre ART. Follow up is giving to the 6 infected cases.

V. Community participation

1. Collectivization activities:

The project is running by the CBO and all are known about the CBO functions. Even though fund shortage, CBO with the support of project staff are running the programme. They had spent Rs.81, 213 for paying rent and other project services.  Project is having a membership of 791 and 225 are active members.  Community event was sponsored by YMCA and they had given onam kit to the HRGs. CBO should provide more focus to join new HRGs in the CBO and increase the active memberships.

2. Community participation in project activities

Project had organized 3 community events under the leadership of CBO and the 458 FSWs were participated. The project has formed community committees of STI, ICTC, condom and DIC and  HRGs membership in the committees are minimal and their involvement need to be increased.

VI. Linkages

1.  The project has made good linkages with the various services providers like STI, ICTC, TB, PHCs/ clinics

2. Support system developed with various stakeholders like legal support agencies, various sponsoring agencies, Health care facilities, HIV positive care centres, STI clinics, etc.

VII   Financial Systems and Procedures.

- Systems of planning: Budget utilisation is as per NACO norms. 42 % Utilization.  Against 42% they received. CBO is supporting the project for paying rent and some programme activities. M&E A got three training from KSACS. Cash in hand-153, Bank-4

SM bank- 366. CBO with the support of project staff are running the programme. They had spent Rs.81, 213 for paying rent and other project services

- Systems of payments:  Vouchers and Bills are properly maintained with supporting documents. Cash payment done for amount less than 2800/-. Vouchers are printed and machine numbered.  There was no mismatch observed.

- Systems of procurement: No purchase done during the period.

- Systems of documentation: SOEs are submitted before 4th of every month. Cash book /ledger maintained properly and countersigned by PM/PD. Cash with bank book, Asset Register, Condom Stock register, Cash denomination book, Attendance register, Cheque issue register and ledgers are properly maintained. Bank reconciliations are made on monthly basis.

VIII. Competency of the project staff

- Project Manager

Project Manager is a Post graduate in Social Work with LLB. He is working in the project for last 3 years. He is leading the project with good team spirit and is team player. His positive attitude towards the HRGs and CBO is appreciable that turns good working environment in the CBO. CBO EB and the project staff is going together and CBO office is under control and there wasn’t any issues among CBO members each other in the last 1.5 years. His supervisor skills and dealing with CBO EB are good. He supported the CBO to get social security schemes and mobilize resources to the CBO/HRGS.

.

- ANM

Post is vacant and not filled so far

- Counselor

Post is vacant and not filled so far

- ORW

There are 3 ORWs working in the project One ORW resigned from the project and not filled the vacancy as per KSACs direction. ORWs are very active and their attitude towards the HRGs is good. 2 ORWs are in the project for 2 years and one is for one year. They are extending their work to one more area (Thripunithura) where there is no ORW. They are trying hard to do the documentation but need to improve .There was some mismatch seen in the documentation. They also need to have an orientation on CBO concept and its Vision. So they also contribute their views to achieve the goals of the CBO.  Field visits of the ORWs were only 10-12 days. This will be increased to achieve more targets and identify more number of HRGs and to provide quality services.

- Peer educators

The project has 16 PEs. It is as per the PE Ratio as per HRG population. All PEs are active and most of them are in the project for last 5 years.  All of them were aware about STI, Condom and all the project services. All them were requested for the PPP clinic at office and lack of this they cant achieve the RMC. Formats are recording with the support of ORWs and some PEs were not able to say the names of HRGS name in the PCU list. They revealed that find difficult to bring HBS for check up. The project needs to identify PEs from HBS for providing direct services

- M&E  officer

M& E officer is a Post Graduate in MPH and new entrant in the project.  He joined in the      project on December 2015. He got 3 days training from KSACS for accounts and maintained accounts well and good. He is learning the formats of programme activities and supporting the ORWs

IX. Outreach activity in Core TI project

The out reach activities of the project has to improve in planning and identification. The   shortage of ORWs need to filled at the earliest. Stretching of the existing staff to one more area will loose the quality of out reach   Project should focus more on selecting PE from House based sex workers and select new PEs as per the risk profile of the HRGs`. Condom tracking is one of the main areas the project should focus. PEs need to be trained on their PCU list.

X. Services

HRGs are taking services from existing govt. systems and they are getting services.  90% were tested ICTC and 72% undergone STI screening. Absense of Counsellor/ ANM was affected to provide quality counseling services. The post should be filled at the earliest for effective programme implementation.

XI. Community involvement

Current EB of CBO is very active and the CBO members are also supporting to run the programme by in terms of cash and materials. But the participation of HRGs in the committees are very minimal. CBO should focus more on to include more HRGs in committees. So that project can identify the problems of New HRGs in the field.

XII. Commodities

The HRGs are satisfied with commodities they are getting from the project. The Condoms are available at their spots and they are interested more on SM condoms rather than free condoms.

XIII. Enabling environment

Advocacy of the project is good. They developed a good relationship with Govt. hospitals, departments, NGOS, legal cell, police department, doctors and utilizing their services. CBO along with Staff is doing the advocacy

XIV. Social protection schemes

CBO has supported 6 HRGs for getting pattayams, educational support for children of FSWs, Food kit, ID card for 10 FSWs and mobilized various resources from NGOs/GOs  for the welfare of the HRGs. Applied for PMAY for 15 FSWs..

XV. Best Practices if any

Few best practiced are

- Advocacy with Sannidyam NGO they provided School kit for Children’s of HRGs, Sponsored Christmas and New year programmes. They also provided food Kit for inmates of P&R Homes.

- Advocacy with Akasa parava they provided Accommodation facility, Medical help and Food kits.

- Advocacy with Doctor Joy Joseph and conducted PT Campaign

- Advocacy with Legal agency they solved crisis management.

- Positive environment created by the CBO.

Name of the Evaluators   			                                             Signature:

Shefeena P.S

Laiji

Date:12-13thFebruary2016