Reporting Format-B

Swaruma FSW Suraksha Project, Perumbavur

- Introduction

- Background of Project and Organisation

Swaruma Swashraya Sangham is a Community Based Organization of Female Sex Workers in Muvattupuzha established in the year 20000 with the patronage of Resource Centre for Training and Counseling, as NGO in Ernakulam district.  The fraternity was formed by 10 sex workers who operated in Kothamangalam, Koothattukulam and Muvattupuzha in order to develop a platform to get together, share and ventilate their individual and community issues and also to empower them to address their concerns independently. It was later registered as charitable society under the Travancore Cochin Literary, Scientific and Charitable Societies Registration Act 1955 Act-XII as Reg. No - ER/1212/2001. Presently the CBO has an Executive Board consisting of seven members and with 650 members in the general body.  The responsibility of implementing targeted intervention in the area is handed over to Swaruma since December 2006.  Currently this TI covers 1212 HRGs.  The site wisepopulation distribution is as follows; Perumbavoor (539), Thodupuzha (182), Muvattupuzha (192) and Kothamangalam (245).

2. Name and address of the Organization: 	Swaruma Swashraya Sangham,											Near Pittappillil Agencies, AM Road, 										Perumbavoor, Ernakulam(Dist),PIN- 683542, 									Ph : 0484 2812042, swarumasuraksha@gmail.com

3 Chief Functionary:  Mrs. Ammini  Joseph,  Project Director.

4. Year of establishment: 2001

5. Year and month of project initiation:  December 2013

6. Evaluation team:                Mrs. Savitha Shenoy

Mr. Anish

7. Time frame: 			2 days (11th & 12nd February 2016)

8. Target Population Profile: 	FSW

9. Type of Project: 		Core

10. Size of Target Group(s):     1144

11. Target Area:    Perumbavoor, Muvattupuzha, Kodamangalam, Thodupuzha

C. Key Findings and recommendations on Various Project Components

1. Organizational support to the programme

Swaruma Swashraya Sangham is a CBO of women in sex work, and holds the vision of empowered group of female sex workers with increased bargaining power in demanding safe sex from their clients. The organisation provides support to the female sex workers to appropriate supportive income generation activities, and provide solace to female sex workers in distress through protective measures.

Swaruma has been implemting TI project successfully since 2006 covering 6 areas viz, Perumbavoor, Muvattupuzha, Kothamangalam, Thodupuzha and Koothattukulam.

The evaluation team had interaction with all executive committee members and all are committed and active. President of CBO is the Project Director.  New executive committee members took charge in August 2015 hence needs capacity building. CBO strengthening would help better understanding to enhance quality management of TI by CBO governing body

2. Organizational Capacity

a. Human resources

As per TI staff allocation, all posts of staff except one ORW are in place.  The appointment of ORW was not done due to finanicial constrain. Project has 3 ORWs  out of which  two are experienced in the project  for 12 and 9 years respectively. I ORW is from community and joined the project six months ago.   The new ORW Community is also picking up with the team. ANM and MEA also doing appreciable service.   All staff have received roles and responsibilities in written and are in place and all staff has been issued with appointment orders but not in Letter head of CBO.  The attendance register was found in place and leave file is maintained.  Majority of the leave letters are there but need improvement in filing and monitoring.

b. Capacity building

As per the staff they got orientation training for one day from the project when they joined but no such training reports were available for verification.  The newly joined staff in this contract period is one ORW.  It is suggested to submit a training report by the newly joined staff to the PM after the training/orientation and training conducted by STRC/KSACS/CBO.  Training registers of the staff are maintained in the office however there is no training report maintained by the staff.  2 PE trainings are organized by the project.

c. Infrastructure of the Organization

Project office is close to the market and Governmnent Hospital . It is in the main area of Perumbavoor and it makes easy access to the office possible. There is abundant  place for program administration, DIC and room for clinic and counseling.  Office is pasted with IEC materials, concepts/definitions and indicators. Toilets are available in the DIC. The project has established one static clinic also in main office but not functional at present due to financial constrains.  DIC is utilized by the community. All assets are codified and entered in the asset register except assets transferred from another TI project which is discontinued..

d. Documentation and reporting

Most of the formats are according to NACO guidelines but MIS tool manual is not available in the project.

The project keeps line listing/master register in the computer and using for any analysis.  MEA is verifying the records but is not up to the mark. They are maintaining the staff meeting minutes and the PD's presence is in almost all meetings. In review meetings more emphasis has to be given on analysing the achievements and shortfalls. The project is maintaining all project related documents but lot of mismatches seen in this period.  The PEs are helped by the ORWs in filling form B and they are reporting their work in the end of month. This data is consolidated for preparing MIS reports by the PM and M&E. Daily reports of staff also has to be given proper attention.  Although the staff are well aware of micro plan and planning requirement they are not using it properly. Project has a very good service tracking system. Gaps were observed in condom requirement analysis documents. Project Manager has to verify the documents at periodic intervals.

3. Program deliverables

a. Outreach: The project is appointed all ORWs in the stakeholder ratio and they know the plans and that one are divided to weekly plans. Out of the total targeted population of 1158 disbursed in 26 hotspots, all are line listed and risk wise categorization is done.  The project has 564 (Street based) and 594(House based).  Out of the total population the project is able to contact 913 FSWs regularly in a month and provided services. Project has 21 new identifications. The project is able to select 1 ORW from the community.  The project is able to regularly reach to 79% of the HRGs inspite of fund constrains. The main focus is to link the HRGs to services and providing condoms. The priority fixing on the base of risk can also taken care of.

Currently the field visits of ORWs are 4 days/week and they are meeting PEs in the concerned areas PCU wise micro plans have been done by the ORWs and the documents are maintained. Planning is mainly done through the service register developed by TSU.  Due to the financial constrains e in  project DGA meetings were suspended for few months.

Peer education: A total of 10 PEs are in place. Most of the PEs are well experienced and trained. But their performance at the time of interaction was not up to the mark. Majority of them are aware of the objective of the project and have good knowledge about the project components. But communication skills need to be improved. Condom demo was done properly. Most of the PEs belong to the age group 35 to 50 which does not match the criteria of PE selection. PEs belonging to lower age group need to be identified and inducted to so as to bring young sex workers into the project loop.  As per the project staff they tried inducting three PEs who were 25-30 years old but they do not have time for providing service and documentation. Some PEs are supported by ORWs in filling form B. Participation of PEs in planning should be raised to a certain level and documentation of the meeting has also to be increased.

b. Services:

STI services: The STI services are in place and are good documentation  are also properly done. They provided PT to all   21 new identification, but FSW was given PT after a gap of 1 year of identification. The project although established a static clinic is now dependent on Government hospitals for providing services to the HRGs. The PPP doctors identified by the project are very helpful.  Project was able to raise sponsorship from philanthropist for the health check up of HRGs.   There is no Pulary centre in the Project area.

845 HRGs have gone for medical checkup in one quarter and 549 HRGs could make it for second time. 3 STI cases were  reported. 746 HRGs went for VDRL testing in this year. The availability of the kits at government hospitals was hindered for few months which has affected the number of HRGs tested for syphills.

HRGs are aware of these facilities and are found to be comfortable with the service provisions and providers.

ICTC services: The project is having good relationships with 6  ICTCs in nearby areas and it enables the SHs to have the testing easier. The project is able to test  864 of HRGs atleast one time in this year. ICTCs had a testing kit shortage for nearly 3 months.  The project has provided line list to the concerned ICTC’s of their areas hence duplication can be decreased.

Counselling: The project is able to provide counseling to only 70% of the total line listed population and this area has to be focused in the coming months.   The project is able to give counseling to 547 HRGs of the RMC attendees. Only 77 HRGs were given Risk  Assessment and Risk Reduction counselling  and it  has to be increased.  Quality of counselling can be increased.

Condom services: The project is able to open 16 outlets in the project area and able to distribute 115846 free condoms and 12150 social marketing condoms. The project has provided condoms to 64% of HRGs as per their requirement out of which 58% of demand is met through free condoms.  The condom requirement analysis had few mismatches which are to be avoided. The outlets are established but monitoring has to be strengthened.   Project has to focus more on social marketing condoms as only 6% of condom requirement is met through SM. During the field visit few condom outlets has suggested that there is a demand of premium condoms also which is not available in project. It has to be noticed that although 79% of HRGs are regularly met only  64% of requirement is met.

c. Community participation: A total of 158 HRGs attended in events held by the project which has to be increase by the project in coming years especially when 650 HRGs are members of the CBO and this is a CBO run project. The project conducted event in relation to the festivals of Kerala.  The participation of community in planning process has also to be increased.

d. Linkages: HRGs are aware of the services provides in ICTCs and PPP clinics. The ICTC referrals found good.According to the community project is keeping confidentiality and they are satisfied with the services provided by the project. They have a very strong  support support system at Muvatupuzha Muncipality.  The project is having a strong referral system for HIV test and PPP clinic. No HIV positive cases were report this year. Three HRGs were referred for TB and no body tested positive.

e. Financial systems and procedures:

- Systems of Planning:

The systems and procedures are going through as per financial manual of KSACS.

- Systems of Payments:

The cash payments more than 5000 were settled by cheques. Vouchers are printed, serially machine numbered and signed by accountant, project Manager and project director. File Registers are all separately maintained. Each payment is made as per the budget. Monthly expenditure statements are sent to KSACS through the submission of SOEs from the project on time. Vouchers are properly kept in the box file. Reconciliation is done on monthly basis.

It was observed that Social Marketing condom cash balance has not deposited to bank for last one year where cash balance is more than Rs.5000/- throughout the year.  Payment of Social Marketing condoms which is purchased 4 months back has not given.

- Systems of procurement :

The Project has no procurement system. Medicines are supplied by KSACS/NACO and no assets is purchased in this contract period. Project has only purchased Social Marketing condoms during the year but quotations are not invited or collected.

- Systems of documentation :

Cash book maintained in daily basis. Bank account is jointly operated by 2 executive members of the CBO. Bank reconciliation made on monthly basis and SOEs are submitting in time.

f. Competency of project staff

1. PM: The project manager is a post graduate in Social Work with 5 years experience in the project. She has workedas M&E Officer in the same project.  She has good knowledge about the proposal and project components.  Financial management, computerization and management of data are good. She conducts review meetings every month and data analysis done with project team. Document verification needs to be strengthened and has to be done periodically.

2. MEA:  Accountant cum M&E has three and half year experience in project and she is basically an accountant. She has good communication with other team members and have good positive attitude. Account related documentation is good but improvement is required in SM account related works. She is properly maintaining Service register/colour coded line list. She needs more orientation in Monitoring & Evaluation part. Cross verification of documents should be improved.

3. Counselor/ANM

ANM has joined the TI before five years who is also undertaking the duty of Counselor. Clarity on risk and vulnerability must be improved. Knowledge on basic counselling and HIV, symptoms of STIs, etc. was found to be good. Data maintenance and updating of clinic registers are done systematically. Maintenance of counselling records  needs improvement.

4.ORWs:

Project has three ORWs out of which one is from community and is learning things pretty fast. The two non-community ORWS have commendable clarity about the project components. This has reflected in project achievements and CBO functioning. All ORWs have good acceptance among PEs and community. Some of the comm

g. Community involvement:

There is one community committee each for DIC & Crisis Management to increase drop in to DIC and for tackling the issues/crisis’s of HRGs respectively in the project. TI has 4 service committees in four sites but it does not have separate committees for Condom, ICTC & STI. Project has Health and Community development committees in major 4 sites.

h. Enabling environment:

Project have a Project Steering committee & local advisory committees in most of the sites and meetings are held periodically. Project has few issues with Perumbavur Muncipality where TI office is situated. Project has tried out various opitions to sensitize them about the project but none is successful yet. They have decided to sensitize  counsellors one by one other than the chairman of standing committee members straight away.

- Social protection schemes/ innovation at project level HRG availed welfare schemes, social entitlements etc.

- The CBO implements Waste Management Porgramme of the Muvattupuzha Municipality.

- Saving scheme programs: Providing the facility to save their money in a better way than any other savings. Orupidi: - It is a confidential saving system allowing the HRGs to save their money (not fixed) at anytime in the office and get it back whenever they demand

- Snehanidhi Medical allowance scheme: Scheme provides small economical support to the HRG to meet their medical needs.

j. Best Practices if any

- One out of three ORW is from community.

- Savings scheme and IGPs

- No profit no lose canteen for HRGs.

- Personality development programmes for HRGs and their children.