Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Sthree ashraya kudumba vikasana sangam (Vanitha Society-Community Based Organization)

Introduction

Background of Project and Organisation

Sthree Ashraya Kudumba Vikasana Sangam (Vanitha Society-Community Based Organization) as a development society registered under the society’s registration Act .It is the continued platform of the sexual health programme implemented by CSRD at Calicut in 1997 whereas the TI intervention started in 2000 by CBO itself and it considered as the first CBO in Kerala. With the tremendous support and effort of the sex workers a new office was setup in their own land at Santhinagar Colony in Calicut district of the Kerala State including 1349 population covering entire Kozhikode. The main objective of the society is the total empowerment of marginalized woman, especially sex workers. The organization works for ensuring human rights and safety of the sex workers like them.

Name and address of the Organization :

VANITHA SOCIETY

AL-HARSH PLANETVIEW APPARTMENT

2ND FLOOR

NEAR KUNIYIL TEMPLE

CALICUT,  PIN - 673001

Chief Functionary:    Smt.Seenath

Year of establishment : 2000

Year and month of project initiation: 2002

Evaluation team :    Helvis vazhapully

Liji U

Time frame:             08-02-2016,  09-02-2016

Profile of TI

Target Population Profile:      FSW

Type of Project:      Core

Size of Target Group(s)       1378

Sub-Groups and their Size:   House based: 670.  Street based: 708

Target Area:       Kozhikode Corporation and Thamarassery sector.

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

The presence of CBO is inevitable in all activities of the TI and other programs. P D’ s presence in the appointment of the Staff, contracting or routing the funds from KSACS, and Project Director’s attendance not only in monthly review meeting of the TI also in all kind of project activities including crisis management. During the commencement of CBO led ICTC and Ujawla, the  CBO was recruited enough staff for handling all these programs, so that they provides all kind of support to the concerned staff to perform optimum. PD and other four governing body members are also part of FSW-TI as they are holding different kind of positions in TI.

II. Organizational Capacity

1.  Human resources:

The human resources of CBO (Vanitha Society) consist of the Staff of TIs, Program Manager and the Staff of the various programs, FSW TI program and the Staff of the ICTC program in Govt: Hospital, Beach. The Program FSW TI reports periodically by print and voice to the P D of CBO. The organization is committed to implement the projects, and it has given sufficient authority to the Project manager to initiate necessary action for the achievement of the target of the TI project and to the counselor of ICTC.

The FSW TI project

Project Manager- 1 (Currently vacant)

Counsellor - 1

M&E Officer cum Accountant – 1

Outreach Workers -4 (1 ORW position vacant)

Peer Educators 12 ( 22 allotted and 10 PE position vacant)

2.  Capacity building:

The CBO led TI has conducted in house induction training for the new staffs. Most of the staff and few PEs trained STRC/KSACS trainings on TI project related topics. The Counselor trained in CBO managers training conducted by VHS (Social protection its importance in TI setting) and all ORWs were received trainings from KSAPS, STRC, and TSU on project components. Staff team need to put effort to familiarize OG and project proposal. The conceptual clarity of PEs should be improved by using hands-on training

3.  Infrastructure of the organization

The Vanitha Society has the necessary infrastructure to support its programs in Kozhikode district. The TI project has sufficient infrastructure for office and administration but space for DIC is not provides enough space for resting or recreation. It must be improved if DIC sustains along with the office. But TI provides privacy and instrumental for STI clinic as well.  TI office found easy accessible to the community.

4.  Documentation and Reporting:

The FSW –TI project is maintaining reports and documents as per the NACO guidelines. The project maintained master register/ line listing as both soft copy and hard copy. PEs format Form B is maintained by the PE s partly only but corrections with the help of ORWs. During the visit observed that ORWs are very familiar with B-form but that must be improved among PE s. Monthly outreach plan and weekly plan is maintained properly but need qualitative improvement. Daily dairy is maintained by all staff with minimum details. Monthly and weekly meeting minutes are maintained properly. Project director is attended every weekly/monthly meetings. The monthly reporting like SIMS and SOE is submitted by MEA within the time line suggested by the KSACS.

III.Program Deliverables Outreach

1.Line listing of the HRG by category.

Contacted FSW’s Line listing is available with the project level which reflects new and drop-out details of FSWs and maintained in soft and hard copies.

4.  Micro planning in place and the same is reflected in Quality and documentation.

The MIP / weekly plan and daily diary of the ORWs are maintained but need quality improvement. Among PE s also considering Form-B first part is as plan but few areas need improvement like activities not done carry forward to next day etc. PLOP documents available with project The quality of risk categorization, due, overdue listing by PCU wise found good. The follow-up actions and quality of reports or evidential documentation system needs improvement.

5.  Coverage of target population (sub-group wise):

As per the numbers presented by the Vanitha FSW project, they have achieved 83 %  coverage  (Regular contact) in last 22 months against the target. Project target for current year is 1349 whereas they have regularly contacted 1126 active FSW population.

6.Outreach planning

The projects outreach is planned based on MIP and with the help of PLOP. The ORWs and PEs do their planning for the coming month well before the starting of new month. That may be end of previous month during PE meeting. The ORW’s plan contains the name of the spots, number of HRGs, services details and the link services  they would visit, Peer team and ORWs are able to plan the number to be covered for services based on the risk  or those who needs to be followed up for specific needs if any.

7.  PE: HRG ratio

# There are 12 PEs in position and maintaining 22 PCUs with the support of ORWs/Counselor and other CBO office bearers so that they can manage an average HRG ratio to PE s and to FSWs.

8.  Regular contacts

The CBO project team identified/contacted and register the FSW population of 1378 against the target of 1349 in the period of April 2014 to January 2016. The current regular contact comes about 83.5 % or 1195 HRGs average. The ORWs and peers are aware of the regular contacts and they are able to report on the same on a monthly basis. They provide information on HIV, sexual Risk, harm reduction and condom education to the community at field level.

9.  Documentation of the peer education

The Format –B and peer daily diaries are the basic documents of peer education. The PEs daily dairy contains only information regarding date and place visited and in some cases name of the HRGs met. There is no uniformity in the way PEs maintain their diary. Similarly the number of condoms that was distributed during their daily field visit is also documented by all the PEs. The quality of documentation needs to improve if peers continuing with the daily diary.

10. Quality of peer education- messages, skills and reflection in the community

The Peer Educators having knowledge on transmission of HIV, prevention methods, sexual risks, service deliveries, condom demo and their field work as PE s. need further improvement in risk categorization and STIs. They are usually coming for the PE s meetings and field activities. Some of them are able to maintain Form-B but they are in fear of tabulation (totaling numbers) the documentation part and participation of in planning, PLOP process etc needs clarity /improvement. As they articulated, they needed an appropriate quality training to improve the outreach activities.

11. Supervision- mechanism, process, follow-up in action taken etc

The project staff team pursue both field level and review based supervision and it was visible that ORWs visited at least four days in a week for the field work, peer meetings, etc. all staff maintains the details of the places visited. The Form-D not properly used to motivate and provide support or it is not documented in F-D. For ORWs, PE s feedback/suggestions provided by both PM and PD. The weekly/monthly review meetings assess the work and identify the gap in components and plan for the next month. The process of supervision quality needs to be strengthened based on monitoring indicators. Proper documentation and follow-up actions needs to be done as a part of supervision.

IV. Services

1.Availability of STI services –

In this phase project is purely depends on Govt. doctors for the STI care and management of the FSW community. During the current phase linked with 8 govt. STI care settings, 1 PPP and project clinic was functioned. So that they can achieve 1350 HRGs visited ST clinic at least onetime and found   29 % HRG s attended for VDRL taste against the target of 1378.

2.  Quality of the services- infrastructure.

The FSW TI project established STI clinic is equipped with all the necessary facilities as per the NACO guideline. The clinic in charge in this phase found counselor. During the current phase project clinical activities found less but more on Govt. settings. They established linkages with 08 Govt. health facilities to manage the STI care to the HRGs. One PPP Doctor still continues at Manipuram near Padanilam.

4.  Quality of treatment in the service provisioning-

STI treatment is provided to community based on the screening by the Govt: doctors where the HRGs are referred. Similarly ICTC referral is also done periodically and followed up by the ORWs through the PEs. HRGs are referred to CBO led ICTC and other Govt: ICTCs. But the ORWs is most of the cases ask the HRGs to come to the CBO-ICTC centre and tested. The referral slips provided at their spot, but sometimes they might lose it. Whenever any reactive cases are identified they are immediately referred to the ART centre. This year the project identified 2 new cases as reactive and linked to ART centre.

5.  Documentation- Availability of treatment registers, referral slips, follow up cards

The project team does the RMC follow up based on their updated dynamic line list that is available with the counselor/ ORWs. Those who turn up for the centre with positive results are treated for STI by the doctor and that information is available in the referral slips maintained by the counselor. STI Treatment reports, referral slips are maintained for STI and ICTCs. No separate follow up list is available but patient wise sheet/slips maintains. The counselor updates the medicine register and counseling register. The counselor writes the date on which the referred HRGs visited the clinic in the referral slips that are available in the office. The stock registers for STI drugs / medicines are maintained by the counselor/M&E currently and the process GMP is applied for purchase of medicine.

6.  Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Detailed project level condom gap analysis is done in every quarter and as per the analysis report outreach team ensured the supply of both free and social marketing condom to HRGs based on the requirements. The channel of distribution is adopted by the project is through the DIC, Condom outlets, ORW staff and PEs.

7.  No. of condoms distributed- No. of condoms distributed

The following table shows the last year’s condom distribution against requirement through condom outlets, ORWs,PE s, counselor and through DIC.

| Last year | Requirement | Distributed |
| --- | --- | --- |
| TOTAL CONDOM DISTRIBUTION | 181992 | 137290 |
| SM CONDOM DISTRIBUTION | 42141 | 14760 |
| FREE CONDOM DISTRIBUTION | 139851 | 122530 |

9.  Information on linkages for ICTC, DOT, ART, STI clinics.

ICTC referral is done periodically according to the performance indicator of proposal and followed up by the Counselor and ORWs through the PEs. HRGs are referred to CBO-led ICTC, govt: ICTCs. The ICTC register the PID numbers also follows by the project if needed for referring to ART. Observed good rapport with Govt.STI clinics, ART center, DOT centers and in this phase project could refer HRGs to TB center for sputum testing.

10. Referrals and follows up

Referrals are mostly done by Counselor/ANM, ORWs to the concerned centers and HRGs are referred individually and sometime called to the centre as a mall group driven by PEs and given their respective referral slips in the centre. Regarding ICTC and STI referrals, the ORWs give referral slips based on when they need to undergo ICTC or STI testing based on due/overdue list prepared by ANM/Counselor. After the service accessibility the NGO copy of the referral slips are collected from the centre and documented/updated in the project level / PCU level service register.

V. Community participation

1.  Collectivization activities:

The community collectivization under this CBO led project is through the CBO memberships, community committees, SHGs, community staff (ORWs) and peer education. The project staff team articulated that from the beginning of the project itself CBO governing body members are strong enough to run a project. Now the community participation in all programs is vibrant and functional.

2.  Community participation in project activities-

The community participation in the project is visible and documented mainly through DIC meetings, Events, SHG activities and CBO general body meeting and election of office bearers. PEs, community committees and the community staff is already established in the documents and reflections during the evaluation. As a CBO led TI, project director itself representing and propagating the community in public programs and meetings.

VI. Linkages

1.Assess the linkages established with the various services providers…

Linkages with other ICTCs, STI clinics, ART, Govt. hospitals are expellant and they are having good rapport with staff team of the linked centers. HRGs are access the ICTC services with the support of PEs or individually at the CBO led ICTC and other centers. The referral register and referral slips properly maintained at project office. Now considering monthly DAPCU meetings are one of the platforms to strengthen Linkages.

2.  Percentages of HRGs tested in ICTC and gap between referred and tested.

During the current phase 1192 HRG s tested once HIV out of the targeted 1349 HRG s. (88 %) and only 82 HRGs tested twice. So there is a gap in this reported but the TI team articulated that this was happened due to the shortage of HIV kit in testing centers about 5 months out of 10 months in this year. According to the TI team, this is one of the issue KSACS / TSU need to address to achieve the TI performance.

3.  Support system developed with various stakeholders

The other Stakeholder’s involvement is visible in the program, in the project level it is there in crisis intervention with Advocates, Networking with pimps, auto drivers, gate keepers, etc.  Advocacy with police and other line departments, health, social welfare and with District collector also documented properly. Network with Police dept and health dept. is remarkable to ensure their support to the project.

VII. Financial systems and procedures

- Systems of planning :

There is system of planning in the project found. The monthly meetings are conducting in project regularly to assess the program achievements and budget utilization was properly done by the project.

- Systems of payments  :

90% of the payments were settled by cheques. Voucher prepared by accountant verified by project manager and approved by project director. It is observed that some vouchers are supported by bills/statements.

- Systems of procurement :

The CBO –TI is adherent to KSACS guideline for procurement system. Project not purchased any assets during the year. The assets are listed and codified.

- Systems of documentation :

Cash book maintained in daily basis. Bank account is jointly operated and Bank reconciliation made on monthly basis and SOEs are submitting in time. Receipts and payment Account and Bank reconciliation statement prepared properly.

VIII. Competency of the project staff

VIII a. Project Manager

Project Manager’s post kept vacant

VIII b. Counselor

Counselor, Mrs.Dilna P. (MSW) having one year experience in FSW TI, Clarity on risk and vulnerability, risk assessment and other harm reduction strategies found good. Counselor as such trying to do the individual tracking of HRGs, follows up and ART motivational counseling’s also. STI counseling register maintain properly. Maintenance and updating of data and registers related to clinic originated in time and fine. Field visits, Advocacy meetings and initiation of linkages also found.

Counselor taking extra effort to manage TI in the absence of project manager and it succeeded remarkably.

VIII c. M & EA

Mr.Nabeel N. M.com, Monitoring and Evaluation Officer cum Accountant had 7 months experience in the project. Initially this post is separated but now converted as M&EA. Now he is entrusted the in-charge of all data base SMIS, other soft documents. M&EA maintaining HRG master register but need to improve the data analysis but the field level data sharing with ORWs, reporting of feed back to ORWs also found good. The office administration and accounts also maintained by M&EA but he needs training in data analysis and on different formats according to the NACO guideline. MEA maintains all necessary soft data in the project and sending SMIS, SOEs and other reports in time. Need concept clarity on community’s behavior, tabulation & Analysis, project proposal to be strengthened.

VIII d. ORW

ORW’s knowledge about target on various indicators for their PEs is found good. ORWs working with proper implementation plan. Outreach plan for each hot spot in place and the orientation on Hotspot analysis and other tools are found with PLOP support. Conducting the weekly review meeting with peer educators in the field and office and it was documented properly. Knowledge on STI, HIV, TB, ART & ICTC is satisfactory. Need more clarity on community mobilization as a CBO TI. STI management was established with Govt. and PPP settings in the project area. Providing support to PEs in field level activities and documented properly but need clarity on Format-D. All documents and formats of PEs are up dating by ORWs only but with the consultation of P E s. Community mobilization and collectivization components need to be strengthened further.

VIII e. Peer educators

The evaluation team could interact with 12 peer educators out of 22 P E s allotted for project during the meeting. According to the project, TSU instructed them to re-size the PE s with the support of PE s appraisal and the project kept 10 PE s post vacant.

- All PE s Found doing condom distribution and few (8) P Es doing Format-B independently and regularly.

- All PE s having condom demo skill.

- Prioritization of hotspots in PE level about 36 % spots were taking place

- 30 % shows lack of clarity on risk and vulnerability factors.

- Importance of ICTC testing, STI testing and knowledge about condom depot found good.

- Knowledge on symptoms of STIs and STI treatment facility need improvement.

- 30 % PEs has limited knowledge on spot analysis and PLOP tools.

IX. a. Outreach activity in Core TI project

- Outreach plan and micro plan in place for outreach team and that same was formulating with the help of PEs and ORWs and implementing without any major issues.

- All deliverables of the project was achieved through outreach planning and monitoring with performance monitoring indicators or target.

- Application of PLOP tools, weekly reviews, committee meetings and other community feed backs considering for evidence based planning and outreach.

- Outreach monitoring is mainly through accompanied field work, Demand generation meetings, referrals v/s testing or service uptakes found well placed.

- Analysis of condom uptake and metrics of condom, social marketing etc. and community mobilized towards CBO and project at least usage of DICs also visible.But DIC need more space as demanded by the community.

X. Services

During the current phase 1192 HRG s tested once HIV out of the targeted 1349 HRG s. (88 %) and only 82 HRGs tested twice. So there is a gap in this reported but the TI team articulated that this was happened due to the shortage of HIV kit in testing centers about 5 months out of 10 months in this year. According to the TI team, this is one of the issue KSACS / TSU need to address to achieve the TI performance.  The FSW TI project established STI clinic is equipped with all the necessary facilities as per the NACO guideline. The clinic in charge in this phase found counselor. During the current phase project clinical activities found less but more on Govt. settings. They established linkages with 08 Govt. health facilities to manage the STI care to the HRGs. One PPP Doctor still continues at Manipuram near Padanilam.

XI. Community involvement

Community participation in project activity is through membership in the CBO, SHG, Other community committees is visible. The project should initiate again the community mobilization activities of leader posts were deleted.  Currently the SHG formed is functioning but need improvement. The process of CBO strengthening should be planned with considering the opinions of the unreached community too. CBO members stated that, So far 1310 members were registered by CBO but related documents are not visible or missing.

During the last year, community members attended in the community event found less. It is observed that the involvement of community members in the similar programs must be improved.

Community Events reported in last phase:

| SN | Events | Date | Place | No. of Participants |
| --- | --- | --- | --- | --- |
| 1 | COMMUNITY EVENT | 6-6-15 | THAMARASSERI | 59 |
| 2 | ONAVILLU | 26-8-15 | THAMARASSERI | 30 |
| 3 | SANGAMAM 2016 | 28-12-15 | KUNNAMAGALAM | 199 |

XII. Commodities

Project conducting condom gap analysis in every quarter in last two years with weekly re-call method and the same was reflected in Format-B. Outreach team ensured the supply of both free and social marketing condom to HRGs based on the requirements. The channel of distribution is adopted by the project is through the DIC, Condom outlets, ORW staff and PEs. Community not aware of female condoms available in the market and the same was demonstrated once in staff training.

XIII. Enabling environment;

Advocacy program is happening in the project found on need based, this is one of the area need to be improved by conducting power analysis, prioritization of stakeholder groups and make advocacy plan etc. is lacking. But the advocacy is happening based on the situation and all members including CBO governing body members also part of the program which ensures result. As a part of developing linkage and network project initiation found excellent as its own kind.

So far project level advocacy as follows:

| ADVOCACY | Meetings done |
| --- | --- |
| POLICE | 2 |
| PRI | 2 |
| DOCTOR | 1 |
| SEVA BHARATHI | 2 |
| CITU | 3 |
| CHILD LINE,DAPCU, VIHAN, VCU INDIA, PIMP/BROKER, CHARITABLE GROUPS | 6 |
| AS A PART OF CRISIS MANAGEMENT | 4 |

XIV. Social protection schemes ( innovation at project level HRG availed welfare schemes, social  entitlements etc.)

During the evaluation period it is found that few social entitlement activities benefited to the community with the help of TI, other staffs at different line departments. The following list of such things available with TI.

  - Possession of ration cards, Aadhar cards, voters ID cards Land for landless, IGP for its members.

  - CBO mobilizing funds through IGP programs, coupons, donations etc.

  - Income generation programs (phenol making unit, tailoring etc.)

  - Formation of SHGs and micro- finance.

  - Rehabilitation of positive HRGs and their child.

  - Positive HRG got land and home through Agathi Asraya programme by Govt of Kerala.

XV. Best Practices if any

Not found any program to consider as best practice.

End report.