Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organisation

Bharat Sevak Samaj (BSS) is a national level NGO registered in 1952 at New Delhi. At present, it is headquartered at Thiruvananthapuram. Since 1st November 2010, BSS is implementing the IDU intervention in the rural areas of Thiruvananthapuram district.

FPAI had been implementing partner for the IDU intervention since its initiation in Thiruvananthapuram district. For effective outreach the intervention in rural area, it was handed over to St. John’s Health Services with a population of 287 IDU HRGs during November 2008. After managing the project for 2 years, St. John’s withdrew their association with the programme owing to organizational priorities and was replaced by BSS in November 2010 with a coverage of 322 IDUs. During November 2011, the population was scaled up to 386 by adding 99 IDUs from adjacent coastal and rural villages of Kollam district which was formerly addressed by FPAI. Last year, the population was again streamlined by eliminating the population from Kollam district. Currently, the project is working among 249 IDUs in two major sites of Thiruvananthapuram rural.

| Name and address of the Organization | BSS IDU Project Thiruvananthapuram |
| --- | --- |
| Chief Functionary | Mrs. Jaya Sreekumar |
| Year of establishment | 2/9/1967 |
| Address of the project office |  |
| Project Director | Mrs. Jaya Sreekumar |
| Year and month of project initiation | 1st November 2010 |
| Evaluation team | Mrs. Sonia Ratheesh Mr. Akhil P |
| Time frame | 1st and 2nd February 2016 |

Profile of TI

| Target population profile | IDU |
| --- | --- |
| Type of the project | Core TI |
| Size of the Target group | 249 |
| Sub groups and their size | - |
| Target areas | Varkala and Kadinamkulam |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

BSS, being an esteemed organisation working in the field of development and education for many decades, believes that incidence of new HIV/STI infection can be waved off by the joint efforts of the project and the self- motivation of the injecting drug users. The evaluation team was able to interact with the Director, Mrs. Jaya Sreekumar during the process of evaluation.

The NGO had been associated with KSACS since 2010. It is noted that the NGO does not have much clarity about the IDU intervention though they are willing whole-heartedly to support the project in all possible ways. Project monitoring is conducted by the Director of the project. She attends all the review and planning meetings and staff meetings. The NGO relies heavily on the experienced manager to run the project.

- Organizational Capacity

  - Human resources: All the staffs are placed as per the TI staff allocation in the proposal. The work is done, reported and supervised in a systematic manner adhering to the NACO norms which is ensured by TSU/SACS. But the Quality of the staff, and thus the work done, is a cause of concern.

  - Capacity building: All the staff got Induction training by STRC/KSACS. The new staff, one ORW and the nurse are yet to be imparted skill development training related to their specific work area. In-house trainings for staff and PEs were reported to have taken place as an extension of the meetings, but no reports of the content and module were found in the documentation during the period under review.

  - Infrastructure of the organization: Good and well maintained infrastructure is available in the office. No separate DICs are functioning due to lack of funds.

  - Documentation and Reporting: Documentation is done as per NACO guidelines.

III. Program Deliverables

Outreach

- Line listing of the HRG by category is available. 249 IDUs are line listed.

- Micro planning is seen on the documents.

- Coverage of target population: 249. According to the registers, all the HRGs are regularly contacted. But it is noted that the staff heavily rely on the peer educators to provide services to the HRGs. Mostly it is their word against the actual interaction with the HRGs. Thus, though it is reported that peer educators are in regular contact with the HRGs, only around 30% of the HRGs are met by the staff/ORWs. HRG-Staff connection is an all-time low in the project.

- Outreach planning is done through B Form, but the effectiveness is a question.

- PE: HRG ratio. All PEs are in place as per the project design.

- Documentation of the peer education is done through B Form. PE daily diaries were not available for perusal.

Quality of peer education: This needs drastic improvement. The messages passed by the PEs were noted to be not making any impact on HRGs other than passing on fresh injecting paraphernalia. No proper behaviour change communication messages are communicated to the HRGs. Lack of sufficient in-house training is noted. PEs needs more training to improve their skills.

- Supervision: Supervision mechanism is a major concern in the project. Lack of an effective field support is evident, though field visits are done by ORWs and other staff. Understanding and clarity regarding intensive and supportive supervision is lacking in the project which affects the quality of the outcome.

IV. Services

- Availability of STI services: STI clinic is in place. It is noted that the clinic is comparably far away from the target area. The difficulty was due to the fact that it was difficult to find an office in the target area due to the volatile nature of the HRGs and the reduced budgetary provision for hiring an office.

- Quality of the services: Infrastructure of the project clinic is good. Clinic has all the equipment as per NACO Guideline and privacy is assured in the clinics. Rotator was not made available by KSACS which had affected the Syphilis screening process. Follow up mechanism should be regularized and improved. Follow-up should also be part of the prioritization of HRG such that the component is well accommodated. This aspect is at present totally neglected.

- Quality of treatment in the service provisioning: Referral to ICTC is done, 74% of the HRGs had undergone HIV testing. The lone HIV positive identified is not on ART owing to the high CD4 count. Abscess cases were treated at the project clinic and followed up by the nurse.

- Documentation: All STI related documents and register are maintained systematically since the current project officer from TSU took charge.

- Availability of Condoms: Condom availability and distribution is fair. Condom is distributed through Pes. It is reported that requirement is met. But the future of condom programming is in apprehension as free condoms are not available anymore in projects and the social marketing condoms are not accepted by the HRGs. Social marketing condoms is reported to be at 14% share of the total condom distribution.

V. Community participation

- Collectivization activities: In spite of being a senior project, no much effort is noticed to collectivize the HRGs.

- Community participation in project activities: Level of involvement of the community members in the project is negligible. Accept for the peer educators, none of the HRGs are involved in any of the project activities.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc: Please refer the details given above.

- Support system developed with various stakeholders and involvement of various stakeholders in the project: Linkages with the police and local self-government systems are not very strong and is found to be merely need-based. Rapport with the health care providers was found to be fair.  The need for maintaining linkages with various stakeholders is not clearly understood or explored by the project.

VII. Financial systems and procedures

All the financial systems and procedures are complied with as per NACO guidelines and under the supervision of KSACS and TSU. The financial crunch had created troubles for this project as well, as it had been affecting the projects across the state.

VIII. Competency of the project staff

- Project Manager: The project manager is an MSW graduate with sufficient experience as per the NACO/SACS norms. He is the senior most staff of the project and had been with the project since its inception. But it is unfortunate that the experience and qualification is not being translated into action and thus the manager is found to be the weakest link of the project which is yet to bloom from its infancy stage. Lack of his initiative, leadership and guidance had affected the project very badly. His knowledge about the program performance indicators are not up to the mark in spite of various trainings that he had attended due his tenure in the project. He gives focus on “target” achievement and not on the behaviour change of the HRGs, thus the staff lacks clarity on the basic object of the project and how to deal with the HRGs. He fails to instil team spirit into the project staff and thus a lack of team spirit is noted amongst the team members. His lethargic attitude had adversely affected the performance of the project.

- ANM: The ANM is a comparably new staff of the project. His clarity and understanding about TI programme and his involvement in the programme is fair. Clarity on risk assessment and risk reduction, and knowledge on basic counselling, etc. needs improvement. He received training on the aforesaid as a new comer into the project and thus had not properly sunk in, due to which he expressed the feeling that an update is essential to clarify and confirm the knowledge. Need clarity in few areas like types of counselling, risk based referrals, etc. He does field visits on a need based basis apart from supporting the doctor at the STI clinic. Lack of proper guidance from the manager is evident in his performance and confidence.

- ORW: There are two ORWs in the project. One of them is new to the project and the other one is one and a half years old in the project. It is surprising to note that the new ORW is active, more systematic and ready to learn when compared to the senior ORW. Lack of guidance from the manager had affected the ORWs too. The ORWs needs a special hand holding. Their clarity regarding TI programme and its various components need to be improved drastically to scale up the performance of the project. Re-defining the PE/ORW link and understanding and enhancing their acceptance among the PEs and community are a necessity.

- Peer educators: The project has peer educators placed as per the requirement. The current PEs are potential candidates for the post.  But their knowledge regarding the project and project components is a major concern. PEs needs training and handholding through series of in-house trainings. PEs currently functions as needle and syringe exchange agents rather than peer educators which is a pathetic condition. They should be trained and equipped in peer education such that the objective of an IDU project is clearly understood by them and subsequently by the HRGs.

- M&E officer: M&E officer is one of the senior most staff of the project. His knowledge regarding finance management and CMIS is fair. There seems to be a power struggle and a lack of coordination between the manager and the M&E officer. This affects the team adversely. It was evident even during the project evaluation.

IX. a. Outreach activity in Core TI project

Field outreach and peer education/support process are the key to interact with the HRGs. The outreach activity of the project is not satisfactory. As mentioned above, the outreach activity is mostly revolving around the peer educators and the involvement of the staff with the HRGs on a regular basis is very low. This results in the lack of proper understanding of the project among the PEs and the HRGs. During the evaluation, the team was repeatedly asked to address matters such as arranging a safe injecting space, giving a month/week dosage of OST drug together to the HRGs. These were voiced out by the PEs indicating their lack of proper understanding about the project. Being a senior project, such lack of understanding is a grave situation. PE capacity needs to be immediately enhanced. Counselling is yet another area which need improvement.

X. Services

Please check the previous information regarding services.

XI. Community involvement

Community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc is negligible. The process of community participation needs to be initiated and this could be supported by the NGO.

XII. Enabling environment

Systematic plan for advocacy is not there and involvement of community in the advocacy is nil. Documentation should be enhanced.

XV. Best Practices if any: No best practices noted.