Confidential

Reporting Form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators |  | Contact Details with phone no. |
| --- | --- | --- |
| Mrs. Sonia Ratheesh |  | 9946009946 |
| Mr. Anish T. A. |  |  |
| Officials from SACS/TSU (as facilitator) |  | Mr. Renjith (PO – TSU) |

| Name of the NGO: |  |  |  | BSS |
| --- | --- | --- | --- | --- |
| Typology of the target population: |  |  |  | IDU |
| Total population being covered against target: |  |  |  | 249 |
| Dates of Visit: |  |  |  | 1st and 2nd February 2016 |
| Place of Visit: |  |  |  | Thiruvananthapuram |

Overall Rating based programme delivery score:

| Total | Score | Category | Rating | Recommendations |  |
| --- | --- | --- | --- | --- | --- |
| Obtained (in %) |  |  |  |  |  |
| 61.5% |  | B | Good | Recommended for continuation with specific conditions |  |

Specific Recommendations:

- The need for an IDU project in the area is imminent. But the current staff is not conducive for an effective intervention. A phased-out staff replacement process needs to be done at the earliest to save the project from complete disaster. The manager, being the weakest link of the project, should be replaced with immediate effect with an experienced and vibrant person. - Close monitoring of the project from TSU/KSACS need to be ensured such that the aforesaid matter is addressed. Moreover handholding of the project by the competent authority is deemed essential in the current juncture. Active involvement and monitoring of the project should be done by BSS. - In-house trainings should be conducted for the PEs so that it benefits the HRGs. Clarity regarding the project and project components, especially BCC need to be imparted to the PEs. There should be a constant follow-up of the trainings imparted and performance need to be monitored on a regular basis. - Micro planning with special emphasis on behaviour change should be done in the project. - Prioritization of follow-up services based on risk and vulnerability should be regularly done. Counselling need to be focussed sufficiently. - Area friendly strategy should be developed to increase regular contact for benefit of majority of the HRGs. Field visits and other field level activities need to be strengthened. - Efforts should be taken to establish effective and productive linkages with various stakeholders of the project.

| Name of the evaluators |  | Signature |
| --- | --- | --- |
| Mrs. Sonia Ratheesh |  |  |
| Mr. Akhil P |  |  |