Reporting Format-B

Introduction

o Background of Project and Organisation

CSRD is established as a Human Rights NGO and is the first NGO in Kerala which started working with sex workers (1995) and has been implementing TI since its inception in the State in 1997. (KSACS initiated TI in Kerala in 1997 and the previous year DfID had done some TI spade works, directly through the NGOs, and CSRD was a partner in its work in Calicut.) Since, in the beginning, there were only two NGOs doing TI in Kerala (Cochin and Calicut) the opposition from the moral public was severely heavy.. To withstand this opposition a sex workers organization “Vanitha Vimochana Vedi” was formed and the board was put up in front of the office in 1998 itself (registered in 2000) which is now known as Vanitha Society.CSRD was the first NGO in the state to hand over the TI project to a CBO that too within five years of TI implementation.

Prior to the starting of the HIV intervention program CSRD was addressing the Human Rights issues of sex workers, particularly the police atrocities. By the implementation of the SW project CSRD could gain a wealth of knowledge and experience in the TI implementation and also could build good net work with the relevant Govt. Departments and could establish high good-will among the Calicut public, including the media and police department.

Then CSRD moved to implement the first IDU project of Kerala (mid-2003) and has completed 10 years of implementation. In the beginning itself CSRD had set up a drop in center in Bangladesh Colony for NSEP and other services, where around hundred IDUs used to drop in a day. This brought the normally occurring over-doze deaths, which was spread out in the town, to one location thereby causing some law and order problems. Concomitantly, by the direction of the District Collector the DIC was closed down and as a strategy shift the project adopted mobile NSEP through PEs and Out Reach staff which is going on steadily since then.

In August 2007 CSRD initiated one of the first OST programs in Kerala and has proved to be a workable harm reduction program to address the drug issues in Calicut. So far 145 injecting drug users have utilized this facility, of them 43 are currently ongoing.

o Name and address of the Organization : Centre For Social Research & Development

Opposite Konnad Bus Stop,Beach Road ,West Hill (P.O) ,Calicut -05.

o Chief Functionary: Mr. Peethambaran .K

o Year of establishment  : 1995

o Year and month of project initiation: June 2003

o Evaluation team  : Dr. Sobha Mathew and Mr. Vineesh

o Time frame        :12/2/16 to 13/2/16

o Target Population Profile:  IDU

Type of Project: Core

o Size of Target Group(s)   :  506

o Sub-Groups and their Size

Daily Users-0

Non Daily Users-506

o Target Area

| Target Area | Population |
| --- | --- |
| Feroke | 168 |
| Medical College | 181 |
| Palayam | 157 |
| Total | 506 |

Key Findings and recommendations on Various Project Components

1.Organizational support to the programme

CSRD is an NGO working in the social sector and so the NGO is committed for conducting social activities. Then CSRD was the first IDU project of Kerala (mid-2003) and has completed 12 years of implementation. Despite all the oppositions CSRD continued Needle Exchange program right from the beginning of the project . The result of these bold actions reflects in the HIV scenario among the IDUs in Calicut, where the infection has come down to zero (ICTC-2011-12) from a recorded high jumping of it in the sentinel studies. (2004-2.5 %, 2005-5.2%, 2006-7.8%). The NGO is taking care of the community consideration. The project has initiated advocacy activities according to the need. The recruitment of staff periodic monitoring of the activities was done by the NGO.

II. Organizational Capacity

All the staff position in the project are filled within the time frame given by KSACS. The staff pattern of the project is as follows

| Category of staff | No |
| --- | --- |
| Project manager | 1 |
| Counselor | 1 |
| Nurse | 1 |
| ORW | 3 |
| Total | 6 |

Appointment letters along with the job responsibilities was given by the NGO.

Daily diary of the staff shows that orientation is given to the newly recruited staff .No proper documents showing that in house trainings was conducted by the project. Capacity Building of the staff should be improved. Harm Reduction Training should be given to all the staffs.

3. Infrastructure of the organization

Infrastructure and spacing is adequate for the project to operate. The drop in of the clients in the DIC is very low and the drop in of the HRGs in the main office is not maintained, only the drop in of the OST clients who are availing services from the Beach Hospital is maintained in the OST centre .  Separate drop in registers should be maintained. The clinic room is hygienic and is maintained properly according to NACO guideline.

4. Documentation and Reporting according to the SACS protocol. Reports especially General CMIS , STI CMIS and the Financial Reports were submitted on time. Weekly review meetings and Monthly review meetings are conducted but the documentation part should be strengthened .Financial Planning should also be included in the meeting.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.  All the HRGs are line listed and updated and prioritization of HRGs done. Got information regarding young IDUs while interacting with the stakeholders . There is a gap in identifying new young HRGs, so the TI should take initiatives to find out the new identifications. The Peer Educators are above the age of 35 yrs and it might be the reason for gap in new identification process.

2. Micro planning in place and the same is reflected in Quality and documentation.

PLOP tool and Micro plan are in place.97% IDUs tested HIV  once during the last year ( 2014 – 2015) and  88% of the IDUs has undergone HIV  testing once during this year ( 2015- 2016 ), 95% of the IDUs were screened once for VDRL during the last year (2014 – 2015) and 95% of the IDUs during this year ( 2015- 2016 ).

3.Coverage of target population (sub-group wise):

Target / regular contacts 506/ 392 HRGs are regularly contacted by the project.

4. Outreach planning – quality, documentation and reflection in implementation

Outreach planning is according the Form B.  Clarity of Planning should be improved. The project is one of the learning site and they have their own training programmes for all level staffs. It may utilize for capacity building of the staffs and PEs .Form B and daily diary are prepared with the involvement of PEs. Need based services are provided to the HRGs.

5. PE: HRG ratio,

PE: HRG ratio is maintained according to the proposal.

6. Regular contacts

Regular contacts are calculated according to the need based services provided by the outreach workers. 79% of the HRGs are regularly contacted by the project.

7. Documentation of the peer education

B forms are prepared  by PEs with the involvement of Out Reach Worker .

8. Quality of peer education- messages, skills and reflection in the community

Interacted with 11 PEs and all the PEs are above 30 yrs . Project should take steps to recruit young PEs to identify young IDUs through innovative approaches. The quality of the PEs should be strengthened by conducting PE trainings on Harm Reduction & Safe injection.

9. Supervision- mechanism, process, follow-up in action taken etc

All the documents are maintained with minimum details. The documents were verified by the concerned staff .Supportive supervision was given to the staff in limited area, it should be done at various levels and in all the areas where there is a need .Capacity building of the staff should also be strengthened by conducting in-house training programme at project level. The project is one of the learning site and they have their own training programmes for all level staffs. It may utilize for capacity building of the staffs and PEs.

IV. Services

1.Availability of STI services – mode of delivery, adequacy to the needs of the community.

STI screening was done by the OST doctor and VDRL test was conducted in a lab at Beach Hospital. Visited the lab and verified the slips. Abscess Management services was provided by the project . STI register , VDRL referral slips and Abscess Management registers were maintained by the project . STI kits are also available and it is properly stored .

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Adequate infrastructure is present in the clinic and the clinic is maintained according to the NACO guideline. There is privacy in the clinic. Doctor is available in the DIC twice a week, and the clinic uptake good . 98 % of the HRGs has undergone regular medical checkups.

3..Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

Among IDUs no STI cases were reported during the year . 95% HRGs  has undergone VDRL testing & 89% HRGs has undergone ICTC testing . 4 cases were reported HIV positive and all of them have registered in the ART. Regular follow up was done by the staff  None  of  the HRGs were referred to DOTs centre .

4. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for STI medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard. Clinic forms were available and verified.  Visited the Regional Lab of Beach Hospital and Sneha Centre of W&C and verified the referral slips . Medicines have not seen purchased by the project. STI drug register present.

5. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Condoms are available in the project office during the time of verification. Verified the stock register. Condoms are distributed through Non-traditional outlets, PEs and ORWs.	Only free condoms were distributed by the project. No initiatives taken to promote social marketing. Condoms requirement analysis done.

6. No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

6870 free condoms were distributed during the last year and 6564 during this year . Condom distribution is conducted through PEs and also through non traditional outlet. Condom requirement gap analysis done quarterly  in the project .Condom stock registers maintained.

7. No. of Needles / Syringes distributed through outreach / DIC.

10727 syringes and 21454 needles were distributed during the last year and 8096 syringes and 16192 needles were distributed through outreach by PEs  , DIC and unmanned outlets during this year. N/S requirement analysis was accurately done quarterly but only 74% of the HRGs are receiving N/S as per requirement. The tracking of N/S Distribution to be strengthened. A separate stock register should be maintained both in the main office and OST centre. The mechanism adopted for waste disposal of N/S is appreciated. Due to the financial crisis IMAGE were not taking  the waste so the  project has made tie up with the nearest government hospital  for waste disposal and the documents were also properly  maintained .

8. Information on linkages for ICTC, DOT, ART, STI clinics.

All the staff & PEs were aware of ICTC and STI clinic and they have a good linkage with the ICTC centre. Needs to strengthen the DOTs referral. The PEs and staff are not aware of the importance of DOTs referral.

9. Referrals and follow up

Referrals are documented & monitored by the ANM/Counsellor . Colour coded PE tracking not present to ensure the follow up services especially ICTC & VDRL.

V. Community participation

Collectivization activities:

Currently, only 36 people are OST from centre . The project has Initiated CBO formation in the year of 2003 but no efforts taken to strengthen the CBO, which is already created. The initiatives of community members may come up through the strengthening of CBO.CBO was formed with membership of 64 HRGs . Should increase the involvement of HRGs in the community committees .

Three community committees were formed and the meetings were not conducted regularly. Involvement of HRGs should be strengthened and it should be reflected in the planning.

Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Planning is only in the ORW level. Only one event was conducted .Community participation should also be strengthened.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

STI screening is done in the OST Centre itself .VDRL screening is done in the Regional Lab of Beach Hospital. The lab is accessible to all the HRGs . VDRL testing is conducted according to the plan.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

100% of the HRGs were referred and 97 % were tested for ICTC once in the last  year and 100% of the HRGs referred and 89%  were  tested during this year.

3. Support system developed with various stakeholders and involvement of various stakeholders in the project.

No such mechanism developed in the project.

VII. Financial systems and procedures

1. Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

Adhered to the guidelines of KSACS.

2. Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

Cash books entries are correct. the project is using printed and serialized vouchers . Financial planning is not mentioned in the minutes. Stock registers maintained but issue of commodities to the DIC was not mentioned.

3. Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

Procurement done according to SACS/NACO guidelines.

4. Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

Maintained separate Bank Account. Audit report not received.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience of the project is  as per norm

Has to strengthen the knowledge of Harm reduction.

Quarterly and monthly plan is in place.

Regularly conduct review meetings but financial planning is not documented properly.

Monitoring and field visit conducted but not documented properly. Needs to strengthen the supportive supervision with scientific tool.

Advocacy initiatives were taken.

VIII b ANM

Educational qualification & Experience of the project is as per norm

Needs to improve the clarity on guidelines of waste management, risk assessment and risk reduction,

Has to strengthen the knowledge on basic symptoms of STIs.

Needs to strengthen the documentation according to NACO guideline.

ANM has adequate abscess management skills..

VIII c. Counsellor in IDU TI

Educational qualification & Experience of the project is  as per norm.

Counsellor is from the Community and he has the knowledge about local drug abuse scenario.

He has the knowledge on basic counselling and HIV, STI symptoms

Should maintain and update data and registers as per the guideline.

Needs training regarding drug related counselling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

.

VIII d. ORW

Interacted with 3 ORWs .All the three ORWs had attended the Harm Reduction Training.

Planning is based on the B form and colour coded tracking plan. Has the knowledge of the importance of  RMC and ICTC testing .Supportive supervision to PEs needs to be strengthened .Field level action based on review meetings is not reflected in the documents. Needs to strengthen the documentation especially daily diary.

VIII f. Peer educators in IDU TI

Out of 12 PEs, the review team interacted with 11 PEs. All the PEs are above the age of 30yrs, so new identification is very less and the number of daily users is nil. From the discussion it was clear that the quality of peer education has to improve in  the areas of harm reduction practices and safe injections. Training of PEs needs to be regularized.

VIII i. M&E officer

The post is vacant

IX. a. Outreach activity in Core TI project

Interact with PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

Outreach activities are conducted according to B form. Micro plans were prepared for the ICTC and VDRL testing .No color coded PE tracking format. Needs to improve the planning in case of NSEP since only 74% of the IDUs are receiving needles are per requirement plan. There is scope for improvement in case of new identification and to identify the daily users.. HRG is included in the planning process.

Out of 12 PEs, the review team could meet and discuss with 11 PEs during the review.  From the discussion it was clear that the quality of peer education needs to be improved in the areas of harm reduction practices and safe injections. New PEs who is young should be recruited for scaling up the programme especially for identifying young daily injectors’ .Training of PEs need to be regularized.  Supportive supervision was given to the staff in limited area, it should be done at various levels and in all the areas where there is a need .Capacity building of the staff should also be strengthened by conducting in-house training programme at project level especially to the ORWs and the Nurse .

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Visited ICTC in the target area, especially at Beach Hospital.

Verified the slips with the ID number and PID number. It was observed that, 448/506  (89%) of HRGs has undergone HIV test from various ICTC centres in the target area during this year . 4 positive cases were reported and all of them were registered in the ART. Regular follow up of the IDU PLHIV should be done by the ANM/Counsellor .

- VDRL Lab Visit

The project developed one government VDRL lab especially at Beach Hospital .  The project team said the that the accessibility of the lab by the HRGs is very easy  since it is in the heart of the city .VDRL referral are conducted according to the plan .Among IDUs no  STI cases are  reported during the year .95% HRGs  has undergone VDRL test once during the year  .

XI. Community involvement

Community committees should also be strengthened by conducting regular meeting , so that the community participation can be improved. The project has Initiated CBO formation in the year of 2003 but no efforts taken to strengthen the CBO, which is already created. The initiatives of community members may come up through the strengthening of CBO CBO should be strengthened with the involvement of HRGs, now only 17% of the HRGs are involved in the community events.  HRGs should also be involved in the Advocacy programme which is conducted by the project.

XII. Commodities

Planning as per B form. Condom requirement gap analysis done. Condoms distributed according to the requirement. No female condoms distributed.PCU wise condom and needles and syringes calculated and distributed by PEs .Distributed swab and distil water. Swab distributed not according to the number of episodes of injecting.

XIII. Enabling environment

There is no proper planning for advocacy in the project. Advocacy programs were not conducted in the project but only one –one interaction conducted. Community involvement in advocacy is very low.   Power analysis done but not according the NACO guideline, it needs to be improved for developing advocacy plan. No crisis management system developed till the time. The review team observed that the project staff did not have any clarity about the importance of crisis management system in the project area. In the community committees HRGs involvement is less, needs to strengthen it.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

No social protection schemes availed by the project.

XV. Best Practices if any

- Waste Management Linked with Government System.

- VDRL testing done at the Regional Lab.