Annexure C

Reporting form C

Confidential

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Helvis vazhapully | 9400780202 helvisv@gmail.com |
| Joyis K V | 9446700439 joyskv@gmail.com |
| Officials from SACS/TSU (as facilitator) | Renjith A J |

| Name of the NGO: | OISCA |
| --- | --- |
| Typology of the target population: | IDU |
| Total population being covered against target: | 382 |
| Dates of Visit: | 5-2-16, 6-2-16 |
| Place of Visit: | Koilandy, Kozhikode |

Overall Rating based program delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- Observed the Fund shortage which directly influences human resource in the program. - Recommended to give immediate attention to fill the vacant staff positions to avoid over load/overlap. - The project needs to re-arrange the HRG-ORW ratio according to NACO guideline. - Project need to focus on new HRGs / revalidate spots if needed as IDU project.(Site may change frequently) - Project need to put effort to increase OST uptake as injecting mode to non-injecting mode.(Project may insist Link / OST center at Koilandy) - Staff team (New) need to put forth effort to familiarize Operational Guidelines and project proposal. - The conceptual clarity of PEs should be improved by using hands-on training or adaptation of alternate learning methods. - Community participation in TI must be improved as seven year old TI.

Name of the evaluators	Signature

| Helvis vazhapully |  |
| --- | --- |
| Joyis K V |  |