Reporting Format-B

Introduction

o Background of Project and Organisation

Solidarity Movement of India is a Non-governmental Organization registered under Travancore Cochin Literary Scientific, and Charitable Societies Registration Act (Reg.No.1/76/87). Since 2008, Solidarity has been implementing targeted intervention programme among IDUs residing/operating in the northern areas of Ernakulum district. The project is covering 386 injecting drug users in four sites viz, Muvattupuzha (210), Kothamangalam (92) Perumbavur (84),

Solidarity was started in 1984 and formally got registered in 1987. Implementation of Suraksha IDU Project at Muvattupuzha had begun on 1st November 2008. Prior to this, CAPS IDU Project was extending their services to the IDUs in this area. Due to limited resource, CAP’s outreach to the area was minimal and hence the KSACS decided to start a separate intervention and engaged Solidarity.

o Chief Functionary	: 	Adv T K Thulaseedharan Pillai

o Year of establishment  : 1987

o Year and month of project initiation: 2008 November 1st

o Evaluation team  : Dr. Sobha Mathew and Mr. Ajith V.C

o Time frame        :1/4/14 to 31/1/16

o Target Population Profile:  IDU

Type of Project: Core

o Size of Target Group(s)   :  386

o Sub-Groups and their Size

Daily Users- 58

Non Daily Users-328

o Target Area

| Target Area | Population |
| --- | --- |
| Muvattupuzha | 210 |
| Perumbavoor | 84 |
| Kothamangalam | 92 |
| Total | 386 |

Key Findings and recommendations on Various Project Components

1.Organizational support to the programme

Solidarity Movement of India is a Non-governmental Organization registered under Travancore Cochin Literary Scientific, and Charitable Societies Registration Act (Reg.No.1/76/87) .It is an NGO working in the social sector and so the NGO is committed for conducting social activities. The Project Director has a clear vision on the objectives and has an active involvement in  the project.  The Project director used to attend the monthly meeting conducted by the project .The NGO is taking care of the community consideration. The members of the NGO extended their need based support to the program.. The recruitment of staff and periodic monitoring of the activities was done by the NGO.

II. Organizational Capacity

All the staff position in the project are filled within the time frame given by KSACS except the PEs  .The staff pattern of the project is as follows

| Category of staff | No |
| --- | --- |
| Project manager | 1 |
| Counselor / ANM | 1 |
| M&E | 1 |
| ORW | 2 |
| Total | 5 |

Appointment letters along with the job responsibilities is given by the NGO.

Orientation is given to the newly recruited staff by the NGO and it was documented in the Training Register but the reports of the programme were not reported separately. Systematic filing of the document was not done by the project. All the staff except the ANM and the newly recruited ORW has attended the trainings conducted by KSACS and STRC. Capacity Building of the staff should be improved. Counselling Training should be given to the ANM.

3. Infrastructure of the organization

The project office is located near the hotspot .Infrastructure and spacing is adequate for the project to operate. The drop in of the clients in the DIC is very less.  The OST clients registered are availing services from  the District  Hospital  Muvattupuzha . The drop in of the  of the HRGs in the DIC should be improved through innovative strategies .The clinic room in the DIC is not maintained properly according to NACO guideline since the HRGs are referred to the District Hospital  Muvattupuzha for GMC.

4. Documentation and Reporting according to the SACS protocols..

The TI maintains the reporting format which was prescribed by KSACS.General CMIS, STI CMIS and the Financial Reports are submitted on time. Weekly review meetings and Monthly review meetings were conducted but the planning part should be strengthened. Dissemination and sharing of the reports should also be reflected in the minute’s .Financial Planning should also be included in the meeting. Daily diaries are maintained by the staff which contains only limited information’s. The drop out mentioned in the line list was not reported.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Line listing of HRGs was available in the office. All the HRGs are line listed and updated .Prioritisation of HRGs on risk based is not properly done. Dropouts recorded with separate colour code in the Master Register but it was not reflected in the report.

2. Micro planning in place and the same is reflected in Quality and    documentation.

PLOP tool and B form are in place. The quality of Outreach should be improved through innovative strategies. Documentation system should also be improved. 99.14% of the IDUs were tested for HIV once during the period (2014-2015 ) and 68.57% of the HRGs tested twice during the period (2014-2015 ) . 105.14% of the IDUs were tested for HIV once during the period (2015-2016 ) and None of the HRGs tested twice during the period (2014-2015 )

3. Coverage of target population (sub-group wise):

Target / regular contacts 350/305 HRGs are regularly contacted by the project during the period 2015-2016.

4.Outreach planning – quality, documentation and reflection in implementation

Outreach planning is not based on the risk categorisation. The clarity of planning should be improved. Prioritisation of HRGs should be done.Form B and daily diaries  of  HRGs were verified .

5.PE: HRG ratio,

PE: HRG ratio is not maintained according to the proposal because only 4 PEs are in place due to the financial crises.

6.Regular contacts

Regular contacts are calculated according to the need based services provided by the outreach workers. 87.14% of the HRGs are regularly contacted by the project during the period 2015-2016 .

7. Documentation of the peer education

B form and Daily diaries of the PEs  are prepared by PEs with the help of  Outreach workers.

8. Quality of peer education- messages, skills and reflection in the community

Interacted with 4 PEs and the quality of the PEs should be strengthened by conducting PE trainings on Harm Reduction to scale up the programme. Communication regarding the Harm Reduction should be improved.100% of the PEs comes under the age group above 35yrs.

9. Supervision- mechanism, process, follow-up in action taken etc

Supportive supervision was given to the staff in limited area, it should be done at various levels and in all the areas where there is a need. There are no proper documents which reflect the monitoring mechanism. Capacity building of the Outreach staff should be strengthened by conducting in-house training programme at project level. All the documents are maintained with minimum details .

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

TI project refer the clients to the District Hospital Muvattpuzha .STI screening was done by the OST doctor. 99.42% of the IDUs were screened for VDRL during the period (2014-2015 and only 21% of the IDUs underwent screening twice during the period (2014-2015 ) . Only 10.57 % of the HRGs were screened for VDRL during the period (2015-2016) and none of them were screened twice. Visited the Hospital and interacted with the Doctor.  Verified the slips. STI drugs are available in the project office and it is kept properly .

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Clinic services were not provided at the DIC.STI screening was done by the OST Doctor at District Hospital Muvattpuzha. STI drugs are available and verified the concerned documents.

3..Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

ICTC referrals were accompanied by staff and PEs . 105.14% HRGs has undergone ICTC testing  during the current project period .10.57% HRGs  has undergone VDRL testing &  No HIV positive cases reported in the project and no STI cases were reported during the year .Only 5 HRGs were referred to DOTs.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for STI medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

The project is following the reports and documents according to NACO guideline but only limited information’s The project maintained the Attendance and the leaves of staff  were documented accurately. Clinic forms were available and verified.  Visited the ICTC centre of District Hospital and the referral slips were verified. Medicines were not seen purchased by the project. Verified the STI drug register . The condom stock register and the clinic forms were  well maintained .present and verified the concerned documents. Risk assessment of the HRGs was not reported in the concerned document and it should be improved .

- . Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Social marketing condoms were available in the project office during the time    of verification. Verified the stock register. Only Social marketing condoms were distributed through PEs and ORWs during the period. There are only 67 sexually risky HRGs and the project quarterly calculates the demand of condom. Condom gap analysis was done quarterly.

5 No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

3192 condoms were distributed during the last period ( April 2014– March 2015)  and 3378 condoms were distributed during the period April 2015–January 2016.. Condom distribution was conducted through PEs and also through non traditional outlet. Condom requirement gap analysis done in the project. The project staff reported that the condoms were distributed through PEs and non-traditional outlets.

6. No. of Needles / Syringes distributed through outreach / DIC.

Needles / Syringes were distributed through PEs , ORWs and through non-traditional outlets.17128 syringes and 34064 needles were distributed during the last 10 months    through outreach by PEs , DIC and unmanned outlets . N/S requirement analysis was accurately done quarterly. The HRGs are receiving N/S as per requirement. On verification of the documents there is a mismatch between the stock register and B form.

7.Information on linkages for ICTC, DOT, ART, STI clinics.

The project staff has good linkage with the ICTC counsellor.   All the staff & PEs were aware of ICTC and STI clinic. Needs to strengthen the DOTs referral. The Evaluation Team interacted with the ICTC Counsellor and the Doctor who is conducting the STI screening.

8. Referrals and follow up

Referrals are documented & monitored by the ANM/Counsellor. Colour coded PE tracking present to ensure the follow up services especially ICTC & VDRL. Referral of HRGs to DOTs and VDRL should be strengthened.

V. Community participation

Collectivization activities: Should increase the involvement of HRGs in the committees.

Three community committees were formed and the meetings were conducted monthly and quarterly. Involvement of HRGs should be strengthened and it should be reflected in the planning. Community participation in project activities is very low. No Event were conducted in the project during the current  phase and only and 167 HRGs attended the event during the project period  (April 2014- January 2016)  . Verified the documents concerned with the community participation. CBO formation initiatives taken earlier was not sustained due to many issues. Community participation should also be strengthened.

VI. Linkages .

1.Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

STI screening was done at the OST centre which is situated at District Hospital Muvattupuzha  .Only 37 HRGs has undergone VDRL screening once  during this period  (April 2015- January 2016).  The STI  Centre is located near the OST centre so the project can utilise the govt centre for testing . The lab is accessible to all the HRGs since it is situated in the heart of the town .  ICTC is accessable to the HRGs and it is also adjacent the OST centre . TB clinic is also situated in the same building .

2.Percentages of HRGs tested in ICTC and gap between referred and tested.

105.14 % of the HRGs were tested for ICTC once in a year and none of them were tested twice during the current period. Target is 350 but the project has identified 36 new HRGs and they also has undergone HIV testing .

3. Support system developed with various stakeholders and involvement of various stakeholders in the project.

No Support System  mechanism developed in the project. A crisis Team was functioning during the project period which include an Advocate & Staff of TI to address the issue.

VII. Financial systems and procedures

1.Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

The Solidarity TI followed the guidelines of NACO for the  financial management. Project communicated  the financial matters with KSACS /TSU officials through letters.

2. Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

The Solidarity TI  maintained  the accounts in Tally software . Project used printed vouchers, The project purchased assets after getting the approval from KSACS and NGO. Verified the documents . 3 quotations were received and the project quoted the lowest. Purchase committee minutes was not available in the project for verification. . Bills along with  vouchers were filed in a systematic way . Stock register with issues of the commodities were maintained as per the guide line of KSACS/NACO  .

3.Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

The Project adhered to the  systems and mechanism of procurement as endorsed by SACS/NACO . Medicines were not purchased by the project.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

Separate Bank account maintained , not joint  but the cheques are signed by the Secretary and the Project Director . Bank  reconciliation made on  monthly basis . The audit reports were not received .

VIII. Competency of the project staff

VIII a. Project Manager

- 5 yrs experience in TI

- Educational qualification & Experience of the project is as per norm .

- Received trainings from KSACS & STRC

- Quarterly and monthly plan is in place.

- Regularly conduct review meetings but financial planning is not documented properly.

- Monitoring and field visit conducted but not documented properly.

- Needs to strengthen the supportive supervision with scientific tool.

- Advocacy initiatives initiated but should put effort to canalise bilateral funding .

VIII b ANM

- 10 months experience

- Educational qualification and experience as per the norm.

- Clinic registers & STI counselling registers were maintained properly.

- Needs to improve the clarity on risk assessment and risk reduction,

- Has to strengthen the knowledge on basic counselling and HIV,

- Needs to strengthen the documentation according to NACO guideline.

VIII c. ORW

Interacted with 2 ORWs .One ORW is from the community and he  had attended the Harm Reduction Training of PEs. The second ORW is a newly recruited person with limited knowledge on the IDU programme . Capacity building initiatives should be taken at the NGO level. Planning is based on the B form.Supportive supervision to PEs needs to be strengthened . ORWs needs more clarity regarding the Outreach plans .. Needs to strengthen the documentation especially daily diary.

VIII d. Peer educators in IDU TI

Out of 9 PEs, only 4 PEs are in place. The PEs are  above the age of 30yrs, the number of daily injectors is very less. From the discussion it was clear that the quality of peer education has lot of scope for improvement in the areas of harm reduction practices , STI, condom demo and safe needle disposal . Knowledge was good. Training of PEs needs to be regularized. Young PEs should be recruited for the identification of young daily injectors.

VIII e. M&E officer

- 4 yrs experience in TI

- Educational qualification and experience as per the norm

- Received trainings from KSACS & STRC

- Maintained the financial and the HRG master sheet with the information needed He was able to provide the information’s about the gaps of outreach.

- He was able to provide the information’s about the gaps of services provided.

- Need to strengthen the knowledge on Harm Reduction.

IX. a. Outreach activity in Core TI project

Interact with  PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

Outreach activities are conducted according to the plan. Outreach activities are conducted according to Form B. HRG is included in the planning process. PE: HRG ratio is not maintained according to the proposal because only 4 PEs are in place due to the financial crises. The review team interacted with 4 PEs . The community was found satisfied with the services of TI. From the discussion it was clear that the NSEP was in place, quality of peer education needs to be improved in the areas of harm reduction practices, condom demo and safe needle disposal . Training of PEs need to be regularized. Used needles were disposed through District Hospital Muvattupuzha but the project has no proper documents to prove. VDRL and DOTs referral should be strengthened. Risk reduction counselling should also be improved.

Supportive supervision was given to the staff in limited area, it should be done at various levels and in all the areas where there is a need .Capacity building of the staff should also be strengthened by conducting in-house training programme at project level especially to the newly recruited staff.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- ICTC Visit  in the target area

ICTC is accessible to the HRGs and it is also adjacent the OST centre . TB clinic is also situated in the same building . 105.14 % of the HRGs were tested for ICTC once in a year and none of them were tested twice during the current period. Target is 350 but the project has identified 36 new HRGs and they also has undergone HIV testing. Verified the slips with the ID number and PID number.

- VDRL Lab Visit

The project conducted VDRL screening in a private lab. Due to financial crisis the only 10.57 % HRGs were screened.  The accessibility of the lab in the Government system is very easy since it is in the heart of the town .So the project can utilize the STI centre for further service uptake.

STI screening was done at the OST centre which is situated at District Hospital Muvattupuzha  .Only 37 HRGs has undergone VDRL screening once  during this period  (April 2015- January 2016).  The STI Centre is located near the OST centre so the project can utilize the govt centre for testing . The lab is accessible to all the HRGs since it is situated in the heart of the town.

XI. Community involvement

Three community committees were formed and the meetings were conducted monthly and quarterly. Involvement of HRGs should be strengthened and it should be reflected in the planning. The projects are focussing on targets and achievements rather than streamlining the activities to meet the needs of the HRGs with the limited resources available.

Community participation in project activities is very low. No Event were conducted in the project during the current phase and only and 167 HRGs attended the event during the project period (April 2014- January 2016). Verified the documents concerned with the community participation. Community participation should also be strengthened. Need to increase the involvement of HRGs in the programmes. 43% of the HRGs were involved in the programmes conducted by the project since last 2 years .

XII. Commodities

Planning as per B form. Condom requirement and Needle requirement gap analysis. Condoms and needles distributed according to the requirement.PCU wise condom and needles and syringes calculated and distributed by PEs .

XIII. Enabling environment

Advocacy programs were not conducted in the project but only one –one interactions conducted. There is no proper planning for advocacy in the project due to the Financial Crunch. Community involvement in advocacy is very much limited apart from Staff .

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

No social protection schemes availed by the project.

XV. Best Practices if any

- STI screening done in Government Hospital as a part of sustainability.

- 100% social marketing of condoms among IDUs.