Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

DESH MSM TI  Thrissur.

Background of Project and Organization

Deepam Educational Society for Health (DESH) was registered in 1991as a voluntary, non-profit, non-government organization and the same was registered under Tamil Nadu society registration act (Reg :No 540/1991)and has developed as a versatile organization aimed for developmental activities in multiple sector.

DESH Suraksha MSM TI project has been functioning in Thrissur district since January 2007.Currently the project is contracted to cover 1204 MSMs in four major sites namely Thrissur, Kodungallur, Guruvayoor and Kunnamkulam.

Name and address of the Organization :     DESH MsM Suraksha Project

Kuttankulangara Temple line road,

Poomkunnam P O, Thrissur – 685002.

Chief Functionary:                                            Mr.Rajesh  K R

Year of establishment:                                      1991

Year and month of project initiation:             January , 2007

Evaluation team:                                                 Helvis vazhapully

Laiji Jacob

Time frame                                                          Two days (1/2/2016, 2/2/2016)

Profile of TI

(Information to be captured)

o   Target Population Profile:   MSM

o   Type of Project:  Core

o   Size of Target Group: 1204

o   Sub-Groups and their Size:  Kothi : 736,  DD : 476

o   Target Area : Thrissur, Kodungallur, Guruvayoor and Kunnamkulam.

Key Findings and recommendations on Various Project Components

I Organizational support to the program:

According to DESH, the NGO assigned PD for TI program in Kerala involving in the project activities especially in advocacy, the designated PD himself involving in program monitoring. The team interacted with the project director during the evaluation he explained that all monthly meetings were attended by the assigned project director during the project period. But the documentation of such meetings must be improved. The directions given by the director (other NGO GB representative not attended) also not mentioned properly in the report. The advocacy activity by the NGO found good and visible. Support from NGO by means of scientific programmatic monitoring need to be strengthened.

II Organizational Capacity

Human resources:

The following staff structure has been allotted and the appointment has been done accordingly. The turnover of staff and PE s is visible and lack of ORW in one position/area affected the output of program delivery. The Project Manager was changed once or more in the last two years.

- Project Director-1

- Project Manager-1

- Accountant cum M & E -1

- ANM-1

- ORWs- 4 (5 post allotted)

- Peer Educators – 15 (19 allotted)

As for the perspective of the staff towards the community, it was observed that they are sensitive to the needs and priorities of the community and respectful towards the dynamics of community. The ratio between ORW-PE-HRG is maintained as per the norm. The manager needs to take responsibility in the few areas like, report verification, Review & planning, office administration and documentation.

Project Manager, ORWs and M&E should be trained on program level reporting and documentation. PE s are experienced and committed to the cause, but lack sufficient clarity on risk, vulnerability and concept of the peer led program must be fine tuned.  NGO must take necessary steps to train the entire staff for documentation and role clarity based on NACO guideline.

Capacity building:

The appointed staffs were trained in project level and attended trainings conducted by STRC The role clarity among the core team should be strengthened. The contents and quality of training need to be ensured the quality. The staff who training attended is provided the clarity on respective formats but it is not reflected in their reports/documentation. The Project manager takes overall supervision of entire staff and the ORWs, but few areas like report verification, analysis of performance and the promptness of documentation have to be improved. The role clarity among all staff should be strengthened. The commitment to the project among the PE s found well, the ratio between ORWs and PE s are maintained based on the guideline.   Large turnover in PE s found and it is challenging.

# TI Team needs training on following topics.

- Thematic training on MSM / Risk factors for PE s.

- Training on Qualitative reporting and documentation.

- Specific training for Internal Monitoring and Evaluation

The entire staff team responded that STRC training during the last year not up to the mark or not useful to us.

Infrastructure of the organization

Project office is not close to the hot spot but it is very near to the Railway station and easy access to the community. There is adequate place for program administration and meetings.  The project office has separate rooms for counseling and STI screening, DIC etc. The existing structure permits privacy for community. It has computer and furniture, minimum IEC materials are placed in the Office. In DIC, community can spend their time.

Documentation and Reporting:

Most of the formats are adhered to NACO guidelines. All staffs are maintaining the diaries with very minimum details which are not enough for collecting basic field level information. The supervisory staffs are not verifying any of the reports periodically and the team not able to identify any trace of corrective measure taken by the manager towards the improvement of reports. Most of the registers and formats are not marked as verified by the concerned M&E or Project Manager. No verification and action taken markings are visible in any of the formats or reports. There are mismatches between CMIS and Form B1, Form C and C1.

HRG master register soft copy not updated in last two years so there is no qualitative document for verifying drop-outs. The project should ensure actual dropouts. All the new identification should be reflect in the concerned monthly CMIS. Positive HRG files are in place. In Positive cases follow ups are documented in correct Time.

III.Program Deliverables

# Outreach

# Line listing

# Line list is available with the project but HRG master register is not periodically updated so, details of drop-outs are not properly documented.

# Micro planning

Micro plan as form-B and Weekly outreach plan in place but the same is not reviewed and found incomplete in few respected columns. Project need to put forth effort for proper verification and follow up as an action plan which reflects the quality of implementation.

# Coverage of target population

1204 MSMs were registered against the target of 1192 MSMs and presently working with 1204. TI Reported that 736 Kothis and 476 DDs currently operating in project locations. Among these 24 DD s found high volume category all others are coming under medium or low volume.

# Outreach planning

Outreach plan of the project based on Form-B1, Weekly outreach plan of ORWs and PLOP tools used once in six months. Outreach activity of ORWs was not reviewed on weekly outreach plan format properly but Format –B in place and reviewed periodically. No monthly action plan Prepared by the project Manager or any Staff it must be corrected.

# PE/HRG ratio:

# There are 15 PEs maintaining 19 PCUs but an average ratio of 1:60 MSMs maintained.

# Regular contacts

The understanding of staff team about the concept of regular contact is good. It was documented that 74 % of target group members are regular contact in every month for the purpose of project services but during the review, found that 5 - 10% disparity with the formats and CMIS/ projected figure of TI.

# Documentation of the peer education

Few PEs are doing Format – B independently, others are with the support of ORWs during the weekly PE review meetings. PEs clarity on B format should be strengthened immediately.

# Quality of peer education-

Most of the PEs is articulate the knowledge about the program service is good. However they need clarity on P E work. Few of them are not able to explain risk and vulnerability. They are part of training held at project level, hence they are sentient of unsafe sex, need of condom and lubricants etc, so they distributing condoms based on the demand analysis of the community. The review team could meet 13 PE s during evaluation. Accompanied referrals to ICTC, STI testing are reported by community members during the FGD. The experienced peer educators are found well known by new community members.

# Supervision process

The system of supervision and field support from the project staff/ORWs found good. Apart from monthly review meetings, the weekly review meetings of peer educators also visible but Format –D need improvement or need clarity on Format-D. Meeting with P D is considered as the other supervision process on project implementation. ORW’s field work with PE s documented in the field dairy of ORWs but kept with very minimum details.  The feedback mechanism should be re-structured and documented. The data validation system by M&E was in place but needs improvement.

IV. Services

1.  Availability of STI services - mode of delivery, adequacy to the needs of the community.

The project could establish network clinics with Govt: settings and PPP settings providing STI and RMC services through these clinics.   One government Hospital provides services and the clinics are located near Ground were community gathers but all other clinic facilities are little farther where they HRGs need to travel to access services. The ORWs mentioned that in most of the cases it is done through referrals accompanied by the PEs.  The project team mentioned all new cases are provided PT.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy et.

The ORWs mentioned that in most of the cases it is done through referrals accompanied by the PEs. If the PEs is not accompanying them sometimes the HRGs will not access services.

STI drug (color coded kits) is available in the project office and matching with the stock register, but there are shortages of drugs in few months. According to the project team, whenever someone has STI problem comes and is provided drug is prescribed by the doctor and the drug is provided to the HRG through the ANM.

Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

PT is followed in the project and drugs are provided through the ANM to those who are diagnosed new or with STI. The project reported that they surely meet those who need drugs and provide it to them. All those who are provided STI drugs are followed during the following week or fortnight. The ORWs also keep track of their RMC, ICTC, STI and Syphilis referrals in their tracking sheet.

During these two year period, about 66 new HRGs given PT by the project .

Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

STI CMIS, Clinic register referral slips are maintained for RMC, STI and ICTCs. No separate follow up card is available but the service provision is tracked through their tracking sheet. Every month the color coded list in the tracking sheet is updated based on RMC, ICTC and Syphilis testing. Those who are provided RMC and STI services are entered in the register which is taken from the clinical slips which maintained at the office.

The M & E and ANM updates the registers. STI drugs are provided through the project only. But there are only few kits are available in the project. Verification of the project data indicated that during the period VDRL test given to 649 HRGs.

Availability of Condoms- Type of distribution channel, accessibility, adequacy etc. color coded

Project established 15 SM out lets and 7 free condom outlets so far and stock registers are maintained. Condoms are distributed through outlets and project mechanism that is PEs and ORWs. The HRGs also access condoms from the DIC when they visit the DIC during meetings. Condom depot and social marketing is being done by the project. There is clarity on condom program by project team based on condom gap analysis and they are calculating demand based on the quarterly micro plan.The condom distribution is followed through the PEs and they give according to the demand to each HRG, thereby their reporting indicates same number of condoms being distributed every alternative week. The HRGs met during the field visit and FGD shows that all the participants responded that they are getting enough condoms when they need.

Lubes distributed

The lubes are not distributed along with the condoms by project mechanism currently through PEs and ORWs. The HRGs access lubes from the medical shops. But during interaction with community and PE s revealed that during anal sex condom breakage is common. The flow of lubes along with the condoms is not followed by the project due to lack of fund but it may lead to an unsafe situation. The distribution of lubes was not given priority by SACS. During the FGD, HRGs expressed that they are not getting lube sachet along with the condoms.

No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

According to the data reported by the project, they have distributed 186564 free condoms against 97283 of the demand for the period. And 36205 SM condom against 91927 SM demand. Condoms are distributed through PEs, DIC and ORWs.

Information on linkages for ICTC, DOT, ART, STI clinics.

Project developed linkage with 17- ICTCs, 1 link- ART centers, 11 STI network clinics and providing one static clinic at DIC level for delivering services (Currently not functioning).  ART referral has been done by the ICTC counselor itself for the reactive people but project kept separate follow up system.

Referrals and follows up

Referral system is followed by the project team mostly based on ANM’s documents but the documentation of the RMC, STI and ICTC referral slips verified by the program manager or M & E but no verification marks provided. Quality of verification and corrective measures taken by M & E needs to be strengthened. The follow up of the HRGs for different service delivery is also by tracking sheet that is maintained by the M & E with the help of the ANM.

V. Community participation

Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

The evaluation team observed that there is community collectivization happening in this project. Though the CBO which experienced in working with the HRG community for many years, they have currently initiated few community collectivization process or community strengthening activities, cultural events and celebrations of festivals, X mas.etc. But, still this is one of the areas the NGO/TI needs clarity. KSACS may give the proper direction to the TI s which completed more than five years and initiated CBO.

Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

The HRG community whom the evaluation team met informed about visiting the office/DIC periodically whenever they are called for providing RMC/STI screening and ICTC camps. It is limited to Events and project focus programs. Last year conducted election of CBO but with the help of project staff.  During the usual days, community will meet the project people and access condoms and other services mainly through staffs. But their participation is limited to accessing services, DIC etc. but no part is played by the community/ CBO in strengthening or steering the project activities. The TI should focus and ensure the participation of community from the program planning itself.

VI. Linkages

Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkage with the health services and allied services found and located in different parts of the project area.

Percentages of HRGs tested in ICTC and gap between referred and tested.

During the review it is observed that there is a small gap between referrals and tested about 35 % referrals are not succeeded during the period (1183 tested once 786 tested twice). So the project needs to put forth the effort to make accompanied referrals with the help of concerned peers.

Support system developed with various stakeholders and involvement of various stakeholders in the project.

The stakeholder involvement is visible in the project during the last two years. The evaluation team interacted with other stakeholders but it is limited to advocacy and participation of programs and crisis management. The project conducted about 26 advocacy programs in last 22 months according to the priority list of power analysis. The project team needs to improve secondary stakeholder’s involvement in program planning.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

They are following the guidelines and protocols as per the contract and same thing is reporting to the SACS. This can be witnessed by observing the documents maintain by the NGO.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO,

availability and practice of  using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of  settling of advances before making further payments.

Here also they maintain the rules and regulations as per the agreements. Using printed and machined serialized vouchers. For the purpose of approval they use to send to JD-TI and get approval if required.  In every meetings they kept record of minutes, before purchase of any item they collect three quotations from different agencies. They use to prepare comparative statements   and finally they get the items from the lowest quotations. This has been observed in the documents.  Bills, vouchers, stock and issues registers are kept regularly. In this TI there is no practice of advance payments.

- Systems of  procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

As per the SACS they are following the rules and regulations for procurement system.

- Systems of documentation- Availability of bank accounts (maintained jointly, reconciliation made monthly basis), audit reports

In this NGO- TI the bank account is operating jointly. The reconciliation statement are preparing on monthly basis. The accounts are audited by the chartered accountant and reports are available with TI.

Other Observations:

The sanctioned budget is not releasing as per the agreement. In turn it is affecting the interventions.

VIII. Competency of the project staff

VIII a. Project Manager

Mr.Aneesh Vavachan. MSW holder is working with the NGO as project manager for last 11 months. He started his work on social development sector in last 5 years. The knowledge on project proposal and program components found good so that, there are no gaps in the project implementation process but needs improvement in quality reporting and documentation. He needs to put forth the effort to develop clarity for the project team in certain areas which is like daily diary, quality of minutes, etc. He has good relationship with the team. The methods he used for monitoring the project was field visit is limited to giving oral instructions to the concerned staff and concerned documents and reports also not verified properly. The conceptual clarity for him about the CBO components should be strengthened. The adherence to the project proposal should be improved

ANM

Mr. Arun MM . Bsc. Nurse was working with the project last 4 years. His knowledge on Clinical management and STI counseling is remarkable. all the reports and documents related HRGs found updated. He need to be strengthen the concept on role clarity of each staff team in a TI project.

ORW s

The team observed that only one ORW is from community and having more than four years of experience with the same project. All ORW s have understanding about the targets which they need to be achieved but the clarity on performance indicators found less, preparing micro plans and have clarity about RMC, STI screening, ICTC testing and follow-up needs. ORWs have rapport with the service providers like ICTC and STI centers. But their understanding is limited to providing these services to HRGs. But have clarity regarding crisis management and advocacy needs. During their supervisory field visits they focus on service delivery and distribution of condoms but lack concentration on the quality of their PEs work. Their documentation also needs to improve in order to understand the data flow and also to capture the quality of their supervision visits.

VIII e. Peer educators

Found that all PEs has clarity about the services they has to provide to the community but need to improve their knowledge on community’s risks and vulnerabilities and the importance of providing services periodically to the HRGs including positive HRGs. They provide condoms to the community as per the requirement but the clarity on confidentiality is lacking. PEs takes condoms from ORWs, office and DIC. There is no proper documentation available on the number of condoms given to HRGs in each contact (Field work not reporting to any diary or notes) The number of condom received by the PE s is matching with the ORWs distribution reported in the weekly meeting register. PE s need clarity on micro-planning and hotspot level analysis / priorities and community participation in different community committees.

IX. a. Outreach activity in Core TI project:

The project’s outreach activities focus on providing condoms and bring in HRGs for clinical services and ICTC. The outreach needs to be strengthened as the HRGs were not able to think beyond these services. Similarly the quality of the monitoring that is being provided should be strengthened as now it is just visits by ORWs and PM but there is no quality community feedback documented during those visits. Overall service uptake found good as an MSM project. HRGs tested syphilis found 1070 at least once in a year and all new HRGs managed with PT is a good indicator.

XI. Community involvement

Discussion with the community revealed that they are involved in all CBO activities. CBO needs to consider them in the planning level/development of new strategies. The PEs is found to be implementing the project activities along with the community. The project needs ensure the CBO improvement by the involvement of community members and other stakeholders to run the CBO independently with the programs.

XII. Commodities: Hotspot / project level planning for condoms, Method of demand calculation, Female condom program if any,

The condoms available to the community and is through outlets, ORWs and through PEs. The project also needs to provide condoms through unconventional condom outlets. The PEs and ORWs found realistic on condom distribution by doing condom gap analysis to find out the exact number of condoms that needs to be provided to the HRGs. There are shortages of Lubes and STI drugs kits due to lack of fund.

Community members articulated that it is risk in anal sex without lubes.

XIII. Enabling environment

Currently project was socially placed with the strength of the NGO only CBO not grown as it desires.  It is observed that, in last few years, both NGO and CBO taking effort for building advocacy in new area especially where HRGs hangouts. About 26 advocacy programs were conducted by project but involvement of community members are minimum. CBO’s involvement in Events and festivals/ gatherings is visible and involvement in such cases found good. The major events in last two years are:

- Tharangam – Annual get together

- Vdhyadeepam-Educational support program

- Thumbapoo- Onam celebrations

- Pulkoodu- X mas program

The project should put forth the effort to improve their CBOs effort in independent advocacy and networking programs.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

No such ongoing schemes initiated by project but few supports provided to community by project staff for getting the welfare schemes. And the social support to community is visible during the visit.

XV. Best Practices if any

Nil

End report .