Annexure: B

Reporting Format-B

LAS MSM  Project- Kollam

Background of Project and Organization

Love Land Arts Society (LAS) is a Community Based Organization (CBO) formed by the MSM Community of Kollam District and registered under Travancore Cochin Literacy Scientific and Charitable Societies Act, Act XII of 1955. The goal of the organization is to reduce the vulnerability of the MSM community in the district by mainstreaming them with the general community. It is formed in the year 2003 by the help of the NGO “KASWWA” ), that identified and implemented TI project in Kollam district since 1999. Since December 2006 onwards the CBO has been involving in the implementation of suraksha project among the person who are practicing MSM activity to reduce their risk of getting HIV/AIDS and other type of Sexually Transmitted Infections (STI) due to the absence of safe sex practices. Currently the CBO is running TG project at Kollam. The CBO had implemented PEHCHAN project during 2012-1015.LAS implements MSM intervention in Kollam District covering the micro site areas of Oachira, Karunagappally, Chavara, Kollam, Kundara, Kottarakkara and Chathannur.

Name and address of the Organization 	: LOVELAND ARTS SOCIETY

Opposite KendriyaVidhylaya , Kollam-12

Chief Functionary				: Sri. Anu Stephen, President

Mob :9526272491

Year of establishment 			: 2004

Year and month of project initiation	: Dec 2006

Evaluation team 			: (1)Sathikumari.P

(2) Aneesh

Time frame 				:4th and 5th of February 2016.

Profile of TI

Target Population Profile			: MSM

Type of Project: 				: Core

Size Target Group(s) of

Target based on their proposal 2014-2016 is 1200. Now the registered population is 1215including 74 new identification and 59 dropouts.

Sub-Groups and their Size 		: Kothi - 944

DD	- 271

Target Area 	:

The project covering the following sites

1.Kollam

2.Karunagapally

3. Chavara

4. Kottarakkara

5.Kottiyam

Key Findings and recommendations on Various Project Components

Organizational support to the programme

The TI is a CBO run program and the president is involved in the program on a full time basis as a project director.  Project Director has attended 6 meetings out of 10 monthly meetings of the project and also as and when required,but the leadership is not commendable. The president and the secretary were available for discussion and the involvement of the CBO executives in project is minimum and they assigned the project manager for overall management of the SURAKSHA project.  In advocacy part the CBO has need based involvement.

- Organizational Capacity

  - Human resources:

As per TI staff allocation, all the staffs are put in place in the project. Appointment letter with job description are given to the staff, but the authority signed is by M&E ,not the project director. Also there is discrepancy in actual joining date and date shown in the appointment letter. The ratio between ORW-HRG is maintained as per the norm but PE - HRG ratio maintained is according to the norm.The attendance register was found in place and leave file maintained and majority of the leave letters are there.  It was observed that the Field staff was maintaining daily movement register and dairies. The project consists of Project Manager, accountant cum M&E,1 ANM and 5 ORWs.

  - Capacity building

Training registers of the staff are maintained in the office however there is no training report of the staff maintained.  During the interaction with PEs it also observed that only input sessions  is given during the weekly meeting and no separate training  given to the PEs.Lack of systematic in-house trainings and lack of input sessions reflects on the  performance of the project and the team need more conceptual clarity in project components.

3.Infrastructure of the organization:

Visibility and access of the project office is good.All assets codified should be entered in the asset register. Assets of the CBO and the project should be recorded and maintained separately.Office  should be pasted with IEC materials, concepts/definitions and updated indicators.

4.Documentation and Reporting:

Most of the formats are adhered to NACO guidelines.Master register is not available in the project.There are mismatches between Form B, Form C and form c1. Supervisory staffs are signing the documents but there is no crosschecking of documents and action taken reports. Quality of the document and reporting system is not commendable. SIMS and financial reports which are supposed to be sent to SACS/NACO are done regularly and timely. Service tracking sheet insisted by TSU is available in the project. Mismatches in the analysis of available data like profiling of MSMs, coverage and service uptake.

Program Deliverables Outreach

Line listing of the HRG by category.

HRG Master register adhered by NACO is not available in the project. The project is maintaining a line listing of the HRGs in another format.

Micro / Outreach and project planning

PCU wise micro plans have been done by the ORWs and the documents are maintained. The project prepares PLOP in quarterly basis and form B is used for micro planning but prioritisation for service delivery is not based on risk and vulnerability.

Coverage of target population

1200 HRG population is there with the project. There were 59 dropouts and 74 new identifications. Hence the HRGs covered is 1215. Out of this, 271 are in the DD category and 944 are in Kothi category.

PE/HRG ratio:

There are 15 PEs maintaining a ratio of 1:80 on an average.According to the project this ratio is based on the instruction from KSACS.

Regular contacts

The project document shows 99% regular contact and cross verification with services reveals that are not genuine. According to the PEs the regular contact is 70-80% of the total registered HRGs.

Documentation of Peer Education:

The PEs are maintaining Form-B with the support of ORWs. Some of the PEs also found to be maintaining the PE diaries. From the meeting of PEs it is observed that majority of the PEs were unable to explain risk and vulnerability.

Quality of Peer Education:

Most of the PEs are experienced, vocal and they have clarity on project activities.They are successful in establishing rapport with the stakeholders.They seems to be very much confident in responding to the questions about their work and about the programme. Majority of the PEs were unable to explain prioritization based on risk and vulnerability.

Supervision:

The project has a system of monitoring the activities through monthly and weekly meetings apart from this there are regular field visits done by supervisory staff to monitor the outreach activities. Project Manager visits field regularly, however there is no cross verification of services with the service providers. All the documents are verified by the PM, but there is no action taken reports. The ORW also conduct meetings with PEs and every week to understand the services provided by the project. ORW’s field work with PEs is documented in the form –D. The feedback mechanism should be documented in all level and it may be used to develop field level strategies for better output. The data validation system at M&E level is lacking and cross verification system should be placed.

Services

STI services

- Availability of STI services:

No static clinic and PPPs function in the project area. The project refers HRGs to the Govt healthcare system for STI services.

The project referred 100% of HRGs for STI screening. Cross verification reveals that the number projected for STI screening are not genuine. OP tickets taken for STI screening has manipulated.

- Quality of the services-

Confidentiality and privacy lacks in STI clinics for physical examination due the rush in the Govt system. One Counselor is working in the project for coordinating clinic level activities. Referral for syphilis screening is also with the govt system.

- Quality of treatment in the service provisioning:

Trained doctors are available for services. Syndromic treatment protocol is adhered to. Referrals to HIV screening and syphilis screening are done.

4. Documentation:

Majority of necessary documentation as per NACO guidelines regarding the service provisions and service uptake is available. The project has given PT to newly identified HRGs, but medicine distribution register is not available in the project. There is no reported STI cases in the phase.

ICTC services

They are referring HRGs to different ICTCs in their area. Cross verification of ICTC documents and project documents shows evident mismatches. Most of the referral slips cross verified are not genuine. ICTC staff complained that, some of the PEs wasting the testing kit of both VDRL and HIV by repeating the same HRG in ICTC and Sneha situated in the same premises and there is shortage of testing kit.

Condom

76% of demand is distributed as free and only 2% by social marketing. Focus is given to provide free condoms. PEs, ORWs and other condom outlets are the major distribution channels.

Financial systems and procedures:

- Systems of Planning:

The systems and procedures are going through as per financial manual of KSACS.

- Systems of Payments:

The cash payments more than 5000 were settled by cheques. Vouchers are printed, serially machine numbered and signed by accountant, project Manager and project director. File Registers are all separately maintained. Each payment is made as per the budget. Monthly expenditure statements are sent to KSACS through the submission of SOEs from the project on time. Vouchers are properly kept in the box file. It was observed that more than 3 times they have kept more than Rs. 5000 as cash in hand.

- Systems of procurement :

The NGO has its own procurement system. Project not purchased any assets during theyear.

- Systems of documentation :

Cash book maintained in daily basis. Bank account is jointly operated by 3 executive members of the CBO. Bank reconciliation made on monthly basis and SOEs are submitting in time.

Competency of project staff

  - Project Manager

Project manager is experienced and has more than 7years of work experience in the same TI. PM has good attitude and gets acceptance among the community as he is from the community.  He has an ability to control the PEs, ORWs and other staffs arevery much appreciable. He is doing enough field visits as part of supportive supervision and having a good rapport with the community. Besides that, PM should visit the service centers and cross verify the service uptake of HRGs. PM should cross verify all the project related documents and should give feedback and action taken reports to the project staff.

  - Accountant cum M&E

Accountant cum M&E has one year experience in project and she is basically an accountant. She has good communication with other team members and have good positive attitude. She is good in finance related works in the project and properly maintaining Service register/colourcoded line list. She needs more orientation in Monitoring & Evaluation part. Cross verification of documents should be improved.

  - Counselor and ANM

Counsellor has joined the TI before five months but have more than one year experience in the project who is also known the duty of ANM. Clarity on risk and vulnerability must be improved. Maintenance of clinical records also need improvement.It feels like his involvement in the project is marginal.

  - ORWs

All the five ORWs are having 8 years’ experience in the TI and out of five, four are from community. Field presence of them are good and have fine rapport with their PEs & HRGs. They are actively participating in crisis management & project advocacy. During the interaction with ORWs, they are not able to explain the risk and vulnerability. Documentation on various formats and reports must be improved. ORWs need more trainings to build clarity on concepts.

- Peer educators

The project has cut short the number of PEs from 20 to 15 in October 2015 as per the direction of KSACS to reduce the expenditure. Most of the PEs do not have knowledge about how to fill B form.  PEs needed periodic training about project components and on B form preparation. Importance of ICTC testing, STI testing, knowledge about condom are good but needs improvement in assessing risk& vulnerability and knowledge on STIs.

Community participation

The project is a CBO led intervention. SHGs formed earlier are not live currently. The members of the CBO are 44% and efforts in strengthening the process of collectivization need improvement.During this year they have conducted one event and the participation is only 13% including the participation from the HRGs of other projects. This indicates that there is a gap in the collectivization activities of the project in spite of the fact that the project is CBO led. According to the PD there are community consultation meetings, but there is no supporting document.

There are community committees for DIC, STI, condomand ICTC.  There is also a crisis management committee for tackling the issues of HRGs.

Enabling Environment

There is a repot of power analysis and a plan for advocacy, but only need based advocacy meetings conducted. Current year project has conducted advocacy meetings with Police, ICTC, PRIs. The project seems to have need based involvement with various stakeholders, but there is no proper follow up. Crisis committee has formed and the issues are addressed by the committee. During the year 2 crisis are handled by the project

The project is having a referral system for HIV test, syphilis screening and STI screening.The need for the linkage and support system development is not perceived properly and thus efforts taken in this regard are not appreciated.

Best Practices if any

Not found during the review period