Reporting Format-B

Malabar Cultural Forum Suraksha (MSM) Target Intervention Project, Ponnani,Malappuram,Kerala.

Introduction

Background of Project and Organisation:

Malabar Cultural Forum is a Community Based Organization of MSM (Men having sex with Men), registered under the Societies registration Act 1860 in the year 2005. MCF with it’s headquarter in Kozhikode, is operating mainly in Kozhikode, and Malappuram Districts. MCF started implementing targeted intervention in Kozhikode and Waynadu districts in the year 2006. In the year 2009, MCF started implementing its second Targeted intervention Project in Malappuram district. The target area covers 7 sites and 18 spots with a population of 1069 as target in the project proposal, but now the TI have an active population of 1021 HRGs. The major sites of TI are Thirur, Ponnani, Thanur, Parappanangadi, Kuttipuram, Edappal & Valancherry.

Name and address of the Organization  :  Malabar Cultural Forum(MCF) Suraksha Project.16/783, 2nd Floor, KT Apartment, High School Road, Kuttipuram

Chief Functionary:               Mr.C.K.Nasar

Year of establishment     : 2005

Year and month of project initiation:  2009

Evaluation team  :         Mr.Aravind S Panicker (Team Leader)

Mr.Akhil P. (Co Evaluator)

Mr. Prajeesh (KSACS Observer)

Time frame :          2 days ( 12-2-2016 to 13-2-2016)

Profile of TI

Target Population Profile: MSM -1069   (1021- Current Population)

Type of Project:                       Core

Size of Target Group(s)           1021- available HRGs

Sub-Groups and their Size               DD-753

Kothi -268

Target Area

| SITE | SPOT | POPULATION |
| --- | --- | --- |
| Thirur | Thirur Old Bus stand | 64 |
|  | Rajana Bar(City Junction) | 64 |
|  | Thirur Railway | 67 |
|  | Foreign Market | 66 |
| Ponnani | Pallapuram | 59 |
|  | Chanaroad | 60 |
|  | CV Junction | 62 |
|  | Ponnani Bus stand | 75 |
| Thanur | Thanur Railway | 59 |
|  | Kalad | 57 |
|  | Ozam Beach | 60 |
|  | Vattathani | 59 |
| Parappanangadi | Parappanangadi Railway | 19 |
| Kuttipuram | Kuttipuram Railway | 64 |
|  | Bus stand | 50 |
|  | Nila Park | 15 |
| Edappal | Edappal Junction | 61 |
| Valancherry | Valancherry Bus stand | 60 |
| Total Population |  | 1021 |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Calicut based Community Based Organization is implemented the Project. The project director is keen in monitoring the TI, since the CBO is from Calicut other GB members could not able to address the need of the community.

The TI has a good rapport with PRI officials, Police, KSACS service centers and the project is not facing any obstacles from the field. In the future years the CBO must focus the development of community leaders from malappuram area. The community leaders of the CBO can give more support & guidance for the TI to achieve its best in the TI implementation.

- Organizational Capacity

  - Human resources & Capacity building:

Presently M&E officer is the Project Manager in charge and counselor is 11 month experienced in the TI. Both the staff needs training in program monitoring and documentation. ORWs are experienced in the TI and well trained. Out of 4 ORWs three are form the community.

  - Infrastructure of the Organization:

The project main office is functioning at Kuttipuram, it is using as DIC for the HRGs. Another DIC is working at Tirur. Now the static clinic is not functional due to the lack of fund. MCF CBO office is operating at Calicut.

  - Documentation and Reporting:

Most of the formats are not available in the year 2014 -15.  In the year 2015 -16 counseling registers are updated. STI referral registers are partially filled. B, C, C1 form is keeping by the ORWs and D form is not maintained. OP tickets are the support for the RMC. Advocacy, crisis, commodity registers are maintained by the TI. SIMS details are not available in the TI. The quality of staff planning document and field diary should be increased.

III. Program Deliverables

Outreach

- Individual HRG Tracking by the Peer Educators

As per the proposal the TI have 17 Peer Educators. Presently 12 Peer educators are involved in the project activities. In the evaluation process interview was held with 9 Peer Educators. All of them have more than one year experience in the TI. PEs are well aware and trained about the symptoms of STI, meaning of HIV/AIDS and TI services. In the field activity PEs couldnot explain the process of condom distribution, condom requirement analysis. Peer Educators have an idea about the headings in the form B, but they are not able to tell the risk pattern and condom usage of HRGs. PE s don’t have field diary to note the field activity. PEs don’t have an idea about the service prioritization and service requirement of HRGs. ORW is filling the form B, the TI couldnot explain the process of data from field to the form B.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Even experienced & educated PEs are not able to fill form B | Motivate & Train the PE to fill the form B |
| 2 | No field diary for PE | Daily field activity must be noted by the PE. Condom distribution, condom requirement analysis, one to one contact etc. |
| 3 | PEs are not able to explain the field dynamics. | ORWs should monitor and motivate the PE to do the best. |
| 4 | Line list and service due list is not seen with the PE. | Line list and service due list should be noted in PE diary. |

- Micro planning:

A specific plan is not found in the TI, a vast plan called monthly plan is used as the planning document. In the plan of ORW it is noted that the field work everywhere. In the field work column where, when and how is not mentioned. The plan of counselor mentioned counseling only. The need and priority of the counseling should be included in the plan as well as in the PM plan is also not specific. Peer Educators does not have a plan and the in the PE meetings there is no planning discussions were noted. As per the colour coded tracking sheet M&E is given due list to ORWs and the filled referrals handing over to PEs.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Staff don’t have individual specific plan. | According to the roles & responsibility each staff should make a specific plan. |
| 2 | PEs are not involved in the planning. | PE meetings can be a platform to collect the PE feedback and can involve PEs in the planning. |

- Registration,Coverage & Regular Contact

As per the proposal the Project has 1069 HRGs and now project is having 1021 active HRGs in the field. Among them 268 are Kothis and 753 are DDs. The TI could identify 20 New HRGs in the last year and the number of drop outs is 68. The drop out details of HRGs in the TI are not properly documented by the TI. The registered 100% of the HRGs identified and needs to update the master register. More than 90% of the HRGs are covered by the and more than 80% of the HRGs contacted regularly by the TI but the percentage of VDRL, ICTC testing is low and the quality of STI check up is a concern.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Master Register is not updated. | Update the master register, keep a base document and and update the data periodically. TI can measure the impact of BCC through this updation. |
| 2 | Huge drop out have occurred in the TI but the TI could not documented the process. | Document the drop out process |
| 3 | High percentage of coverage | Free condom distribution percentage is high so strictly monitor the free condom distribution. |
| 4 | Even high percentage of regular contact noted but the HRGs availability in the field is not found. | Ensure the quality of field work of ORWs and PEs by PM, M&E. |

- ORW field monitoring :

As per the proposal the ORW has to visit his all PEs in a week. In the TI the ORWs could visit all the PEs once in two weeks. The field monitoring and review details not documented in the field diary. ORWs didn’t maintain form D.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | ORW field monitoring is not equally distributed to all spots. | PM & M&E ensure the quality of ORW field monitoring. |
| 2 | Form D is not maintained by the ORWs | ORW should keep form D |
| 3 | Field monitoring details not recorded in the field diary | PE monitoring details and field dynamics should be noted in the daily diary. |

- PE: HRG ratio:

Out of sanctioned 17 Peer educators 12 are working now. PE - HRG ratio is 60 as per the sanctioned PE s number but 5 PE posts are vacant and the TI could not fill the vacancy due to the shortage of fund. Present PE HRG ratio is 1: 85

- Quality of peer education- messages, skills and reflection in the community

The evaluation team could meet 9 peer educators and it was observed that all of them are having good communication skills and they are well aware of the basic knowledge about HIV/AIDS/STI, use of condom etc. Out of 12 PEs 9 are under the age of 30. Evaluation couldn’t get the opportunity to assess the knowledge of the community because only 5 HRGs were interacted in the field.

- Supervision- mechanism

Presently M&E officer is the in charge of PM. PM post is vacant in the last 3 months. M&E and counselor is doing the supervision. The supervision of the CBO is weak because the CBO is situated in Calicut and most of the GB members from Calicut. The monitoring of ORWs must be strengthened by the TI.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | ORW monitoring by the PM/M&E has to be strengthened. | Make a specific plan for field monitoring. |
| 2 | CBO monitoring is weak. | CBO should appoint one regular person from Malappuram area to guide the TI. |

IV. Services

- Availability of STI services and quality of services

Due to unavailability of fund the PPP system is not working now. Purely the TI has to take services from Government settings. There is no privacy for physical checkups in the Govt hospitals. The quality of STI check up found less in the TI. OP tickets were taken by the staff filled and documented as the support of RMC. Doctors were not signed in the most of the tickets. Referral register partially filled from October 2015. The 2014 -15 documents are not available in the TI. 14 new HRGs were Presumptive Treatment in the last year out of 20 HRGs identified. The VDRL kits are available in the Government hospitals but the testing is low. 5 STIs have identified in the last year by the TI.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Quality of STI testing is a concern. | PM and counselor should take care of the quality of STI screening. Try to conduct advocacy meetings with doctors & DMO. |
| 2 | VDRL testing in Government clinics are less. | ORW can make the due list of HRGs and share it with PEs. The testing facility details must be reached to the HRGs. |

- Quality of treatment in the service provisioning-.

In the last year TI could identify 5 symptomatic cases. And the follow up & partner testing is not done and 14 out of 20 new HRGs were received STI kits in the year 2015 -16 but in the year 2014 -15 only 15 members were received PT out of 51 new HRGs. One reactive cases identified in VDRL but no partner testing done in that case. Positive HRG follow up is not ensured by the TI.

- Documentation-

Net work clinic card is not maintained by the TI since the HRG is testing in the Government clinics. Referral register partially filled from October 2015. Before that the referral registers not maintained by   the TI. The details of testing are entered in the colour coded tracking sheet for the year 2015 -16. Updated colour coded is not available for 2014 -15. Kit registers were updated. The number of service uptake has difference in ORW data, project registers & colour coded sheet.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Project is distributing condoms through direct and out lets. Project having 19 outlets in the 7 sites. The evaluation team could not visit any one outlet. Condoms distributed through the outlets are not documented. Peer educators are not recording the field level condom distribution. Form B is the only document for condom distribution and condom requirement analysis. PE s and HRGs interacted reported that they are received enough condoms. Social marketing condoms are less in the TI. Revolving fund system is followed by the TI. Cash is taken back from the PE TA.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Condom distribution channel is not recorded properly. | PE s can note the condom distribution in their field diary. |
| 2 | CSM condom movement is less and revolving system is not followed | Study the needs of CSM or type of condoms used by the MSMs and the client condom bringing behavior. |
| 3 | Condom movement through the outlets was not calculated. | ORWs or PE can record the outlet condom movement. |

- No. of condoms distributed-

The review team observed that free and social marketing condoms distributed against demand. A total of 121564 free condoms were distributed in the year 2014 -2015 the requirement was 133764. In the register number of condoms distributed in the year 2014 -15 was 113267 (84%) of the requirement. In the same year TI reported that they could distribute 5906 CSM condoms but in the register that is only 360(1% of the demand). In the year 2015 -2016 free condom distribution was 66598 against the demand 97638. In the register the number is 71854(73.5% of the requirement).  In the last year TI reported that they could distribute 3621 CSM condoms but in the register that is 12310(50% of the demand). Mismatch is observed with condom distribution and documentation.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Mismatch found between condom distribution reports with condom distribution register. | PM & ME should clear the condom distribution in each month. |
| 2 | HRGs actual condom demand is not matched with the condom requirement data in form B. | Condom requirement analysis should be done by PE with consult with all HRGs. |

Information on linkages for ICTC, DOT, ART, STI clinics.

HRGs are well aware about the service locations of the TI. PE s remarked the attitude problem of ICTC counselor at Tirur. After the interaction with the counselor in the Tirur ICTC center it is clear that he is having knowledge about HRG group and he is eliminating all the chances of duplication and manipulation in the testing. Even the ICTC testing centers are available at Ponnani and lots of the testings were done in ICTC pattampi, perinthalamanna, Malappuram, Trichur, Tirurangadi & Vadakkancherry. Mismatches have noted in the Ponnani & Tirur referral slips. The counselors are these centers are strict in the quality of testing.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Difference of the names in ICTC register and referral slips. | Counselor & M&E should cross check the testing details. PM must be cross check the testing details with ICTC staff. |
| 2 | Line list is not shared with ICTC centre | Sharing of TI line list may minimize the chance of duplicate testing. |
| 3 | ICTC testing in other districts | PM & M&E should cross check the ICTC testing in the other districts. |

V. Community participation

Collectivization activities:

791 members from the TI are registered in the CBO but 400 members are paying the monthly fees. All the documents kept at the CBO office Calicut. Community committees are not active and new HRGs were not involved in the committee activities. 92 HRGs participated in one community event held here at Tirur. TI is stated that nearly 400 members were participated in Orukkam conducted by MCF calicut. Support document is not available with the TI.

VI. Linkages

TI stated that they have good rapport with the service outlets of KSACS, Health & PRI officials and Police. TI could not arrange stakeholder meeting for the evaluation.

VII. Financial systems and procedures

| Findings | Recommendations |
| --- | --- |
| 1.System of Planning: Expenses as per the budget guidelines of KSACS. TI could utilize the 99% of the released amount. | Nil |
| 2.Systems of payments: a) Vouchers and bills are properly maintained by the TI. No cash transaction above 2000,No cash balance above Rs : 5000 and the proper approval obtained from PD. b) CSM register not kept properly. c) Fixed Assets have not been purchased during the period. | Revolving fund system should be ensured by the TI. |
| 3.Systems of Procurement: a) No procurement in the contract period. | Nil |
| 4.Systems of Documentation: - Bank statements for both the period are available for verification. Month wise Reconciliation has been done and signed by the Project Manager, Director and Accountant. - Statement of Expenditures submitted in Time. |  |

VIII. Competency of the project staff

VIII a. Project Manager

M&E officer is the Project manager in charge for last 3 months and he has          more than 1 year experience in the TI. Project manager in charge is competent and monitoring and documenting the TI activities is good. The documentation and the supervision in the year 2014 – 2015 by the PM in that period could have been done better. The documents are not available with the TI including colour coded tracking sheet and registers. PM need more training in Program planning and monitoring.

VIII b. ANM/Counsellor

Present Counselor has 11 month experience in the TI. He has good rapport with the HRGs in the TI. Technically he needs training in planning and documentation of counseling. Counselor need to focus in the positive HRG follow up.  2014 -15 counseling documents are not available in the TI. One positive HRG was dropped out from the TI in the contract period. Present Positive HRGs CD4 details is not available in the TI even the HRG is regularly visiting the DIC.

VIII c. ORW

Out of 4 Out Reach Workers 3 ORWs are from community. All the ORWs are well experienced & trained in the TI. ORWs need to give more focus in field activities especially the monitoring of PEs. ORWs are not fully utilizing the ability of active PEs. ORW should motivate the PEs to mobilize the HRGs. The planning and documentation is not proper by the ORWs. In the evaluation process even the community ORWs could not arrange the HRGs for meeting.

VIII d. Peer educators

Interacted with 9 PEs out of 12 PEs working. They are well aware about the project services and HIV/AIDS & STI. TI need to involve PEs in program planning and documentation. Some of the PEs not tested for HIV, VDRL & STI in the last year.

IX. Outreach activity in Core TI project

Outreach activity should be strengthened by the TI. HRGs are available in the project area but the TI could not mobilize the HRGs into the project services. PM should motivate the ORWs to monitor and guide the PEs to mobilize HRGs. Specific planning and documentation must be essential to strengthen the TI.

X. Services

The quality of condom distribution, STI, ICTC, VDRL checkups should be ensured by the TI.

XI. Community involvement

Community committees and the involvement of HRGs in the program planning needs to be strengthened. CBO must review the project activities and involve more MSMs in the CBO activities from the project area. Crisis were reported from the HRG level is not documented & solved by the TI.

XII. Commodities

CSM condom was unavailable for the TI in three months. Even lube was available in the TI they could not distribute it properly. Lube distribution was not documented properly. Mismatch found between register and balance available.

XIII. Enabling environment

Advocacy meetings were conducted without a proper plan. Some of the advocacy was aimed to improve the service delivery eg.with VDRL lab but the follow up meetings were not done by the TI. There is no dermatologist in the Taluq hospital Tiur but the TI is not done any advocacy to fill the post.

XVI. Best Practices:

TI Claims that they have formed one whats app group for facilitating fast communication. But the TI could not lead it into the maximum service delivery and HRG mobilization.