Reporting Format-B

SWANTHANAM MSM TI, ERNAKULAM

Introduction

Background of Project and Organisation:

Swanthanam is a Community Based Organization of MSM (Men having sex with Men), registered under the Societies registration Act 1860 in the year 2006. Swanthanam with it’s headquarter at Pandalam is operating mainly in Pathanamthitta and Ernakulam Districts. Swanthanam started implementing targeted intervention in Ernakulam districts in the year 2012. The target area covers 5 sites and 11 spots with a population of 820 as target in the project proposal, but now the TI have an active population of 878 HRGs. The major sites of TI are Ernakulam, Thodupuzha & Cochin Corporation.

Name and address of the Organization:  Swanthanam Suraksha MSM Project.House No 34A, shenoy road, Kaloor, Cochin 17

Chief Functionary:               Mr.Ajil Thankappan

Year of establishment     : 2006

Year and month of project initiation:  2012

Evaluation team  :         Mr.Aravind S Panicker (Team Leader)

Mrs.Resana Suresh (Co Evaluator)

Mr. Rony ( KSACS Observer)

Time frame :          2 days ( 04-2-2016 to 05-2-2016)

Profile of TI

Target Population Profile: MSM -820   (878- Current Population)

Type of Project:                       Core

Size of Target Group(s)           878- available HRGs

Sub-Groups and their Size               DD-251

Kothi -627

Target Area

| SITES | SPOT |
| --- | --- |
| Ernakulam & Cochin corporation | Fort Kochi |
|  | Thoppumpadi |
|  | South |
|  | Vytila |
|  | Subhash Park |
|  | Marine drive |
|  | Aluva |
|  | Vypin |
| Thodupuzha | Perumbavoor |
|  | Muvattupuzha |
|  | Thodupuzha |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Pathanamthitta (Pandalam) based Community Based Organization is implementing the Project. The project director is involved in the monthly meetings conducted by the TI. Most of the GB members are from Pathanamthitta area so the focus of the CBO concentrated at Pandalam.

The TI has a good rapport with PRI officials, Police, KSACS service centers and crisis have occurred in the last year. The community project staff is dealing and solving the most of the crisis. In the future years the CBO must focus the development of community leaders from Ernakulam area. The community leaders of the CBO can give more support & guidance for the TI to achieve its best in the TI implementation.

- Organizational Capacity

  - Human resources & Capacity building:

Project Manager & counselor have more than one year experience in the TI. M&E cum accountant have more than 4 years experience in the TI and he is the core person ensured the quality of the TI services. Presently one ORW worker is working in the TI and he is from community. ORW has has more than 3 years of experience in the same TI. Two ORW posts are vacant and TI could not fill the vacancy due to shortage of funds. PM & Counselor need training about Project management and need based counseling. CBO leaders can handhold the TI to achieve 100% quality in the TI components.

  - Infrastructure of the Organization:

The project main office is functioning at Kaloor, it is using as DIC for the HRGs. Now the static clinic is not functional due to the lack of fund. Swanthanam CBO office is operating at Pandalam.

  - Documentation and Reporting:

Documents are maintained in the year 2015 -16 but in the year 2014 -15 counseling register, STI referral registers, Form B, C, C1 and D are not updated. Colour coded tracking sheet is not maintained in the year 2014 -15. In the year 2015 -16 TSU is supported the TI with an elaborated colour coded sheet used by the TI.  M&E officer is keen in the updating the documents. STI service registers are also available in the TI. Positive HRG tracking and file documented nicely by the TI. Relieved ORWs documents are not updated.

III. Program Deliverables

Outreach

- Individual HRG Tracking by the Peer Educators

As per the proposal the TI have 11 Peer Educators. Presently 11 Peer educators are involved in the project activities. In the evaluation process interview was held with 6 Peer Educators. Mostof them have more than four years experience in the TI. PEs are well aware and trained about the symptoms of STI, meaning of HIV/AIDS and TI services. PEs are not aware about the concept of CBO and its aim and activities. In the field activity PEs could not explain the process of condom distribution, condom requirement analysis. Peer Educators are not familiar with form B. PE s don’t have field diary to note the field activity. PEs don’t have an idea about the service prioritization and service requirement of HRGs. ORW is filling the form B, and M&E officer is giving priority list to the PEs.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | PEs are not familiar with form B | Motivate & Train the PE to fill the form B |
| 2 | No field diary for PE | Daily field activity must be noted by the PE. Condom distribution, condom requirement analysis, one to one contact etc. |
| 3 | PEs are aware about the HRG crisis. | The crisis and needs of HRGs should document in the TI. |
| 4 | Line list and service due list is not seen with the PE. | Line list and service due list should be noted in PE diary. |

- Micro planning:

A specific plan is not found in the TI, a vast plan called monthly plan is used as the planning document. In the plan of ORW it is noted that the field work everywhere. In the field work column where, when and how is not mentioned. The plan of counselor mentioned counseling only. The need and priority of the counseling should be included in the plan as well as the PM plan is also not specific. Peer Educators does not have a plan and the in the PE meetings there is no planning discussions were noted. As per the colour coded tracking sheet M&E is given due list to ORWs and the filled referrals handing over to PEs.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Staff don’t have individual specific plan. | According to the roles & responsibility each staff should make a specific plan. |
| 2 | PEs are not involved in the planning. | PE meetings can be a platform to collect the PE feedback and can involve PEs in the planning. |

- Registration,Coverage & Regular Contact

As per the proposal the Project has 820 HRGs and now project is having 878 active HRGs in the field. Among them 627 are Kothis and 251 are DDs. The TI could identify 72 New HRGs in the last year and the number of drop outs is 14. To ensure the quality of outreach the TI cut down the HRGs number with the help of HRGs and PEs. But the TI didn’t document the process. If the TI document the process it could have been a model. The registered 100% of the HRGs identified and needs to update the master register. More than 80% of the HRGs are covered by the and more than 70% of the HRGs contacted regularly by the TI but the percentage of VDRL, ICTC testing is low and the quality of STI check up is a concern.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Master Register is updated. | Keep a base document and and update the data periodically. TI can measure the impact of BCC through this updation. |
| 2 | Makes quality for the line list in the year 2014 -15. But the TI didn’t document the process. | Further processes must be documented. |
| 4 | Activitys in the thodupuzha site is comparatively weak. | PM should ensure the field work of ORW. |
| 5 | Field activity and young HRGs involvement in the TI is appreciable. Social media is used to mobilize new HRGs to the TI. | The strategy shall be share with other TIs operating in Metros. |

- ORW field monitoring :

Presently one ORW is working in the TI. He is working in Thodupuzha site is far from the project office. So the CBOs involvement in that area is crucial. In other two sites ORWs are not working but the M&E officer and counselor is dealing the area used PEs. Relieved ORWs documents are not updated and the field monitoring and review should be strengthened.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Relieved ORWs formats are not updated. | CBO should strictly guide the TI to update the documents before relieving from the TI. |
| 2 | Present ORW is keeping the formats and mismatches have identified in C & C1 formats. | PM & M&E should check the formats to avoid minimal errors. |
| 3 | Field monitoring details not recorded in the field diary | PE monitoring details and field dynamics should be noted in the daily diary. |

- PE: HRG ratio:

Out of sanctioned 11 Peer educators 11 are working now. PE - HRG ratio is 60 as per the proposal. Present PE HRG ratio is 1: 79

- Quality of peer education- messages, skills and reflection in the community

The evaluation team could meet 6 peer educators and it was observed that all of them are having good communication skills and they are well aware of the basic knowledge about HIV/AIDS/STI, use of condom etc. Out of 11 PEs 4 are under the age of 30. The risk patterns of the PEs are matched with the HRGs risk pattern. PEs are not aware about the CBO and its activities.

- Supervision- mechanism

Project manager is guiding and supervising the staff. Counseling and M&E officer monitoring the activities of two sites since there is no ORW. Project Mangers field visits should be planned and more focused. It feels better that PM should monitor all the sites equally.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | ORW monitoring to the PEs and reviews were not documented. | Record in the ORW field diary. |
| 2 | CBO monitoring is weak except the PD involvement. | CBO should appoint one regular person from Ernakulum area to guide the TI. |
| 3 | PMs field monitoring is not equally distributed. | PM should plan the monitoring to cover all the areas. |

IV. Services

- Availability of STI services and quality of services

Due to unavailability of fund the PPP system is not working now. Purely the TI has to take services from Government settings. Nearly 100 cases were screened in the private clinics.  There is no privacy for physical checkups in the Govt hospitals. The quality of STI check up found less in the TI. OP tickets were taken from the hospital and documented as the support of RMC. Most of the cases are general checkups rather than STI checkups. The 2014 -15 documents are not available in the TI.  In the year 2015 -16 715 (81%) cases were tested as RMC and 21 STI cases were identified and treated. Out of that 2 partners were tested. Follow up details of the STI cases and partner tested details were not documented. PT is given to 59 new HRGs out of 72 HRGs identified. The PT was given through camps. 309 (35%) HRGs were tested for VDRL and identified 7 reactive cases. 140 tests were done in the private labs. 2 partners were tested out 7 reactive cases. One partner was also reactive.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | The rapport with the private lab could help the TI to test VDRL in the private labs. | Document the efforts and share it with TSU/KSACS |
| 2 | Follow up of positive cases and partner testing were not documented. | Counselor should ensure the documentation of follow up and partner testing. |
| 3 | General checkups counted as RMC | Motivate the PEs to ensure the quality of STI screening. |

- Quality of treatment in the service provisioning-.

In the year 2015 -16 715 (81%) cases were tested as RMC and 21 STI cases were identified and treated. Out of that 2 partners were tested. Follow up details of the STI cases and partner tested details were not documented. PT is given to 59 new HRGs out of 72 HRGs identified. The PT was given through camps. 309 (35%) HRGs were tested for VDRL and identified 7 reactive cases. 140 tests were done in the private labs. 2 partners were tested out 7 reactive cases. One partner was also reactive. One HIV positive case was identified as VDRL positive.

- Documentation-

The documents in the 2014 – 15 year are not available in the TI. 2015-16 RMC & VDRL check up details are properly documented. The follow up STI cases and partner tested details are not documented.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Project is distributing condoms through direct and out lets. The evaluation team could not visit any one of the 13 outlet. Condoms distributed through the outlets are not documented. Peer educators are not recording the field level condom distribution. Form B is the only document for condom distribution and condom requirement analysis. HRGs interacted in the marine drive side demanded that they need one condom outlet there. TI stated that authorities will oppose that move, but TI could not make any advocacy meetings to open one outlet in the highly populated area. Social marketing condoms are less in the TI. Revolving fund system is followed by the TI. Cash is taken back from the ORW.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Condom distribution channel is not recorded properly. | PE s can note the condom distribution in their field diary. |
| 2 | CSM condom movement is less and revolving system is not followed | Study the needs of CSM or type of condoms used by the MSMs and the client condom bringing behavior. |
| 3 | Condom movement through the outlets was not calculated. | ORWs or PE can record the outlet condom movement. |
| 4 | Need of condom outlet at near marine drive area. | PM need to plan one advocacy to open one outlet near marine drive. |

- No. of condoms distributed-

The review team observed that free and social marketing condoms distributed against demand. A total of 254412 free condoms were distributed in the year 2014 -2015 the requirement was 264579. In the register number of condoms distributed in the year 2014 -15 was 255770 (97%) of the requirement. In the same year TI reported that they could distribute 9864CSM condoms but in the register that is only 9464 (18% of the demand). In the year 2015 -2016 free condom distribution was 105366 against the demand 145655. In the register the number is 121166(83% of the requirement).  In the last year TI could 9936 (3%) CSM condoms. Mismatch is observed with condom distribution and documentation. No revolving system is followed in the CSM.

| S No | Observation | Suggestion |
| --- | --- | --- |
| 1 | Mismatch found between condom distribution reports with condom distribution register. | PM & ME should clear the condom distribution in each month. |
| 2 | HRGs actual condom demand is not matched with the condom requirement data in form B. | Condom requirement analysis should be done by PE with consult with all HRGs. |

Information on linkages for ICTC, DOT, ART, STI clinics.

HRGs are well aware about the service locations of the TI. Fort Kochi, Mattancherry, Govt Hospital Ernakulam, Aluva, Tripunithura, Piravom, MCH Ekm, Angamali, Kaladi, Paravoor, Perumbavoor, Kothamnagalam, Muvattupuzha, Thodupuzha, Vadavukodu are the ICTC centres under the TI. ART centre is at Govt Hospital Ernakulam. Pulari clinics are available at Govt Hospital EKM, MCH Ekm, Fort kochi And Aluva. Project has good linkage with Cochin corporation

V. Community participation

Collectivization activities:

Community event participation is less. Only 52 HRGs attended in the 2015-16 community event. Total CBO membership is 578 and active members are only 320. Community committees are not active and donot have in any role in program planning and monitoring.

VI. Linkages

TI stated that they have good rapport with the service outlets of KSACS, Health & PRI officials and Police. TI could not arrange stakeholder meeting for the evaluation.

VII. Financial systems and procedures

| Findings | Recommendations |
| --- | --- |
| 1.System of Planning: Expenses as per the budget guidelines of KSACS. TI could utilize 100% fund received from KSACS. Total budget as per proposal is Rs. 18,666,20. Grant received from KSACS as on Jan 2016 is Rs. 7,80,951 and fund utilized is Rs. 7,96,871 | Nil |
| 2.Systems of payments: a) Receipts and vouchers are maintained. Verified the vouchers and found the entries are recorded in the books on the basis of vouchers along with supporting documents wherever required. b) CSM register not kept properly. c) Fixed Assets have not been purchased during the period. | Revolving fund system should be ensured by the TI. |
| 3.Systems of Procurement: a) No procurement in the contract period. | Nil |
| 4.Systems of Documentation: - Bank statements for both the period are available for verification. Month wise Reconciliation has been done and signed by the Project Manager, Director and Accountant. - Statement of Expenditures submitted in Time. - Recommendations given in previous audit was strictly implemented and followed. |  |

VIII. Competency of the project staff

VIII a. Project Manager

Project manager he has more than 1 year experience in the TI. Project manager is active in making events and activities.  PM need to give more focus on documentation and program monitoring. Planned field visits may help to motivate other staff. PM needs training in Program management and documentation.

VIII b. ANM/Counsellor

Present Counselor has more than one year experience in the TI. He is regularly visiting the field with M&E officer. Technically he needs training in planning and documentation of counseling. Counselor need to make priority wise plan.

VIII c. ORW

One ORW is working and he is from the community. He is well trained and have knowledge in the concept and components of the TI. He should document his field activities in the diary and review and guide his PEs to achieve a good result.

VIII d. Peer educators

Interacted with 6 PEs out of 11 PEs working. They are well aware about the project services and HIV/AIDS & STI. TI needs to involve PEs in program planning and documentation. All the PEs are tested for HIV, VDRL & STI in the last year. PEs need training from the CBO about the of CBO empowerment.

Viii e. M&E Officer

M&E officer cum accountant is efficient and he ia also a community member. His dedication in the project improves the quality of services. He could mobilize the communities through Social medias.

IX. Outreach activity in Core TI project

Outreach activity of the TI has good quality. The vacancy of two ORWs affected the outreach activities. But the M&E officer and counselor could do the field work. TI could motivate new HRGs to the program. The ICTC and VDRL testing have quality.

X. Services

VDRL , ICTC check up have good quality even the percentage is less. But TI should ensure the quality of condom promotion and STI check Up.

TI have 10 positive HRGs and 5 are on ART. TI could tested 4 positive cases in the last two years. TI maintained a good follow up with positive HRGs and maintained the individual file. 3 HRGs CD4 details not tested in the last year.

DATA MIS MATCHES IN VARIOUS DOCUMENTS

| Source | ICTC |  | VDRL |  | RMC |  | PT | Condom |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | HRG | Total | HRG | Total | HRG | Total |  | Free | CSM |
| Project Report 2015 -16 | 472 | 474 | 309 | 309 | 947 | 1123 | 72 | 105366 | 9936 |
| Colour coded 2015 -16 | 446 | 450 | 272 | 272 | 718 | 890 |  |  |  |
| Colour coded 2014 -15 | 572 | 573 | 421 | 421 |  |  |  |  |  |
| Project Report 2014 -15 | 572 | 573 |  | 888 |  |  | 66 | 255770 | 9464 |
| SIMS 2014 -1 5 |  | 642 |  |  |  | 1031 | 7 |  | 7854 |
| SIMS 2015 -1 6 |  | 567 |  |  |  | 869 | 31 | 121166 | 9836 |

XI. Community involvement

Community committees and the involvement of HRGs in the program planning needs to be strengthened. CBO must review the project activities and involve more MSMs in the CBO activities from the project area. Crisis were reported from the HRG level is and solved by the TI staff not the CBO.

XII. Commodities

STI drugs, free condoms and lubes were available in the TI. Last year TI could not supply more social marketing condoms.

XIII. Enabling environment

Advocacy meetings were conducted without a proper plan. Project has good rapport with VDRL private labs and some clubs. But the effort behind the rapport building is not documented.

XVI. Best Practices:

TI is using the social media like whats app and Face book. TI could mobilize new HRGs through the social media.