ReportingFormat-B								Annexure: B

Structure of the Detailed Reporting format

### (To be submitted by Evaluators to SACS for each TI evaluated with a copy NACO)

Introduction

- Background of Project and Organisation:

Snehatheeram charitable society is a community based organization registered under Society’s registration Act, in 2003 implementing TI project among MSM population in Kannur district of kerala. The project is originally own by Jeevanasamskriti and handed over to Snehatheeram during 2010.

- Name and address of the Organization: Snehatheeram, Thalap, kannur

- Chief Functionary:				  Biju.K.V

- Year of establishment			  2010

- Year and month of project initiation:  April 2014

- Evaluation team				  Dr.S.Vinod Kumar & Nikhil.K.S

- Time frame					  8th & 9th February 2016

### Profile ofTI

  - Target Population Profile	: MSM

  - Type of Project			: Core

  - Size of Target Group(s)		: 919

  - Sub-Groups and their Size	: Kothi – 350, DD- 514

  - Target Area		: Thalassery, Koothuparamba, Payyannur & Kannur

### Key Findings and recommendations on Various Project Components

- Organizational support to the programme

Detailed discussion had with five of the office bearers who are also peer educators in the project. Project director was not present during the evaluation and Secretary who was co opted by the president, treasurer and executive members were present for the discussion. Except the secretary, who was a peer educator and an active member of the CBO could share information related to CBO. It is informed that they used to monitor the project activities and provide support on a need based approach. But could not produce any documentary evidences for the same. Lack of clarity on vision and objectives of the CBO is visible during the interaction. What has been shared is community empowerment and mobilization. But could not explain how to achieve the same.

### Organizational Capacity

  - Human resources:

CBO members could not provide sufficient input as they have limited knowledge about the programme and objectives of the CBO. Project manager and counsellor position is vacant till Jan 2016 and November 2015 respectively. It is informed that the PO and authorities from KSACS suggested not to recruit any staff till March 2016. Further fund shortages also affect the programme delivery. PD is the one who directly monitoring the project and attending majority of the monthly staff meetings.

  - Capacity building:

Project Director provided training to the newly recruited M & E who is holding the position of the accountant. There was no supporting document except a register. A good majority of the CBO executive members are also peer educators and its limits scope of training to the peer educators.

  - Infrastructure of the organization

Project has got sufficient infrastructure facilities which were procured during the early phase of the project.

  - Documentation and Reporting:

Maintaining documents as recommended by KSACS but no effort seen to review the data, dissemination and sharing of reports etc. CBO do not have a specific supervision mechanism to monitor the TI activities. Monthly and weekly meeting minutes describes the details of target and achievement but without any follow up plans.

### Program Deliverables Outreach

- Line listing of the HRG by category.

Line listing HRGs maintained as soft copy and no hard copy is available at project office.

- Micro planning in place and the same is reflected in Quality and documentation.

Micro planning in place and was not reflected in quality and documentation.

- Coverage of target population(sub-group wise):

689 regular contact as against the target of 835. Area wise or category wise coverage details not available with the project team.

- Outreach planning–

Out reach planning in place and was not reflected in field work or quality documentation. Even the peer educators are not able to communicate the purpose of the process.

- PE: HRG ratio

Ratio maintained but not exactly as per the NACO guidelines. Instead of 40 HRGs , the peer educators are having 52 HRGs as lowest and 66 HRGs as highest with peer educators.

- Regular contacts:

As per records the regular contact seems to be 689 as against the target of 835. Though the achievement is around 82%, the project team should take steps to increase the number of HRGs undergoing RMC and ICTC as it is the main source of validating the project success.

- Documentation of the peer education

Peer educators are maintaining form B with the help of ORWs. Some of the peer educators are not able to describe the process and even not aware of entering the data. The importance of base line data which are very crucial in determining the programme delivery, to be explained and the peer educators should be oriented properly.

- Quality of peer education- messages, skills and reflection in the community

Majority of the peer educators are having good knowledge about programme delivery and project components. But the same was not reflected in quality documentation. Even after repeated request, the project team could not even bring one peer educator to the project office during the second day of evaluation. Being a CBO managed programme and lack of commitment from the part of the peer educators raises questions?

- Supervision- mechanism, process, follow-up inaction taken etc

Project manager and counselor position vacant and the charge was assigned to M & E. She used to verify the data submitted by the ORWs. Periodic weekly meeting organized and used to discuss about the previous weeks performance, due target if any and suggestions for improving the work. Though stated the evaluation team is of the opinion that the project need to develop a proper system for supervision at field level and also for documentation.

### Services

- Availability of  STI services–

STI services to the community are linked with the Government health care system. HRGs are referred to Govt hospitals and mostly accompanied by the peer educators or ORWs. Evaluation team could not have judgment about the STI services as the medical practitioner is on leave.

- Quality of the services.

Since the service delivery is linked to the Govt system, the project team cannot assure the privacy, quality etc. The clinics/hospitals are centrally located and easily accessible to the target population. Target group members constantly demanding for PPP as they are more comfortable with the PPPs.

- Quality of treatment in the service provisioning-

Target group members are satisfied with the treatment procedures. Only complaint is that they have to wait in the queue for longer hours and cannot discuss freely with the practitioner. Kits provided from the KSACSis available with the project but the staff members does not have any idea about the same.

- Documentation-.

Maintaining registers as suggested by KSACS from time to time. Some of the registers are incomplete. The project team could not present the details as they are not clear about the process. Evaluation team could not ascertain the balance based on the records.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Condom distribution is mainly through peer educators and ORWs. They used to collect condoms from the office and supply during field visit. A few outlets are also functioning at hotspots. But no details or review of condom movements , etc are made by the staff.

- No. of condoms distributed- As per the documents, the demands comes to 139120 and distributed 127286. There is no proper documentation system for condom distribution. Project team should develop a proper system for condom distribution.

- Information on linkages for ICTC, DOT, ART, STI clinics.

Linkages established with ICTC, DoT, SRT etc.

- Referrals and follows up

There is no referral and follow up system in place. The importance of follow up is not perceived properly by the project team. .

### Community participation

- Collectivization activities:

No. of  SHGs/Communitygroups/CBOsformedsinceinception,perspectivesofthesegroupstowards the project activities.

There are 572 HRGs registered with as CBO members. Executive board members are having limited idea about the vision and objectives about the CBO. No effort seen for collectivization. Even the community event held during 2014 has very minimla participation from the community.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Limited involvement in project activities by the community members. There is no document that shows the participation of community members in planning, advocacy etc. The committees formed last year is not functioning due to non availability of funds. Lack of community ownership is also visible.

### Linkages

### Established linkages with ICTC centers, Govt hospitals, TB clinics etc. Evaluation team has doubts on the utilization of the established linkages. ICTC tested – 578, with 69% achievement. There is no data available for referred cases. Only 60 HRGS tested twice during the last year. There is no follow up mechanism for the drop out cases. Lot of confusion and lack of clarity on project components and implementation is reflected during the interaction with the project team. Lack of leadership and quality input from the monitoring agencies are also visible.

### Financial systems and procedures

Cash book and ledger are upto date. Bank account is jointly operated by project director and treasurer. SOEs are submitting in time to KSACS. Voucher prepared by the accountant verified by project manager and approved by project director. It is also observed that majority of the vouchers doesnot have payee’s signature. Initially vouchers manual numbered but was shifted machine numbered ( voucher no 75 onwards). Audit report is not available for the last assessment period. It is stated that the CBO has its own procurement system but could not produce any documents for the same. Project has not purchased any assets during the assessment period. Fund shortage seriously affected programme delivery.

### Competency ofthe projectstaff

VIIIa. Project Manager

Vacant

VIIIb. ANM/Counselor

Vacant

VIIId. ORW

Three ORWs on the board with years of experience. Good knowledge about the target on various indicators. Out reach plan and hotspot analysis is in place but could not seen implemented at field level as per the documentation. Adequate knowledge about STI symptoms, RMC, ICTC testing etc. Need improvements in field level support to peer educators.

VIII e. Peer educators

Out of the 14 per educators 13 peer educators present during the evaluation. Most of them are experienced and in project for last several years. Prioritization of hot spot was done by the ORWs and giving directions to the peer educators. Importance of RMC and ICTC has been properly conceived by the peer educators. But the same was not reflected in programme delivery.

VIIIi. M&E officer

Though new to the project with limited exposure, M&E officer is able to provide analytical information about the gaps in outreach, service uptake to the project staff. She is managing the project and assuming the role of project manager, counsellor, M&E and accountant. She could generate the data as and when required and is visible during the evaluation process.

### . a. Outreach activity in Core TI project

Peer educators and ORWs do outreach regularly as per the documents. But there is a lot of mismatch in the documents. As stated ORWs provide supportive supervision to the peer educators at field level. There is no hot spot meeting conducted during the last year. It is stated that they could not conduct as there is no budget provision for providing tea or snacks. Out reach plan in place but not reflected in programme delivery.

### Community involvement

Community event held on 15.03.2015 at IMA Hall, Kannur  with a total participation of 137 HRGs. Organised cultural programmes discussed about project activities. No events organized during the current phase. Being a CBO, the activities for the community members seems evry less and might have affected the participation. Only 16% participation as per records. This seems very less in a project owned by CBO. The CBO leadership should take up the matter seriously to address the issue.

### Commodities

Condom requirement was done along with the micro planning as per the documents. There is no effort for condom gap analysis, ensuring the end use etc. Discussion with peer educators and with the ORWs reveals that they are also not clear about the mechanism to be adopted

### Enabling environment

There is no concerted effort for building an enabling environment for the smooth dissemination of project activities. Established linkage with service providers but not with other segments of the society. There is no proper planning or follow up for advocacy, even with police personnel.

- Social protection schemes /innovation at project level HRG availed welfare schemes, social entitlements etc.

No attempt was there from the part of the project team or CBO

- . Best Practices if any

There are a number of opportunities to experiment and develop the project as a learning site, the same was not utilized by the CBO or the project team.

### Confidential	ReportingFormC

## AnnexureC

EXECUTIVESUMMARY OFTHE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Dr.S.Vinod Kumar | 9447451466 |
| Nikhil.K.S | 9961137848 |
| Facilitator- Ranjith | 9895065459 |

| Name of the NGO: | Snehatheeram |
| --- | --- |
| Typology of the target population: | MSM |
| Total population being covered against target: | 864 against 919 |
| Dates of Visit: | 8th & 9th February 2016 |
| Place of Visit: | Kannur, Thalasserry, Koothuparamba |

OverallRatingbasedprogramme delivery score:

| Total Score Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 46.4 % | C | Average | Recommended for continuation |

Specific Recommendations

  - Six months extension to prove that the project has adequate support from the community.

  - To ensure quality programme delivery.

  - Periodic monitoring and supportive supervision from the monitoring agencies and to ensure quality programme delivery.

  - Review the programme delivery and community participation after six months and then decide about the continuation.

Name of the evaluators	Signature

| Dr.S.Vinod Kumar |  |
| --- | --- |
| Nikhil.K.S |  |
| Ranjith |  |