Reporting Format-B

Detailed Report of Jawahar Migrant Project, Kottayam

February, 7-8 - 2016

Introduction

Background of Project and Organization

Jawaharlal Memorial Social Welfare and Public Cooperation Center is a social welfare voluntary organization registered in the State of Kerala under Travancore-Cochin Literary, Scientific and Charitable Societies Registration Act 1960 as No. K19/70.The Goal of the Organization is to identify the disadvantaged and oppressed and to tackle their problems through relevant approaches viz. training, education and motivation for collective leadership; so as to become self reliant and self sufficient to lead a normal life. Since from the inception in the year 1970, the Organization has been implementing various social development programmes in urban and rural areas of various Districts in Kerala with the support of different funding agencies.

Brief history of the Project									       Since October 1999, Jawaharlal Memorial Social Welfare and Public Cooperation Center has been implementing Targeted Intervention programmes of KSACS.During the year 1999-2006, the organization has implemented PSH Project at Thalayolaparambu Panchayath, Vaikom Municipality and Mulakkulam Panchayath successfully. Since November 2006, Jawahar Center has been implementing targeted intervention programme among female sex workers in Alappuzha District. Since December 2009 the Organization has implementing targeted intervention programme among migrant workers at Kottayam with a target High Risk population of 10,000 in a financial year, still the project has identified 11 HIV Positive from the targeted area and all are linked with ART

Name and address of the Organization :- Jawahar Memorial Social Welfare and Public cooperation Centre, Thalayolaparambu

Chief Functionary: 				President

Year of establishment 			1970

Year and month of project initiation:  	 1st December 2009

Evaluation team

Domi. J.  (Team leader)

Raghi Bhaskar (Co evaluator)

Time Frame				Feb 7-8, 2016

Profile of TI

Target Population Profile:   		Migrant

Type of Project:  			Bridge Population

Size of Target Groups			7768

Sub-Groups and their Size:  		Construction (4141), Industrial          Workers  ( 3627)

Target Area:  		Kottayam Town, Pala, Paippad, Changanacherry

Key Findings and recommendations on Various Project Components

- Organizational Support to the programme:

All the positions in the project are filled.  Although two staff have resigned the positions were kept vacant as per the direction from the KSACS as part of financial measures.  All the 15 PLs were terminated since November 2015 in the same manner.

NGO has provided a separate office and infrastructure to the project. Involvement of the NGO in crisis management and creation of enabling environment is also high.

- Organizational Capacity

- Human Resources

The staffing pattern in the project is as per the proposal. They have 5 ORWs currently (one resigned)  15 Peer Leaders were in place till the end of October 2015.  The evaluation team has found a good team work among the staff members who are willing to shoulder responsibilities of their team members in places in order to overcome the language barrier of some ORWs. Out of the 8333 migrants for the ten months the project contacted 7768 migrants.

Despite the financial cuts and delay in the payment of salary, the morale of the team members is unaffected.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

There are in-house trainings conducted with the help of external resource persons by the NGO and they are documented. There is some system for capacity building or inducting the new PLs or the staff. The Intellectual and professional support of the Project Manager in this area is found to be very good.

Apart from the in-house trainings the newly inducted ORWs were taken by the PM a number of times to the sites to introduce them to the stakeholders and PLs.

- Infrastructure of the organization

Sufficient infrastructure found in the project office.  The DIC in Paippad has privacy and access by the community members.  It is very much accessible and it has all sufficient infrastructure.  Despite the delay in the release of rents, it is permitted to continue by the house owner.   The DIC in the Project office needs more infrastructure.

The assets, including the furniture, of the project are codified and numbered in the asset register.

The evaluation team could get easy access of all the statutory document and forms when asked for very promptly.  Report and feedback mechanism are also good.

- Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of  documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

The staff meeting minutes are kept updated. The other systems for documentation and reporting are satisfactory in the project. Professional systems are in place in adherence with SACS protocol. There were no deviations from the proposal in the staff appointment and PL selection. The sequence of different registers and reports are provided.

- Program Deliverables

Outreach

- Line listing of the HRG by category.

Updated Line listing of the HRGs is available in the project. The target group – the migrants- by the very nature are transient and floating.  There is system to update the exit of migrants from the sites

It is recommended to update the existing line list and there after update the exit of migrants every month.

- Registration of migrants

Migrants are identified though camp conducted by the local PHC or with the PPP doctor.  STIs detected are further followed up with the General Hospital after counseling.  DIC and STI registers are also maintained.

However there were some delays in the registration in Pala area where a migrant was found to have registered after one year of arrival in the site.

- Micro planning in place and the same is reflected in Quality and documentation.

There is good system of micro planning for outreach. All the ORWs submit a monthly programme plan to the project manager at the beginning of the month. There is subsequent weekly planning or hotspot wise planning practices are found. The monitoring of the outreach work is also active.

The documentation of registration, STI, ICTC, DIC, major events, and meetings are quite satisfactory.

- Coverage of target population (sub-group wise): Target / regular contacts

The project could reach out to 7768 HRGs against the target of 8333 HRGs.  The line list along with sub group wise data is available with the master sheet.

- Outreach planning – quality, documentation and reflection in implementation.

Plan is documented well. It seems due to the uncertainties in the nature of work of the PLs and HRG, many a time the plan is not implemented as per the plan.

- PL: HRG ratio

15 PLs have been appointed as per the proposal. As PLs have been in place only for 7 months.  If we take that into account the PL : HRG ratio for the 7 months coverage is more than 800.

- Documentation of the peer education

Attendance sheets and sessions paper are available.

- Quality of peer education- messages, skills and reflection in the community

PLs from the community are rather long standing.  The HRGs are aware of the risks HIV and need for using condoms.  ORWs intervention is very much there for activating the PLs.  PLs from the contractor and supervisor category mostly worked as condom outlets

- Supervision- mechanism, process, follow-up in action taken etc

Project  level supervision is effective by the PM.  ORWs are self motivated and team players.

- Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community

The project hires the services of doctor from Pushpagiri MCH, Thiruvalla for the STI treatment. 58 cases have been detected and they have been treated by a single doctor.  No material evidence of payment has been available, since the there was no funds for paying the PPP doctor.  Medicines were purchased by the Contractors.

We need to strengthen the coordination with the Pulari Clinic in the five government Hospitals in the District.  The PM need to take initiative to liaison with the Superintendent to fix a convenient timing for the HRGs of all the projects to get a green channel entry for treatment.  In that case medicines can also be obtained from the Government Hospitals.

Otherwise we need to device a Special OP sheet for the HRGs when prescription is made by the PPP doctor, so that they are accepted in the Pharmacy of the Govt Hospital.  KSACS may take up the case for Linkage with the Health Services Department.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Not applicable

- Purchase of Drugs

Not applicable

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres

Followed

- Documentation- Availability of treatment registers, referral slips, follow up cards ( as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

Documents are available in the project.  No STI medicines are purchased and stocked at the office.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc

PLs and the supervisors are the main outlets apart from the traditional outlets like Medical shops.  There are a lot of scope for improvements in the condom programming.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

7768 condoms distributed by the project in the current year. It means one condom per HRG in the ten months period.  Condom programme seems to be the weakest leg of the project.

An average of one SM condom per HRG has been distributed in the place of 3 for three quarters being evaluated.  Even out of the 7768 condoms distributed in the current year, only Rs. 4278 has been collected @Re.1/- per condom. There is no reason to believe that the Migrant HRGs whose income level is par below, purchase condoms from outside.  That being the case, the condom programme is yet to make any headway as far other components of the project are concerned.

- No. of Needles / Syringes distributed  through outreach  / DIC

Not applicable.

- Information on linkages for ICTC, DOT, ART,STI clinics

Linkage with the ICTC and ICTC referral are satisfactory and good.  Documents are available and cross checked with that of the mobile ICTC.  The project is depending on mobile ICTC for the 90 percent of its uptake.  The project has done excellently to pick from the adversities created by the non availability of ICTC kits and fuel for nearly three months.

Out of the 58 STI cases only all were tested for HIV.  .all the 3 HIV positives have been linked to the ART

Fund for the fuel for the Mobile ICTC may be provided to the TI; or the General Hospital may be given an order from the DHS/ PD KSACS to spend POL from HMC fund in case fund is not available and the same may be recouped when the fund is provided to them.

- Referrals and follows up.

Referral cases are documented and followed up. A system is good.

- Community Participation

Community participation to the extent that could be expected of a migrant community is there.  Linkages

- Linkage with the ICTC and ICTC referral are satisfactory and good.

- Linkage with the Mobile ICTC has made the testing of Migrant HRGs all the more easy

- Support system includes the PPP doctor, HR Managers, supervisors, contractor, District Health system, District Administration etc.  There a good level of support from these stakeholders.  Support from the labour officer and Police need to be ensured.

- Linkage between STI and ICTC is clearly established

- The project has been able to establish a very good connectivity with the district admistration ie DC, ADM and the DMO that it has been instrumental in rolling out a campaign in the whole district coordinated by the DC to assess the conditions of the Migrant labour camps.  555 camps in the district have been surveyed in the process and strict enforcement by the Collector lead to improvement of the general conditions of the labour camps.

- Financial systems and procedures

  - Systems of planning: Existence and adherence to NGO-CBOguidelines/anyapprovedsystemsendorsedbySACS/NACO-supportingofficial communication.

All the formats are according to the guidelines. The project is maintaining good organizational structure, NGO relationship and financial management system. A commendable fact seen is that PD has attended all the monthly meeting in the project.

  - Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

Most of the payments were settled by cash.  The above Rs. 5000/- transaction were through cheques. Voucher prepared by accountant verified by project manager and approved by project director. All the transactions have corresponding vouchers and bills and there is no mismatch with register and cash book. Cash book maintained in daily basis. Ledgers are counter signed by the PD.

  - Systems of procurement- Existence and adherence of systems and mechanism of procurement endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

No medicines are purchased. KSACS does not have supply of medicines to the project. The condoms received from KSACS are circulated among HR through proper social marketing. There are sufficient numbers of outlets for supplying the condoms to all the HR as required.

  - Systems of documentation- Availability of  bank accounts (maintained jointly, reconciliation made monthly basis), audit reports

The Jawahar Migrant Project has a Bank account started for transaction and various financial purposes with respect to the projects. In the projects financial transactions above Rs.5000/- are transacted through cheque and only lesser amount are circulated in cash. Audited annual accounts are conducted. The audit on annual accounts for each year is duly conducted and certified by auditors which are properly maintained. Even though there is an insufficiency of funds in the project, all necessary steps are active endeavors are made to conduct service delivery and other activities of the projects, which is highly appreciable and plausible fact.

- Competency of  the Staff

- Project manager

Project Manager is in place for last 3 years.  He is MSWHe is proactive in bringing in connectivity with the support systems.  Quarterly and monthly plan are in place, financial management is as per norms of SACS (please see the financial review report), computerization of all the migrants data with individual tracking done.   He has knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit.   Advocacy initiatives are also strong.

DC, ADM and DMO were very satisfied and praised the interventions of the project.

- ORWs

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action are good.

e. Peer Leaders

Terminated since November 2015

i. M&E officer

MIS in the project is well maintained.

VIII. Outreach activity in Truckers and Migrant Project

Major outreach activity in the project is Health camp at sites and outreach sessions by the ORWs and PLs.  Presence of the ORWs in the field is very much felt in the service uptake in terms of ICTC, STI, condoms etc.  .

IX. Services

Overall service uptake in the project in terms of health camp, ICTC referrals, are good, quality of services in the DIC is visible.

X. Community involvement

Involvement of the community members in the project is high (limitations of the migrant project in this case is to be considered).

XI. Commodities

Zone level planning for condom programming is done.

XII. Enabling environment

Advocacy events are planned and conducted systematically.  The project has achieved desirable entry points in the District Administration and health department, PHCs etc.  a Mini Marathon Programme organized on WAD 2014, and the Onam Celebrations attended by the Minister, DC, Municipal Chairman, DMO, ADM etc brought the issues of the migrant labourers in to the agenda of the administration.

These programmes were organized without spending any money from the project.

XIII. Social protection schemes / innovation at project level HRG availed welfare schemes,

Social entitlements  etc.

Welfare schemes for the migrant employees is well coordinated by the project.

XIV. Best Practices if any

- Health camps coordinated with the local PHCs are owned by the PHCs also.  This mutual assistance has made health services (sexual health and general health)  more accessible for the migrants.

- Team work among the project staff is to be very much appreciated

Major Recommendations

- More specific efforts should go down to reach out to migrants in unorganized sector.  Migrants in the organized sector have more access to the services; those in the unorganized and those brought directly by the brokers need more attention.

- MSM behavior among the migrants is to be suspected and such cases need be traced from the PLs and they may be provided with focused BCC rather than generalized services by the project.  Condom program also needs more focus.

- The project cannot afford to move along without Peer Leaders; it’s like running a marathon without limbs.

- Visibility and utility of the DIC in the Project Office at Kottayam may be improved

- The project needs to update the existing line list of HRG Migrants with exit and entry of migrants every month.

- SACS may develop an OP Card for the Migrant STI screening and tie with the Health department to supply STI drugs from the Pharmacy of the Government Hospitals, when they are shown after prescription by the PPP Doctor.

- The cooperation of the PPP doctor is a significant component in the outreach camps in the sites and overall coverage.  But the over reliance on one person may sabotage the project in case of negligence by the doctor.  More such proactive doctors need to be pooled as a support system for each zone.

- The delay in the registration of the HRGs is to be reduced optimally as the geographic mobility is very high among the community.

- Coordination between the Pulari clinic and Surksha is to be strengthened to avoid delay in the services when HRGs are brought to the Pulari clinic.

- There should be clarity in the funding; financial cuts in between the project period can derail the project; but for the commitment of the project team.

- Fund for the fuel for the Mobile ICTC may be provided to the TI; or the General Hospital may be given an order from the DHS/ PD KSACS to spend POL from HMC fund in case fund is not available and the same may be recouped when the fund is provided to them

Conclusion:

The project on the whole has made significant inroads into the major migrant zones in the district.  The team was amazed to see the rapport established the ORWs and PM over the Paragon Factory, other Real Estate Contract camps in Kottayama and Paippad.  The major components in the proposal are implemented with the required level of rigorousness.  HIV testing, Health Camps and Enbabling environment are the strong areas of the project.  Condom program is yet to pick up momentum.  It can fast become a beautiful learning site with little more focus in condom program and finding effective linkage with local PPP doctors.

The contribution made by the NGO by closely monitoring the components and by inducting ORWs requires special mention.

Sd/-

Domi. J

Team Leader

For Evaluation Team