Evaluation Report (Format - B)                Annexure B

Rajagiri Outreach Migrant project, Ernakulam

A. Introduction

1. Background of Project and Organisation

Rajagiri outreach is the professional service wing of Rajagiri college of social sciences. The NGO is registered under the Societies Registration Act (Reg No. 157/02) The agency has strength of 74 staff including 50 qualified social workers. Since September 2008, Rajagiri has been implementing TI among migrants at Ernakulam district. The migrant population is mainly concentrated at Ernakulam and the NGO had able to establish a strong linkage in this program.

2. Name and address of the Organization:

Rajagiri outreach

Pulimoodu Building, 										Opp. 10th PIUS Church, Church Road,

North Kalamassery

Phone No: 04842108302

rajagirioutreachsuraksha@gmail.com

3. Chief Functionary:   Mr. Antony, Project Director

4. Year of establishment: 2002

5. Year and month of project initiation:  September 2008

6. Evaluation team:                Mrs.Savitha Shenoy

Mrs. Rani Nithesh

7. Time frame: 		2 days (Feb 8th & 9th  2016)

B. Profile of TI

1. Target Population Profile: Migrants

2. Type of Project:                   Bridge Population

3. Size of Target Group(s):  According to proposal 10,000

4. Target Area : The target population of the TI is 10,000 high risk migrants belonging to Kochi Corporation and neighbouring Panchayaths and Municipalities of Ernakulam District. The project covers 5 sites (target areas) and 62 hot spots belonging to Kochi Corporation, Kalamassery, Thripunithura, Aluva, Thrikkakkara, Paravur and Eloor  Muncipalities and Varapuzha, Edathala, Alangad, Karumalloor and Kadungallur Grama Panchayaths. The site wise population distribution of our Project area includes Ernakulam (above 50,000), Kakkanad (above  30,000), Aluva  (above 20000), Kalamassery (above 30,000), and Paravoor ( above 20,000).

C. Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

According to the PD, the institution is very supportive to the project. They have another migrant project at Perumbavoor also. Governing body supports the TI very much. They are not directly involving in the project and complete freedom is given to the project director to take decisions. The NGO back up is really appreciable. The project director although involved in the project related all activities his attendance in few monthly staff meetings not reported. For better monitoring and giving proper support to the TI the NGO assigned a Sr. Project Officer as incharge also.

2. Organizational Capacity

a. Human resources

The staff structure is as follows

Manager - 1

MEA - 1

Counselor - 1

ORWs – 5 (now four, one ORW resigned in December)

Project has presently 4 ORWs  and out these one ORWs is a senior person and have a good knowledge about locality. Other three ORWs joined project in this contract period the counselor and MEA joined 10 months ago.

The newly joined staff undergo orientation training by the project. These orientations training must be properly documented. The roles and responsibilities are in place and all staff has been issued appointment orders. The leave registers are maintained by the project. Project manager takes overall supervision but needs to focus on documentation and monitoring. The conceptual clarity of all staff  has to be improved.

b. Capacity building

As per the staff on joining each new staff will undergo one day orientation in the project. The Sr. Project Officer will lead the session and later a senior staff will accompany to field. But the project is not preparing any training reports for such training hence could not be verified.  PEs are also getting trained as per the staff but only one report was seen. Evaluation team suggested proper documentation of all trainings attended and imparted by the project.

c. Infrastructure of the Organization

Project office is situated in Kalamassery and is accessible to community but they are not using it, There is adequate space available for program administration. They have displayed the map of Ernakulam district in the office. The DIC was closed down due to financial constrains.

d. Documentation and reporting

The project maintains the formats of NACO. The project keeps line listing/master register in the mode of soft copy but is not using in an analytical way.

PM is not verifying the documents and reports regularly. They are maintaining the staff meeting minutes and the PD's presence is also observed in the meetings. Daily dairy is maintained by the staff but there was no information regarding the follow up given to the HRGs who were given symptomatic treatment for STI, Inputs given to the PEs, etc. Monthly plan and weekly plan is done elaborately but change in the programme is not recorded anywhere.   Movement register needs to be verified with the daily dairies by Project Manager.

The Formats of the project lack quality as a whole and many of the staff are fulfilling them without much understanding. The registration format has data but cannot be analysed for further use as the data is not correlating. In staff meetings the review must be properly documented and all the planned programme, changes in planned programmes and the review of the conducted programmes has to be included. The major decisions also has to be documented in the end of the report. Counselling formats also lacks quality. There is no change in the information filled for counseling on RR or Follow up counseling.

3. Program deliverables

- Outreach:

The project has appointed five ORWs  (one ORW resigned in November) in the stakeholder ratio.  The understanding of the ORWs regarding microplanning and project concepts  is very minimal. The condom demo is done by the PLs in the field along with the health classes.  Few ORWS were not at all comfortable in taking session. The PL present was also having many misconceptions regarding the HIV/AIDS.  Now the project does not have PLs (except 4) who work for project. It was very apprehensive for the evaluation team to understand the quality of services provided to the contacts  achieved by the project.

The project is able to register 8906 HR migrants in this year out of the total target population. 3992 migrants were screened from 78 camps. Out of these 53 were  sponsored health camps. The target for sessions are 350 per month and is achieved by. The staff has to be oriented about the outreach planning  and using it as a team.

Peer education: A total of 4 PLs are in place out of the proposed 15 PLs.  Due to shortage in funds project has VPL instead of PLs. All the VPLs are from source states which include West Bengal, Orissa Assam, UP etc. ORWs are supporting them in field and the ORWs visiting the field 5 days/week as per the ORWs. Evaluation team could meet only two PLs. The peer educators are having good knowledge about the work and HIV/AIDS but have few misconceptions too. There were no reports of PL/VPL meetings held at the project office. PL are not involved in the planning but they are instrumental in entering new sites when they shift there.

The PLs know the usage of condoms and they are able to do the demonstration.

The contractors, managers and safety officers are helping in PL selection. Currently all PEs are from source states. The project is keeping a PL photo directory also.

Currently the field visits of ORWs are 5 days/week and the target for the sessions to each ORW is 70 per month. In this 10 sessions they have to directly conducted and rest 60 sessions are to be conducted by their 3 PLs (each PL has to conduct 20 sessions). 3244 sessions were held in the current year. Most of the sessions are conducted by the ORWs in the project. The PM has to visit the field regularly and has to increase the relationships with PLs. The closure of DIC has added to the agony.

b. Services

ICTC: The project is able to test 970 HR migrants for HIV and two were found positive. One of them was referred to the ART centre by the project. No counseling support was provided to the HR by the project counselor.

STI services are in place and systems are also good. The project introduced ICTC referral slips with 3 portions. As per the PP doctor about 40 - 50 migrants are coming in a health camp and he knows Hindi. .Out of 3992 HR screened 100 were identified as having scabies cases but no one teasted for HIV. The project collected some general medicines and sample medicines and they are given at health camps to HRGs. The prescriptions are giving to the migrants. Out of 100 cases 44 were followed as per the format of counseling but the quality of counseling is not verifiable. TI documentation has to be more clear. Attitude of the doctors is well appreciated.  Project is able to identify a very good and dedicated doctor for the medical camps. Dr. Jose Mathew is associated with Metro Rail Project as their Medical doctor and is genuinely involved with the health and hygine issues of migrant workers.  He can converse in hindi that make things easy.

The project is having tie ups with some PHCs also.  Project has good link with mobile ICTC.  Abrupt cancellation of visit by mobile ICTC hampers the efforts taken by the project in assembling HR Migrants for test.

STI services: Currently the STI medicines purchased by the project and general medicines are collected from other sources. Sometimes the PHC will provide medicines and labour dept.

also gave medicines. They had enough medicines and it was purchased from the revolving fund.

Pulari Clinic is not utilized by the HRs.

Counseling: The project is able to provide counseling to 33% of the community and the quality of the sessions has to be improved a lot. For 10 months the TI is able to provide counseling to 2939 persons. The time taken for counseling is 15 minutes on an average as per the documents and the counseling details is filled in a preprinted format. The information regarding the risk of the HR are same in all the counseling sheets evaluation team verified. The follow up of the STI cases was also limited to 44 out of 100 identified.  One of the HR identified with HIV was referred to the ART and DOTS but no counseling was done by the project counselor.

Project has two staffs PM and MEA who can support counselor during the health camps in counseling.  The project team lacks coordination in terms of maximum utilization of resources available within the team.

Condom services: The project is able to open 35 outlets and in this 23 are non traditional but the supporting documents are not there. The evaluation team could verify only one outlet.  Outlet monitoring is not done regularly and many areas lacked outlets. Outlets are only known to ORWs. Although project office is in Kalamassery no outlets were functional to be shown to evaluation team. Evaluation team was very much surprised due to this fact.

Involvement of TI in developing more social marketing outlets is found insufficient. Project team is not aware about the condom outlet concept and its need.  The project is able to distribute 4950 social marketing condoms. Currently there is no free condoms and they are using SM condoms for demos. Condoms are placed at work sites and supervisors and PLs are the custodians.

Mid media/Congregation events/film shows

The role played by mid media activities in the information passing for behavioural modification are very significant amidst all the constraints. 12 mid media events were held out them 9 were sponsored and three were conducted using the project fund. Due to fund constrains more mid media events could not be conducted. Congregation events were held in two spots with the financial support of the employers and 254  migrants participated in the events.

d. Linkages: HRGs are aware of the services provides in ICTCs and health camps. They are not familiar with ART details. The ICTC referrals found good but seeing the doctor in Government Hospitals was found time consuming. They were not ready to sacrifice their income unless it was very urgent.  According to the community project is keeping confidentiality and they are satisfied with the services provided by the project. They are having a good linkage with labour dept. also.

e. Financial systems and procedures:

  - Systems of planning:  system of finance management is as per the guidelines of SACS only

  - Systems of payments- cashbook, ledger, cheque issue register is updated, bills and vouchers are in place, no mismatch found, all supporting documents were available. Monthly expenditure statements are filed.

  - Systems of  procurement- there is no purchase of medicines due to shortage of fund. They are collecting medicines for STI clinic through sponsorships.

  - Systems of documentation- separate bank account maintaining, passbook is available. No audit report given from SACS.

f. Competency of project staff

1. PM: PM has experience of two years in this project but has to improve his skills in verification and monitoring of project documents.  He is good at presenting the project activities.  He has to take special care to make all members of the team work together rather than in the individual capacity. Project Manager has to explore his demonstration  skills with regards to the project.  He should prepare a schedule to fit in all areas of his project to be demonstrated in minimum time like meeting HR, outlet, ICTC, PPP doctor, PL,etc

2. MEA: The MEA has 1 year of experience and has learned the TI work immediately. He has to do field visits more and it will help in analysing the data also. He has to present the analysis in staff reviews. The data filled in by the project staff  have to be critically analysed. MEA can help counsellor during health camps and vice versa.

3. Counselor: The counselor is having an experience of 10 months and needs to get counseling training in context to the project.  Actually now information gathering is done rather than information passing. The counselor in more into achieving target rather than quality of the counselling.  The evaluation team suggests that more emphasis (quality wise) can be paid on STI cases, PLWHA, migrant who are really at risk.  The documents related with counseling are to be properly filled. The attitude of him towards the community is good.

4. ORWs: Out of the 5 ORWs, the project is having 4 ORWs at present and one of the ORWs resigned on 30th Nov 2015. Senior most ORW is good at his work but is over loaded due to supporting other lady ORWs. Two Lady ORWs were very shy to do condom demonstration.  One of the ORW was completely nervous when asked to take a session at her own site.  The arrangement to visit the site was done by the senior ORW and not by the one who is incharge of that site. It is very doubtful to the evaluation team as to how these ORWs are working at sites, conducting session, filling A format, training PLs. etc. Language is hinderance to one of the ORWs but as her PL knows Malayalam she is managing.   Migrants are free to intervene  during evenings  but project does not have working culture after 5.30 pm. ORWs are to be trained in a communication package to be delivered in health class and should definitely include STI symptoms.

g. Enabling environment: The project is able to address the issues relating with the community. The goodwill of NGO is supporting in achieve these. They are having a good networking with panchayaths, labour dept and PHCs. Advocacy part is dealt by PM and ORWs are also having strong relations. Planned advocacy has to be given more priority and document the activities in detail. The project was unable to organize steering committee meeting due to panchayath elections.  The project was able to raise funds from the employers to organize medical camps, congregation events and mid media events.

h. Best practice/new initiative:

- In the context of fund shortage, TI could conduct sponsored programmes, mega events, STI Clinics and allied services under the sponsorship of various employers, builders and secondary stakeholders like Metro Rail Project Partners and sub contractors such as L&T , SOMA, Alstom, Mcnally and So on...

- TI could ensure maximum services for HR Migrants through programmes in co-operation with health department , Govt. Of Kerala and its sub-agencies such as PHC, Leporacy division, Malaria division and so on..

- Challenges faced:

The abrupt cancellations of the visit by mobile ICTC has brought down the ICTC visit. Migrant with high risk behavior need to be assembled in advance to be tested when mobile ICTC comes to the site. When sudden changes in plan happens the preparatory work done by the team is wasted and it takes extra efforts to reorganize them.

Fund shortage: Although NGO was supporting the project financially to some extent the programme was held back at some places like enrolment of PLs.

### Confidential	Reporting Form C 		Annexure	C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile ofthe evaluator(s):

| Name ofthe evaluators | ContactDetails with phone no. |
| --- | --- |
| Savitha Shenoy | 9447804942 |
| Rani Nidheesh | 9747211514 |
| Officials from SACS/TSU (as facilitator) | Mr. Pappu |

| Name of the NGO: | Rajgiri migrant Project, Kalamassery |
| --- | --- |
| Typology of the target population: | Migrants |
| Total population being covered against target: | 8864 |
| Dates ofVisit: | 8th and 9th February 2016 |
| Place ofVisit: | Kalamassery, Ernakulam |

OverallRatingbasedprogramme delivery score:

| Total Score Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 41%-60% | C | Average | Recommended for continuation with Regular monitoring by SACS/TSU/NGO |

Specific Recommedations

  - Project  team has to be empowered in terms of skills and concepts clarity.

  - Counselling  quality has to be strengthen.

  - Outlets for Social marketing condoms distribution has to be increase and monitored.

  - Steering committee has to be formed and meeting held at least once in a year.

  - All STI identified HRs to be referred to HIV testing.

  - All STI identified HRs given proper follow up

Name of the evaluators	Signature

| Savitha Shenoy |  |
| --- | --- |
| Rani Nidheesh |  |