Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organisation

Rajagiri Outreach is the professional service wing of Rajagiri College of Social Sciences, Kalamassery. The NGO is registered under Societies Registration Act (Reg. No. 157/02). The intervention among the migrants in and around Perumbavoor was initiated by an NGO, CARB. Rajagiri Outreach took over the management of the Project in December 2010. At present, the project is covering a population of 10,000 high risk migrants in Perumbavoor Municipality, Rayamangalam, Vengola, Vazhakulam, and Koovappady.

| Name and address of the Organization | Rajagiri outreach Rajagiri College of Social Science Rajagiri P.O., Kalamassery, Kerala |
| --- | --- |
| Chief Functionary | Rev. Fr. Jose Alex CMI |
| Year of establishment | 2002 |
| Address of the project office | Palayath House, Lakshmi Nilayam, Opp: Boys High School Ground, Near Taluk Hospital, Perumbavoor Phone No: 04842254676 |
| Project Director | Mr. Antony M.P |
| Year and month of project initiation | December 2010 |
| Evaluation team | Ms.Shefeena P.S Mr. Asish |
| Time frame | 5th to 6th February 2014 |

Profile of TI

| Target Population Profile | Migrants |
| --- | --- |
| Type of Project | Bridge |
| Size of Target Group(s) | 10000 |
| Sub Groups and their size | 90% Plywood company workers |
| Target Area | Perumbavoor, Rayamangalam , Vazhakkulam, Vengola, Koovappady, Okkal, Kalady |

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

RAJAGIRI outREACH is the professional service wing of RAJAGIRI College of Social Sciences. The agency has strength of 74 staffs including 50 qualified Social workers. The expertise and manpower of Community Health division is the major supporting division to the project activities. Resources (Infrastructure and man power) and reputation of RAJAGIRI College and the NGO are utilized for the implementation of the project activities

Rajagiri outreach Suraksha Migrant project was started on 15th December 2010. The support of Rajgiri outreach can be visible in programme monitoring and implementation .The involvement of project director and co-ordinator was good in all the aspects. They are providing timely input and monitoring the project well. Their experience in the social development sector is utilising by the project for advocacy and networking.

- Organizational Capacity

  - Human resources: All staff are placed as per Ti guideline except counsellor. Post was vacant for last 6 months and not filled the vacancy as per the direction of KSACs. Staff are well experienced and have good knowledge on TI programme. They are clear about the roles and responsibilities and have a food relationship with organisation. Their attitude towards the target population is also good.

  - Capacity building: Capacity building is being taken care by the NGO. The NGO as a training resource centre has been utilised in capacitating the Staff of TI. Analytical skill of the outreach workers need be enhanced.

  - Infrastructure of the organization:  Infrastructure of the project is available as per necessity and needs.

  - Documentation and Reporting: Documentation system maintained in the project is as per SACS/NACO guidelines. CMIS and other allied documents maintained well. All documents were available in the project for verification. Most of the documents were found to be complete and triangulated. The skill of presenting data of these documents by the team needs to be practiced at project level which helped to get quality data.

III. Program Deliverables

Outreach

- Line listing of the HRG: The line list data entry is not properly tallying with the data of ORWs revealed at the time of personal sitting. Registered 8282 in the line list- Missing of 45 beneficiaries from the line list.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling: 8282 were registered in the project and provided service

- Micro planning: Field visit area were not properly mentioned, ICTC target setting not mentioned in the plan

- Coverage of target population (sub-group wise): 8282 migrants were covered out of the target of 10000.

- Outreach planning:  out reach plan is prepared by the project and it is documented. Weekly and monthly reviews were also done in the project.

- PL: There were no PLs in the project. Due to fund shortage KSACs had instructed the project for the same. The PLs are now using as VPLs and they are supporting the project for providing services in their respective companies. One to one interaction done with 5 VPLs. They were efficient and able to provide condoms and conduct group sessions. One VPL who we met was very shy to reveal the HRG details even though he is working for the project for last 2 years.

- Documentation of the peer education: All the documentation part was done by ORWs. The works of the VPL’s are reflected in the daily diaries of the ORWs.

- Quality of peer education: Most of the VPLs who were met during the evaluation were found to be with good communication skills except one. They are well aware of the risk behaviour of their peers and have essential information regarding STIs and HIV.

- Supervision: The overall supervision of the programme is done by the manager .Monthly review meetings were conducted properly and discussed various issues regarding project activities and action taken according to the decisions .The project should focus more on to improve the quality of data in the field and do critical analysis of  various work done by the project staff. This should help the project to get quality data

IV. Services

- Availability of STI services: Even though shortage of funds, the project could organised health camps as per plan and they had mobilised Saw mill association funds for health camps 3886 HR migrants were given STI screening service out of 75 camps conducted. PPP doctor was also linked in all the camps .Each camp for about 4 -5 hours. The project has 3 PPPs doctors and they are supporting the project. 135 symptomatic cases identified and treated through medical camps.

- Quality of the services. STI screening is done through risk assessment by ORW/PM. PPP doctor was linked with the camps and STI medicines were provided to the cases.

- 135 STI cases were identified and treated. All the cases were given follow up and it was documented in the ORW dairy and in the register. All the STI cases were tested for HIV.

- Quality of treatment in the service provisioning: Syndromic treatment protocol is followed. Referrals to ICTC, ART and DOTS centres are done on a need based manner. Total 2021 HR migrants were tested for HIV. Two positive cases were identified. One was linked with DOT and ART centre. Project had utilised the services of the mobile ICTC which helped the project to achieve the target.

- Documentation-Project has maintained all documents related to screening /referrals, ICTC

- Availability of Condoms: Compared to last years the project had improved SM of condoms. Project had distributed 7497 SM condom during the reporting period. All the VPLs who we met are distributing the condoms to the needy. Accounts of the SM were maintained well. The project has started 50 outlets and 34 are active (31 non traditional, 3 traditional). All the traditional outlets are inside the company.

- Information on linkages for ICTC, DOT, ART, STI clinics:  Linkages were done properly.

V. Community participation

- Collectivization activities: Bhai Mela was organised and 203 migrants were participated in the programme. The programme includes Ganamela, Cinematic dance, Fire dance, Fusion dance etc.

- Community participation in project activities: There is no PLS in the project and VPLs are supporting the project organising the migrants for health camp, group sessions, and condom distribution.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc: Linkages with all service providers in the project area were done properly.

- Percentages of HRGs tested in ICTC and gap between referred and tested: 2021 HR migrants were tested in ICTC which is about 25% of the target population.

- Support system developed with various stakeholders and involvement of various stakeholders in the project: A project management committee was formed by the project to ensure support from various stakeholders. The project is getting support from Health Inspectors in the Rayamangalam and koovappay areas and project was associated with all the camps organised by the health in these two areas. Saw mill association (SOPMA) supporting for addressing various issues

VII. Financial systems and procedures

- Systems of planning: Budget utilisation is as per NACO norms. 86 % Utilization. NGO had supported the project to run the programme.

- Systems of payments:  Vouchers and Bills are properly maintained with supporting documents. Cash payment done for amount less than 2000/-. Vouchers are printed and machine numbered.  There was no mismatch observed.

- Systems of procurement: No purchase done during the period.

- Systems of documentation: SOEs are submitted before 4th of every month. Cash book /ledger maintained properly and countersigned by PM/PD

VIII. Competency of the project staff

- Project Manager: Project Manager is a Post graduate in Social Work with LLB. She is working in the project for last 5 years. She is leading the project with good team spirit. Her qualification and experience is helping her in leading the project. Monthly reporting is done as per the requirement of SACS/NACO.  Presentation and justification data, Critical analysis and providing feed back need to be increased. She could identify the potentials of the team members and assign activities accordingly.

- Counsellor: Counsellor is Vacant and not filled  till date as per the direction of KSACS

- M&E/A: M&E is doing sincere efforts to maintain the documentation system of TI project well. She is doing M&E and accountant duties. All the documents are maintained well and all are matching each other. She is very active and a good team player. She needs to improve the quality checking of the data which is getting from the field and present before staff.  Also needs to cross check the line list data with other formats maintained by ORWs

- ORW: There are five ORWs in place. Most of them are in the project for the last 5 years. All are good in Hindi language which helps them to interact with migrants. Performance of ORWs is good. The relationship between the ORWs and VPLs is good and VPLs who were available for interaction were comfortable with the ORWs. The documentation skills of the ORWs are improved and they need to focus more on taking quality data from the field and provide an orientation to the ORWs how many migrants they covered and % of High risk identified.

- Peer leaders:  Currently project is not having Peer leaders. Most of the activities are carried out with help of VPLs and directly by the ORWs. VPLs are supporting the project for organising health camps, group meetings, condom distribution etc.

IX. Outreach activity in Migrant Project

The outreach sessions are conducted by ORWs. 105 sessions were conducted by ORWs. Through the out reach activities 3886 migrants participated in Health camps and 135 are identified with STI symptoms and 2021 referred to ICTC. Out reach activities were conducted as per the suggestions of Migrants and Supervisors.8 congregated events were organised and 789 migrants were participated in the same.

X. Services

STI check up and counselling is done through camp approach. DICs were stopped as per the direction of KSACS. The project was utilized mobile ICTC service which helped the project to provide the ICTC test to the maximum. All the identified STI cases were given proper treatment. Counselling service was provided to 2015 migrants

XI. Commodities

Condom outlets are in right place where the migrants can easily accessible.HR migrants were practised to buy social marketing condoms and they are paying it to the VPLS/ Supervisors. Social Marketing of condoms has increased in the project area. The project has given more focus on SM condoms during the reporting period. Project had distributed 7497 SM condom during the reporting period. All the VPLs who we met are distributing the SM condoms to the needy and paid money. Condom distribution details were mentioned in the ORW dairy.500 free condoms were also distributed. There are 34 condom outlets in the project area where condom distributed.

XIII. Enabling environment

A Project management committee was formed with municipal chairman, secretary, SI , medical superintendent, Assistant labour officer, representative of Saw mill association, hotel and restaurant association and ward counsellors. Advocacy need to be a more planned so as to address more issues among migrant population and visibility of the programme. Project need to take more efforts to increase the visibility of NGOs name in all the programmes.

XV. Best Practices if any

- Project has taken appreciable efforts to celebrate children’s day programme at Govt. UP School Kandanthra

- As a part of collectivization step project has organized BHAI Mela where 203 migrants participated

- Project has helped migrant children to get school admission.

- Ant tobacco day was celebrated

- Project could open ICTC clinic on Sundays as per the convenience of target population.

- Project made good effort to utilize the SOPMA fund for health camps in the target area.

Name of the evaluators

Shefeena P.S

Asish

Date:5th and 6th of February 2016