Annexure: B

### WHI Suraksha Migrant Project, Thiruvananthapuram

Introduction

- Background of Project and Organisation

Women Empowerment and Human Resource Development Center of India (WHI), is an NGO registered under the Travancore-Cochin Scientific Cultural and Charitable Societies Registration Act XII of 1955. The orgaisation has its head office at Trivandrum, and five community development centres spread across four districts.FIRM, organization based in Trivandrum District had started Migrant TI project in the District in 2008.  From 2010 onwards this TI project has been implemented by WHI.

- Name and address of the Organization

WHI Surakha Migrant Project

KRA-14, Kalippankulam Road,

Manacaud P.O, Trivandrum-695009

Ph: 0471-2725110

Office Mail Id: whiindia@yahoo.co.in

- Chief Functionary:		Dr. K.G. Vijayalekshmy

- Year of establishment : 		1998

- Year and month of project initiation: December 2010

- Evaluation team

Mr. John T Samuel (Team Leader)

Mr. Shiju Samson (Co-Evaluator)

- Time frame 01-02 February 2016

### Profile of TI

  - Target Population Profile: MIGRANTS

  - Type of Project:  Core

  - Size of Target Group(s) 10000

  - Target Area: Trivandrum city, Palayam, Kazhakkoottam, Menamkulam, Aakkulam

### Key Findings and recommendations on Various Project Components

### Organizational support to the programme

The TI project is contratcted by the organization. WHI gives free hand to the Staff to conduct the programme. The President of WHI who is also the Project Director visits the project frequently to interact with the Staff.

### Organizational Capacity

The project has 1 Project Manager, 1 Counsellor, 1 M&E Officer, and 5 Outreach Workers. The Staff is committed to the project. The project does not have serious Staff turnover. All of them have been in the project for the last 1 year. The Staff attended the 4 training organised by KSACS in 2015. The organization does not conduct any training for the Staff. The project has the necessary infrastructure for the conduct of TI project. Documentation follows SACS protocols. Documents are available for verification, and are periodically reviewed by the KSACS officials. The project submits the necessary reports to KSACS in a timely manner as specified by KSACS.

### Program Deliverables - Outreach

### WHI TI project has registered 7635 migrants from the service sources like STI clinics, DIC and Counseling. Micro-planning documents are in place, by they are not specific and do not detail the services to the rendered to the migrants. Outreach planning is not reflected in the micro-plans of the ORWs.

### The project has only 9 Peer Volunteers. They are from 3 sites. 2 sites do not have Peer Volunteers, as they have dropped out due to lack of remuneration. The Project Manager supervises the work of ORWs in the field, and the ORWs supervises the Peer Volunteers where they are available.

### The medical camps are the avenues for STI identification and HIV test. All the referred cases have tested for HIV.

### Services

### STI services are channeled through the Government Hospital and the Medical College. Identified HIV + cases have been referred to ART Centre in Medical College, and 1 case diagnosed with TB has been referred for DOTS. Treatment registers and clinic cards are well maintained by the Counsellor. The Doctors do not sign or affix their seal to the clinic documents. The doctors follow SACS protocol in providing STI services. The ORWs follow up identified STI cases. This is not reflected in the documents.

### Community participation

The project has not organized any collectivization activity in 2015.

### Link

### The project has established good linkage with Government health structure (General Hospital, Medical College), and with other stakeholders like the Labour Department, Construction Agencies, and labour contractors. They provide support for the Group Sessions, medical camps, and individual meetings with the migrants.

### Financial systems and procedures

Normally the financial records are managed by the M&EO. Since the M&EO is on leave of absence, the Project Manager maintains the finance related records. The Cash Book, ledgers, and other financial records are well-maintained as per KSACS norms. Fund utilization is 100%. Against an approved budget of Rs. 18,18,400, the project received Rs. 7,34,446 – 40% of the total budget. The project expenses till 31stJanuary 2016 is Rs. 7,17,951 – 98% of the funds received.

Project Director does not sign the vouchers to approve each expenditure.

WHI maintains separate bank accounts for the TI and Social Marketing. The Project Director and Treasurer of WHI jointly operates the bank accounts.

All cash transactions are below Rs. 5,000 and the Cash-in-Hand is kept to the minimum of Rs. 3,000.

### Competency of the project staff

- Project Manager

Project Manager is a post-Graduate (MA) with 4 years experience in WHI TI project. He knows the proposal, quarterly and monthly plans are in place. He manages the Accountant’s and M&EO’s duties in their absence. He has knowledge about program performance indicators, conduct review meetings, visits the ORWs in the field to support them.

- Counsellor

The Counsellor is a post-Graduate in Social Work with 2 years experience as Counsellor in WHI TI project. She has sufficiently clarity on risk assessment and risk reduction, knowledge on basic counselling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages.

- ORW

The 5 ORWs has good relationship with the target population and other stakeholders like the labour contractors, Labour Officer, Service outlets, etc. Their outreach plans are vague, and is not based on a hotspot analysis. They have sufficient knowledge about STI symptoms, and importance of RMC and ICTC testing.

- Peer Educators

6 out of the 9 Peers represent the source States of the migrants. Their involvement has reduced with the withdrawal of honorarium. Currently they help the ORWs to gather the migrants for group meetings and other common programmes. Some of the PEs keep a stock of condoms to be purchased by the migrants.

- M&E Officer

The M&E Officer is a post-Graduate in Social Work and is working in the WHI TI project and M&EO for the last 2 years. She is on leave due to pregnancy at the time of evaluation. The Project Manager vouches for her capability as an M&EO.

### Outreach activity

Outreach activities of the ORWs result in the uptake of services through the medical camps.

### Services

The migrant population is happy with the services for STI care and ICTC support provided through the Government Hospital and Medical College Hospital

### Community involvement

The community of migrants have least involvement in the TI programmes facilitated by the project.

### Commodities

Social Marketing Condoms are available in sufficient quantity through the 20 outlets (petty shops and Peer Educators).