### Confidential

## Annexure C

EXECUTIVESUMMARY OFTHE EVALUATION

WHI Migrant Suraksha Project, Thiruvananthapuram

Profile ofthe evaluator(s):

| Name of the evaluators | Contact details with phone no. |
| --- | --- |
| John T Samuel | johntsamuel@gmail.com +91 944 656 9319 |
| Shiju Samson | 9745591965 |
| Kaveesher Krishnankutty, TSU | kaveesher@gmail.com +91 954 445 2680 |

| Name ofthe NGO: | Women Empowerment and Human Resource Development Centre of India (WHI) |
| --- | --- |
| Typology of the target population: | Migrant |
| Total population being covered against target: | 7635 /10000 |
| Dates of Visit: | 01 – 02, February 2016 |
| Place of Visit: | Thiruvananthapuram |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 67.2 % | B | Good | Recommended for continuation |

Specific Recommendations:

- The Project Director should record her monitory interventions during monthly meetings.

- The outreach plans should be specific. The plans of the ORWs should specify

  - STI care follow-up and ART follow up, and

  - Details about the Group Sessions (topic, resource person)

- The number of migrants availing ICTC service is to be increased.

- Peer Educators with leadership capability should be identified in sites where there are no PEs.

- Project Management Committee is to be constituted at the earliest.

- Festival days of the migrants should be utilized as Congregation Events of the project

Name of the evaluators	Signature

| John T Samuel |  |
| --- | --- |
| Shiju Samson |  |