Reporting Format-B					Annexure: B

Structure of the Detailed Reporting format

### (To be submitted by Evaluators to SACS for each TI evaluated with a copy NACO)

LISS INDIA, Ernakulum

LDTD intervention

Introduction

- Background of Project and Organization

LISS INDIA (Legal Industrial and Socio educational Society of India) is a Charitable Organization working for the welfare of the under privileged people, women, children and unemployed youth. LISS INDIA  was established in the year1995. The experience we gained throughout these years helped us to expand our field of activity to all shears of social and community development. Liss India trust on participatory development and involve the people from the planning stage to the evaluation stage of our programs. It encompasses tribal & rural areas schools and colleges, promotion of Reproductive and Child Health (RCH), Prevention of RTI/STI and focus on Family counseling to help the needy people.

- A brief history of TI intervention

- Since October 2011 onwards the project working as a TI partner with Kerala AIDs Control Society. Cochin in Ernakulum district is a major economic and trade Centre of Kerala. Truckers passing through Ernakulum district transports Timber, Cashew, Coal, Petroleum Products etc. The Micro Level Planning (MLP) report categorizes the Transshipment Locations (TSLs) around Ernakulum district as under the category B. There are 4 identified trucks halting area in Ernakulum TSL and these are Ambattukavu, Thaikkavu, and Kalamassery & Perumbavoor. The Truckers TI managed by the LISS India (Legal Industrial and Socio educational Society of India) since October 2011, has an annual denominator of 10,000 long distance truckers flows primarily from Tamil Nadu, Andhra Pradesh, Karnataka and certain northern states.

- The Current Project’s Target is either 40,000 new truckers or 10,000 new truckers and their repeat contact for four times in a year.   As denominator Proposed target for 2014 -2015 & 2015- 2016 the number of Truckers to be covered 40000 per year The program envisages resource and technical support from KSACS and TSG to achieve the project objectives through the structured targeted interventions. The program planned with 9 staff members (including project director and 2 part time doctors) & 10 Peer Educators and a total annual budget outlay of Rs. which ensure 10,000 truckers and helpers passing through the area are provided with the project specific services for four times annually.

- Name and address of the Organization

LISS INDIA SURAKSHA Trucker Project

House No: 27/1133,

Opp. Vimalagiri Public School,

Kothamangalam,PIN:  686691

- Chief Functionary:			        Dr LISSY JOSE

- Year of establishment                         1995

- Year and month of project initiation:   2011

- Evaluation team                                  JOHN CYRIL

NIKHIL

- Time frame                                         11th and 12th   February, 2016

### Profile of TI

(Information to be captured)

  - Target Population Profile:               TRUCKERS

  - Type of Project:                               Bridge population

  - Size of Target Group(s)                    40000

Sub-Groups and their Size

Target Area -                   Kalamassery, Thaikkavu,Ambattukavu, Perumbavoor

### Key Findings and recommendations on Various Project Components

- Organizational support to the programme

Legal Industrial and Socio educational Society of India ( LISS INDIA) is a reputed NGO in kerala with laid down policies and sustainable programmes being implemented for the last  16 years. As part of its plan to widen its horizons and diversify its interventional areas the NGO took up TI project joining hands with kSACS. LISS INDIA visualizes sustainability of the program through handholding with line departments and tapping the redundant resources which will be streamlined to halt and reverse the deadly epidemic among truckers.

LISS INDIA has planned strategic level implementation for effective monitoring of the program.. The support of the director in Advocacy initiatives is well appreciable.

Organization is utilizing its reputation in society to leverage the activities of the TI program and which has also supported the intervention in dilemma situations

The director monitors the project activities by her physical presence in the meetings held especially it was visible in the advocacy initiatives of the intervention.

### Organizational Capacity

  - Human resources:

The project is having the below tabled staff pattern

| SL NO | Position | Sanctioned | Existing |
| --- | --- | --- | --- |
| 1 | Project Manager | 1 | Nil |
| 2 | MEA | 1 | 1 |
| 3 | Counselor | 1 | Nil |
| 4 | Health Educators | 4 | 4 |
| 5 | Peer Educators | 10 | 10 |

The organization is having HR policy and the appointment letters were issued along with detailed job descriptions to the staff and project and properly updated. . Attendance and Leave file is maintained by the project but PE attendance register is not maintained by the TI.

It was observed that staff turnover is affecting the TI in a negative manner  disturbing  the   work equilibrium especially the turn over regarding  core staff. It should be mentioned that in   the absence of the PM and Counselor the MEA in charge is managing the TI in an appreciable way. The organization is helpless as due to fund crisis the vacant posts were instructed to be continued without positioning them.

  - Capacity building:

During the discussion with staff and PEs it was understood that induction training and regular technical inputs were given to the staff . PE training needs to be more focused as the PE knowledge enhancement was found weak.  The same could be verified with supportive documents.

Training  is provided not according to a laid down plan but it is provided as  for all categories. Staffs are deputed for all training programmes organized by KSACS – STRC. Input sessions are conducted for staff but PEs training need be more focused. During the interaction with PEs it was also  observed that only  input sessions were given during the PE meeting and no separate  training given to the PEs with separate module and purpose.

Regarding training the organization has to develop a specific plan on assessment of training needs for the staff and PEs.

  - Infrastructure of the organization

Considering   the difficulty to identify an office space within the limited budget in the city of Ernakulum, the organization has taken good effort to identify the Project office near the National Highway itself near the truckers halting point itself. DIC of the intervention is established at Perumbavoor

In the project office DIC is functioning. Static clinic also is set up in the office. Limited space available has been fruitfully utilized.

The crisis in budget is affecting the intervention to a good extent. The NGO is supporting the organization for remittance of rent in crisis situations. The budget needs to be expand regarding rent as this will enable the intervention to access a more suitable space for the intervention very near to the Transporters office where the truckers could be mobilized more easily and effectively

  - Documentation and Reporting:

Documentation needs to be more focused as it can greatly increase the quality             of the intervention. The staff turnover especially the core staff has affected the documentation process. But it is appreciable that the MEA and the team has satisfactorily accomplished the documentation even in the absence of the PM and the counselor.

The project maintains most of the document and the PM in charge is signing in the documents but comments for improvement were not visible in the documents. There are mismatches in ICTC test physical verification and MIS reporting.

Staff meeting is the main tool for monitoring. Program level achievements are reflected in the staff review minutes. The quality of the staff meeting minutes needs enhancement as the gaps found out and the measures taken to bridge the gap should be reflected in the staff meeting minutes. The project staff is supposed to explore and utilize the reports and documents for more effective planning and monitoring of the intervention. The TI is submitting to KSACS the relevant documents properly furnished.

### Program Deliverables Outreach

- Line listing of the HRG by category.

Line listing is done and kept updated in excel format and the same is retrievable when needed. Registration Formats has been filled and filed for all the registered LDTD covered under the intervention. Registration process was done as per instruction, through STI clinics/camps and counseling.

- Micro planning-  ORW files available in which the tools for planning were applied are filed. Translation of the plan to activity needs to be more strategic as a gap is observed in the same. This gap is reflected in the low percentage regarding service intake.

- Coverage of target population- The TI has covered 45443 against 40000, 113%  in 2014-15 and 34515 against 33330 , 104% in 2015-16 . During the First year the TI has achieved 114% of the target while in the second year a gap was observed compared to the coverage of 2014-15.

- Outreach planning – Outreach planning is done by the TI maintaining the needed quality of the same and documented. But the conversion of planning to implementation is having some drain as there is huge gap between coverage and service intake. Tis needs to be focused as the covered truckers must be converted to services for effective implementation of the program. Service conversion is the core objective of the intervention which should be given importance. The TI must derive strategies as if to ensure that the covered truckers are converted to services.

- PE: HRG ratio, PE:migrants/truckers

The TI is having 8 PEs against the sanctioned 10. It is suggested to fill all the PE post for more effective intervention. Only 6 PEs could be met during the evaluation process.

The Lack of PE incentive that exists as a reason of Fund crisis is affecting the intervention to a great extent

- Documentation of the peer education

There  are both literate and illiterate PEs . Maintaining of PE diary needs more focus as it was not seen. Needed forms are completed with the help of ORWs .

- Quality of peer education-

The persons working as PEs are ex truckers . This helps to a great extent in delivering the message of HIV  prevention. The quality of Peer education needs enhancement. The way of delivering the message regarding HIV prevention needs to be overlooked by the TI as the effectiveness of the same should be increased. The PEs distribute condoms to the truckers and motivate and channelizes the truckers for STI screening and ICTC testing.

It was observed that the motivation level of PEs is showing a downward trend due to lack of incentive due to fund crisis. It is to be noted that the crisis regarding fund is dragging the quality of the TI as it mainly affects the motivation of Peers which constitutes a major factor for the success of the intervention.

- Supervision-

Weekly review meetings and field monitoring are the major mechanisms for supervision. The ORWs are expected to supervise the PEs in the field. The peer educators claim that they get necessary guidance and  support from the ORWs.

Project team is well aware of the supervision mechanism to be followed in the project.

### Services

- Availability of STI services.

Static clinic is established in the project office but is non functional for more than 6 months. It was shared by the staff that  it was due to lack of fund that the functioning of the static clinic was disturbed and gradually ceased.

Measures should be taken by the TI staff to make functional the Static clinic. The TI could have utilized the support of external stake holders for mobilizing the cost of conducting static clinic. The NGO is also supposed to utilize its resources and linkages for effective running

The dysfunctional state of the static clinic has affected the performance of the intervention to a great extent. As the static clinic is operating close to the halting point and in the midst of a number of transporters office hundreds of truckers would have utilized the services of the clinic if it was functional

Two doctors are linked to the STI services.  In the first year of the intervention 6206 truckers have availed STI services and in the second year 2570 truckers only have utilized the service. A fall in STI service is vivid from the data available.  While in the first year the TI was able to achieve 100% of the target in the second year the STI services was drastically down bringing down the figure to half of the previous year’s achievement.

- Quality of the services-

Clinic is well set up in the project office with all equipment’s and required infrastructure but  is nonfunctional for more than six months. Project office is situated in a good location

102 truckers were treated for STI in the first year and 78 treated in the second year of the intervention. The shortage of STI medicine is affecting the quality of the services.

Privacy is maintained in the clinic.

- STI drugs.

A procurement system exists within the TI and the TI is adhering to its norms and drugs re available with the TI. The TI is making use of revolving fund for purchase of drugs but no drugs was purchased in the current year

- Quality of treatment in the service provisioning-

The TI has registered with ART 5 positives out of the eight positives that it identified within two years of intervention. It could be considered as an achievement as registering the positive truckers in ART center is a difficult task .

ICTC achievement has come down which should be taken seriously. The first year witnessed 75% testing and this underwent a   drastic fall in the second year of the intervention bringing down the figure to 25%.

- Documentation-

All documents related to STI referral and treatment is kept in the office and updated. Medicine stock register is maintained by the project. Documents related to static clinic are not updated as the clinic is nonfunctional

- Availability of Condoms-

TI is distributing SM condoms through the 49 outlets it has formed as part of the intervention. Condom register is maintained by the TI. Out of the total condom outlet s 8 comes under traditional and 41 are nontraditional. The TI sold 11901 condoms. 10050 condoms were distributed through traditional and nontraditional outlets and 1851 condoms were sold directly to truckers during  medical camps.

- Linkages and Referrals

Project has established good rapport with various service centers. Timely referral is done for ART, STI and ICTC. Follow up of ART cases is done by the TI.

PE reviews needs to be more focused as a gap was observed in the same. Effective PE reviews can very well change the implementation quality of the TI. Knowledgeful and quality PEs can only deliver a good project quality.

### Community participation

Community participation apart services needs enhancement. Some sort of special interventions is the need of the intervention for collectivization activities. Collectivization activities must be strengthened as this will increase the mileage of the intervention.

### Linkages

### Project has established good linkages with various service providers. This was visible in the FGD conducted. The truckers expressed their happiness regarding the services rendered to them. During the interaction with ICTC centers, doctors and other stake holders the same feeling was shared. They are happy regarding the services provided by the project and the motivation and support provided by the intervention.

### Financial systems and procedures

  - Systems of planning:

- The planning system is based upon the monthly meetings conducted. Gaps were found in the monthly meetings that needs to be bridged.

  - Systems of payments

All payments were settled by cheques. Voucher prepared by accountant is verified by project manager and approved by project director.  The cheque issue register is to be kept in the office for verification which was in the NGO office during the time of evaluation as according to the staff.

- Systems of   procurement.

The NGO is adhering to the procurement system of KSACS. The project has not purchased any assets during the year.

- Systems of documentation-

Cash book maintained in daily basis. Bank reconciliation is done and SOEs are submitted to KSACS on   monthly basis. Bank account of the project is operated by LISS INDIA. The hard copy of SOEs are filed in the project office.   Cash in hand is observed as below 5000. KSACS audit reports are properly filed. The report of the  previous audit conducted by KSACS on August 2015  was not given to the TI and hence the copy of the same was not filed in the TI.

### Competency of the project staff

Project Manager

Project Manager post is vacant in the TI for more than a quarter. The TI is unable to  absorb the post due to fund restrictions. The work of PM is executed   by MEA

ANM/Counselor

The post of counselor is vacant in   the TI. The TI is unable to fill the post due to fund restrictions imposed.

ORW

The TI is having 4 ORWS against the sanctioned number of 4 . ORWs of the intervention are committed and having good knowledge regarding the intervention. The ORWS are skilled to communicate with the truckers in their own language. One ORW is the   joint secretary of district transporters union. This linkage is helping the TI to establish good networking with the transporters and through them to the truckers.

Planning needs to   be more focused as it can produce more effective results regarding the intervention.  PE meetings are conducted by the ORWs and it is observed as a very good platform for knowledge transmission regarding the intervention.

VIII h. Peer Educators in Truckers Project

The TI is having 10 PE position against the sanctioned 10. Majority of the PEs are ex truckers or is working in association with the transporters office. Here it is to be noted that the transporters office is a good catchment area of truckers. The fund crisis due to which the PE incentive is blocked is affecting the motivation level of PEs to a great extent.

The PEs are having good knowledge regarding the intervention.

Condom demo was done by the PEs and it was as per the demo steps to be followed. The PEs are active in  Mid media activity  . The mid media activity of the intervention needs to be more focused. Truckers are more interested in mid media activities than classes. The TI can mobilize the support of the colleges and clubs surrounding kalamassery which is a halting point for truckers.

M&E officer

MEA is handling the responsibility of the PM. It is appreciable that the MEA is maintaining the   equilibrium of the intervention even in the absence of Project manager and the counselor. MEA presents analysis of data during the monthly staff meeting. Record of the same was documented in the staff meeting minutes.

### b. Outreach activity in Truckers and Migrant Project

ORWs and PEs are having good knowledge of the intervention and they have worked for converting the planning to services. Gap has occurred in the transformation regarding contacts to services. Service figures of the projects tend to be low especially HIV test where as the sessions conducted Vs planned is not having such a huge gap.  Effective implementation must be followed where planned services must be actually achieved. The limitation of the TI as absence of PM and Counselor and also the lack of funds must be taken for consideration.

### Services

### It is observed that a downward trend has happened regarding quantity of service intake.  ICTC has dropped from 75% in the first year to 25% in the second year. STI services drastically dropped  from 89% to 44%. The reason for STI services not happening is conduction of health camps showing a downward trend of 87% of the target in first year to 35% in the second year. ICTC kit shortage and lack of fund for STI screening may be cited out as one of the important reason for non achievement of targets.

### The TI could have derived alternatives for STI screening as sponsorship from transporters and other stakeholders. The influence of LISS INDIA  being such a credible NGO with wide linkages and networking could be utilized for the same.

### Community involvement

### Community involvement is happening in the intervention but needs more focus

### Commodities

### The TI sold 11901 SM condom pieces during 2015 April to 2016 February . 10050 condoms were distributed through TOs and NTOs and the rest of the SM was sold directly to the truckers during the health camps conducted as part of the intervention.

### Enabling environment

### Advocacy initiatives are supported by the community as mobilizing of truckers who are not currently in the service net of the TI is also happening. The efforts from the side of the TI for community involvement is happening. Coordination committee helps to provide space for conducting camps in broker offices and this helps in increasing the footfall regarding STI services. The information regarding medical camp will be sticked on the broker offices and so the brokers can shift their duty to avail the service of the health camp. This has helped in the STI camp drop in.  It is appreciable that the PD is participating in th advocacy meetings conducted by the TI. The TI has conducted advocacy initiatives with the municipality which has helped in making the intervention more vibrant and gain more acceptance among the truckers.

### The TI as part of its advocacy initiatives was awarded with an order from Kalamassery municipality to conduct the programmes of Truckers intervention inside the premises of kalamassery municipality. It is observed that the TI has developed a coordination committee with Cochin lorry agents association. Programmes in association with Apollo health care Centre and ST Joseph transport needs special mention.

- Social protection schemes / innovation at project level HRG availed welfare schemes, social  entitlements etc.

Focus needs to be provided by the TI  in this area

- . Best Practices if any

No such replicable best practice observed.

### Confidential	Reporting Form C

## Annexure C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| JOHN CYRIL | 8589034341 |
| NIKHIL KS | 9961137848 |
| Officials from SACS/TSU (as facilitator) | GEORGE KURIAN |

| Name of the NGO: | LISS INDIA |
| --- | --- |
| Typology of the target population: | TRUCKERS |
| Total population being covered against target: | 40000 |
| Dates of Visit: | 11TH AND 12TH FEBRUARY 2016 |
| Place of Visit: | KALAMASSERY PROJECT OFFICE, GDEDESOM |
|  | DESHOM, MOBILE ICTC TESTING |
|  | PREMIER CONDOM OUTLET, |
|  | PETTY SHOP CONDOM OUTLET, kalamassery |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific recommendations

The TI has scored 67% marks in the evaluation and comes under category and is

recommended for continuation.

Name of the evaluators	Signature

| JOHN CYRIL |  |
| --- | --- |
| NIKHIL KS |  |