## Programme delivery
Targeted Intervention -Annual Evaluation Tool (FSW/MSM /IDU TIs more than 5 years)-2012
Name of the NGO:Voluntary Social Development Organization |  |  |  |  | District:South |  | State:Tripura
Program Delivery
Sl.No. | Indicators | Typology Applicable | Target | Achievement | Key Questions | Methodology to be adopted | Assessment Scores |  |  | Score Resulted | Explanation for score
S. no | [6 empty] | 1(Poor) | 2(Average) | 3(Good)
[7 empty] | 1 | 2 | 3
SECTION 1: BASIC SERVICES
OUT REACH
1 | Individual HRGs tracked for project services by peer educators | FSW/MSM/ IDU | 100 % of active population | Target population - 483 Active population- 489 | Whether PEs are maintaining the weekly planning and activity sheet (Format B/B_1) as per NACO's guideline. | Verify the master register of HRGs / line listing /weekly format B/B_1 of the last one quarter. Meeting with PEs should be conducted. | Form-B/B_1 is maintained by PEs but no prioritisation of HRG done by ORWs based on risk and vulnerability data. | Form-B/B_1 is maintained by PEs and proper prioritisation of HRG done by ORWs based on risk and vulnerability data. | Form-B/B_1 is maintained by PEs and PEs are able to explain the use of risk, vulnerability, condom & needle/syringe demand data during BCC, IPC and service delivery. Prioritisation of HRGs done and formats are properly filled & understood by each PEs. | 2 | Form B is maintained by PEs and prioritisation done by ORWs
2 | Out reach plan in place at project level. Micro plans are available for each hotspot . Individual HRG not taking any project services in the last 2 quarters has been identified and micro plan highlighted the same. | FSW/MSM /IDU | Outreach and micro plans should be available for all hotspots | Outreach plan and microplan in place | Verification of outreach plan and micro plan. The micro plan is being used to follow up pending ICTC, RMC and Syphilis testing cases. Updation of Risk, vulnerability and condom demand needle/syringe data on quarterly basis. | Interview with ORWs and PEs. Verification of micro plans and outreach plans during hotspot meeting with target group. | Outreach and micro plan in place but not in use. Individual HRGs are not tracked for RMC, ICTC, Syphilis testing. | Outreach and micro plan in place and the same is used by ORW and counsellor/ANM in delivering the project services. Individual HRGs are also tracked for RMC, ICTC, Syphilis testing. | Outreach and micro plan in place and the same is used by ORW and counsellor/ANM in delivering the project services. Individual HRGs are also tracked for RMC, ICTC, Syphilis testing. Risk, vulnerability and needle/syringe, condom demand data for individual HRG are updated on quarterly basis. | 2 | Outreach and Micro plans are in place and are used by ORW and counsellor to track individual HRG for service
3 | Registration of HRG against target | FSW/MSM /IDU | 100% | Target-483 Registered till date-1623 | All HRG should be registered by ORW. Format-A should be properly filled and master registration sheet completed and to be computerised | Verify the computerised master register of HRGs , line listing and filled format-A (data filled for all indictors) for all the registered HRGs. Check for Drop-out records and TI to provide explanation in case of less than 100 % registration. | 70-80 percent of the target HRGs registered. | 81-90 percent HRGs were registered against the target | Above 90 percent HRGs were registered. | 3 | The NGO has registered more than 100% of the target
4 | Percent of target HRG reached by the project (As per contract) during last one year | FSW/MSM /IDU | 100% of active population | Active population- 489 Contacted at least once in every month-484 | Average no. of HRGs were contacted at least once in every month with any or all project services by PEs during last one year | Verification of project proposal, ORW's format-C and monthly CMIS report. At least 20% of the randomly selected HRGs of selected hotspots need to be verified during the hotspot visits.80% of the population and Line list ID numbers is to be constant. Cross verify with indicator for micro plan. Verify the remaining HRG taking services regularly by the TI. | 60-70% of active population were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | 71-80% of active population were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | Above 80% of active population were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | 3 | Almost 98% of the active population contacted at least once in a month
5 | Regular Contact - All services (No. of individuals target HRG contacted with any or all project services (atleast twice in every month in a gap of 10-15 days) during last one year . | FSW / MSM | 100% of active population | Active population- 489 Regular Contact-449 | Average no. of HRGs contacted at least twice in a month (in the gap of 10-15 days). The verification of STI, RMC, Individual tracking register, medicine stock, doctors payment register to be verified | PE form-B and ORW's format C . At least 20% of the randomly selected HRGs from randomly selected PEs need to be verified during above during hotspot visits. | 60-70% of target group are contacted regularly and provided project services by PEs . | 71- 80% of target group are contacted regularly and provided program services by PEs. | Above 80% of target group are contacted regularly and provided program services by PEs. | 3 | Almost 91% of the active population contacted at least once in a month
6 | Regular Contact - NSP (No. of individuals target HRG contacted with any or all project services - NSEP/BCC/IEC/Referral | IDU | 100% of daily and medium-high volume injectors | NA | Average no. of IDUs that were contacted at least 20 days in every month for the purpose of NSEP/BCC/IEC/Referral | PE form-B and ORW's format C and PE diaries . At least 20% of the randomly selected IDU need to be verified during above during hotspot visits. | 60-70% of target group are contacted at least 20 days in every month for the purpose of NSEP/BCC/IEC/Referral | 71-80% of target group are contacted at least 20 days in every month for the purpose of NSEP/BCC/IEC/Referral | Above 80% of target group are contacted at least 20 days in every month for the purpose of NSEP/BCC/IEC/Referral |  | NA
7 | Percent of new HRG covered through hotspots / DIC level meetings during last one year. | FSW/MSM /IDU | 100% of new HRGs registered | New HRG registered- 179 Attended field level meeting- 126 | Every month ORW / PE should conduct meetings at the hotspots / DIC at least twice in a month covering all the registered HRG. | Hotspot / DIC level meeting registers. PE / ORW dairies. Verify registers. The same should be verified during hotspot visits | Meeting attendance register indicate that 50-60% of newly registered HRGs participated in atleast 3 meetings. Minutes of the meeting to be reviewed qualitatively in narrative reports. | Meeting attendance register indicate that 61-70% of newly registered HRGs participated in atleast 3 meetings. Minutes of the meeting to be reviewed qualitatively in narrative reports. | Meeting attendance register indicate that Above 70% of newly registered HRGs participated in atleast 3 meetings. Minutes of the meeting to be reviewed qualitatively in narrative reports. | 2 | Almost 70% of the newly registered attended field level meeting
8 | Field visit by ORWs | FSW/MSM /IDU |  |  | ORW visiting the field minimum 5 days in a week and providing supportive supervision to all the PEs of his/her areas for effective delivery of project services by PEs to HRGs and to ensure all the PEs have required skills. | ORW diaries, weekly staff meeting minutes, ORW movement plan/register and Form D. The same should be verified with the community and stakeholders during the hotspot visits | All PE have been met at the hotspot and provided support by ORW at least twice in a month | All PE have been met at the hotspot and provided support by ORW four times in a month | All PE have been met at the hotspot and provided support by ORW more than four times in a month and all hotspots are covered in a month | 1 | It has been understood that the ORWs met all the Pes at the hotspot 2 times in a month and provided supportive supervision
CLINIC SERVICES
9 | Established STI clinic / PPP /Government STI clinics linkages | FSW/MSM /IDU | STI Services should be established | STI services through linkages with Gvt STI clinic /PPP | Set-up of STI clinic / PPP/ linkages developed with DSRC/Govt. Hospital as per NACO guideline. | Observations should be made based on NACO guidelines. Project STI Clinic, PPP registers and payment registers to be verified. | Project STI clinic / PPP linkages has been set-up but not as per NACO guideline. | STI clinic / PPP linkages in place but registers / patient card (Network clinic format) are not maintained as per NACO guideline at clinic | STI clinic / PPP linkages in place and requisite registers / patient card (Network clinic format) are maintained at clinic. | 1 | it was understood there is a linkage with STI clinic /PPP but not as per guideline
10 | HRG attending STI clinics (Project based/ PPP /Government STI clinic) are counselled | FSW/MSM /IDU | 100% of clinic attendees | HRG visited STI clinic- 448 | No. of HRG visiting to clinics are counselled. | Counselling registers, STI register and monthly CMIS report. Interaction with STI providers/counsellors/ANM | 60-70% of HRGs attending STI clinic were counselled. | 71- 80% of HRG attending STI clinic were counselled. | Above 80% of HRG attending STI clinic were counselled. | 2 | It was estimated that 70% of the HRGs visiting STI clinic are counseled from counsellors book.
11 | All HRG line listed during last one are counselled at project level | FSW/MSM /IDU | 100% linelisted | Conuseled 478 | All HRGs are counselled on risk and vulnerability by counsellor / ANM in last one year. | Counselling registers, STI register and monthly CMIS report. | 60-70% of HRGs were counselled by counsellor / ANM | 71-80% of HRGs were counselled by counsellor / ANM | Above 80% of HRGs were counselled by counsellor / ANM | 3 | Above 80% popualtion are counseled in the last year
12 | HRGs attending regular medical check-up (including symptomatic treatments and visit to clinics) in last one year | FSW/MSM | 100% of active population | HRGs attended RMC 301 | No.of HRGs attending regular medical check-up at least two times during last one year | PEs Form-B/B_1, STI registers / tracking sheet, ORW form-c field diary, referral slips/registers, Payment register/slips of PPP doctors and monthly CMIS report | 60-70% of the individual HRGs had undergone for RMC twice in past one year. | 71- 80% of the individual HRGs had undergone for RMC twice in past one year. | Above 80% of the individual HRGs had undergone for RMC twice in past one year. | 1 | 61% of the active population attended RMC twice in last one year
13 | Newly registered asymptomatic HRGs provided presumptive treatment (PT) during last one year | FSW/MSM | 100% of newly registered HRGs | New HRG registered- 179 and PT -131 | No. of new HRG registered during last one year and received PT | STI CMIS reports, Referral register, referral slips | 50-60% newly registered HRG provided PT. | 61- 70% newly registered HRG provided PT . | Above 70% newly registered HRG provided PT. | 3 | 73% of the Newly registered HRGs had been given PT
14 | Percent of HRGs tested for Syphilis | FSW/MSM /IDU | 50% of line listed HRG | Active population -489 and tested syphilis -447 | Percent of individual HRGs tested for Syphilis during last one year | STI CMIS reports, Referral register, referral slips, individual tracking sheet | 30-40% of HRGs underwent Syphilis test | 41-50% of HRGs underwent Syphilis test | Above 50% of the HRGs underwent Syphilis test | 3 | 91% population has taken syphilis test
15 | Percent of individual HRGs tested for HIV during last one year | FSW/MSM /IDU | 100% line listed HRG | Active population -489 and HIV test -447 | No. of line listed individual HRGs tested for HIV during last one year | Referral registers, referral slips and PE form-B/B_1 and ICTC data. Verify the referral slips signed by the ICTC counsellors and POD no. provided. | 50-60% of the HRGs underwent HIV test during contract period | 61-70% of the HRGs underwent HIV test during contract period | Above 70% of the HRGs underwent HIV test during contract period | 3 | 91% of the active population are tested for HIV
16 | Percentage of HRG tested positives are registred in ART | FSW/MSM /IDU | 100% of HRG tested positive | HIV positive -0 and ART linkages- 0 | No. of positive HRGs registered in ART during last one year | Verify with the ART centre, referral register | 50-60% of the total identified positive HRGs linked to ART | 61-70% the total identified HRGs linked to ART | Above 70% HRGs linked to ART | 1 | HIV + is not identified in the last tenure
17 | Abscess Management | IDU | HRGs reported with abscess | N/A | Proper dressing and treatment for all abscess cases under aseptic conditions at the clinic and through outreach | Clinic records, inspection of DIC, and interaction with clients | Aseptic abscess management services established but available to limited clients for limited time | Aseptic abscess management services established and available to most clients for extended time | Aseptic abscess management services established and available to most clients for extended time + Abscess management by nurse and ORWs in the field
COMMODITIES
18 | Individual HRGs are getting condoms as per condom requirement analysis | FSW/MSM /IDU | 100 % of distribution against condom demand | Condom demand - 64118 and distribution -57599 | Condom distributed should be as per demand/requirement gap analysis. | Verification of individual peer form "B/B_1" and ORW form "C". Verification to be done during hotspot visit | Condom gap analysis done and 60- 70% of individual HRGs distributed condom against the requirement. | Condom gap analysis done and 71-80% of individual HRGs distributed condom against the requirement. | Condom gap analysis done and above 80% HRGs were provided condom as per the requirement. | 3 | The NGO has done condom gap analysis and distributed 90% of the demand generated
19 | Individual HRG are getting Needle and Syringes as per N/S demand analysis | IDU | 100 % of distribution against N/S demand | N/A | N/S distribution should be made as per demand/ requirement gap analysis. | Verification of individual peer form "B_1" and ORW form "C". Verification to be done during hotspot visit | N/S gap analysis done and at 60-70% of individual HRGs distributed against the requirement. | N/S gap analysis done and at 71-80% of individual HRGs distributed against the requirement. | N/S gap analysis done and Above 80% of individual HRGs distributed against the requirement. |  | N/A
20 | NSEP: Needle/Syringe Return Rate | IDU | 80% of distributed needles/syringes should be returned / collected after use | N/A | Percentage of needles/syringes distributed to IDUs being returned / collected after use for safe disposal | Verification of PE & ORW diary, DIC record, disposal register | 40-50% of used needles/syringes being returned/collected for safe disposal | 51-60% of used needles/syringes being returned/collected for safe disposal | More than 60% of used needles/syringes being returned/collected for safe disposal
21 | Safe Waste Disposal | IDU | 100 % of returned needles/syringes being disposed off safely | N/A | Whether NACO waste disposal guidelines are being followed for the safe disposal of returned/collected needles/syringes | Verification of PE & ORW diary, DIC record, disposal register, photographs | Waste Disposal mechanism in place but only collection of needles/syringes being done as per NACO guidelines | Waste Disposal mechanism in place but only collection and disinfection being done as per NACO guidelines | Waste Disposal mechanism in place: collection, disinfection and final disposal being done as per NACO guidelines
18 | Availability of drugs for STI treatment and Abscess management, with a buffer stock management in place. | FSW/MSM /IDU | 3 months buffer stock based on average monthly consumption |  | No. of times STI drugs, have been purchased/supply during the contract period. Was there any stock-out of commodities reported during contract period. If the supply is an issue from SACS, the indicator to be verified for the period when stock was available. | Verification of stock & distribution register and vouchers. Ask question about buffer stock system to project manager/ANM/Counsellor. | Reported stock-out of STI drugs during contract period | No stock out reported during contract period but buffer stock system was not followed as per guideline | No stock out reported during contract period and buffer stock system was maintained as per guideline.
SECTION 2: SUPPORT SERVICES
22 | Condoms distributed through social marketing | FSW/MSM /IDU |  |  | Condoms socially marketed by the project, an average of last 6 months to be taken. | Verification of register for condom Social marketing, stock registers, PEs/ORW daily formats and CMIS monthly reports. | Social Marketing of condoms carried out on need based. | Upto 15% of condom demand of the project met through social marketing | More than 15% of condom demand of the project met through social marketing | 1 | CSM carried out need based
23 | Identified cases from HRG were linked for TB to DOT centre (RNTCP) during the contract period | FSW/MSM /IDU | 100% of all identified cases of TB | TB-0 | No. of target group member linked to DOT centre during the contract period, detected for TB. | Verification of registers, general treatment register, referral slips/register | 40-50% of the total identified HRGs linked to DOT | 51-60% of the total identified HRGs linked to DOT | Above 60% HRGs linked to DOT | 1 | TB cases not identified as few are referred for screening
ENABLING ENVIRONMENT
24 | Advocacy meeting with key stakeholders (health service providers, Police personnel, ICTC/ART centres, PRI, Social Welfare Dept., Gate Keepers, etc.) | FSW/MSM /IDU |  |  | Advocacy meeting held with key stakeholders at various level with plan. | Verification of minutes, meeting registers and MIS reports | Advocacy meeting are conducted on need based | Advocacy meeting conducted at all levels as per plan without proper documentation and follow up | Advocacy meeting regularly conducted as per plan at all levels with proper documentation and follow-up | 1 | Advocay meeting was conducted as need based
25 | Crisis management team in place | FSW/MSM /IDU | To be addressed 100 % cases |  | Set up of crisis management team at TI level, No. of cases right of violation reported and solved within 24 hours | Advocacy activities/ Crisis management or meeting register/no. of harassment cases reported (If no such cases reported then verify during interaction with HRG whether they have faced any such harassment/violence/ crisis during the contract period). To review supporting financial documents. | Crisis management team addressed 60% of the cases all reported during last one year | Crisis management team addressed 61-70% of the cases reported during last one year. | Crisis management team addressed above 70% of the cases reported during last one year | 1 | It was understood that the TI has no focus on crisis issues
COMMUNITY MOBILISATION
26 | Collectivisation (No. of HRGs part of committees /CBOs / support groups) | FSW/MSM /IDU |  |  | No. of HRGs are part of committees /CBOs / support groups out of the total registered HRG with the project | Verification of records/minutes of Committees /CBO / support groups meetings against the HRG registration document (If CBO do not exist with TI then HRG representation in the committee should be considered) | At least30 % of the (registered HRGs) are part of Committees /CBO/ / support groups | 30- 50% of the registered HRGs are part of Committees /CBO/ support groups. This should also include at least 30% are new HRGs registered more than 3 months | More than 50% of the registered HRGs are part of Committees /CBO / support groups. This should also include at least 50% are new HRGs registered more than 3 months | 1 | Committees are not properly formed
27 | Events held on regular basis | FSW/MSM /IDU |  |  | No. of events organised during contract period with 25%-50% of the HRGs registered. | Events register, minutes of the monthly meetings with attendance sheet, CMIS monthly report, Verification to be done during hotspots visits | 25-50% of the registered HRGs attended /participated in the events | 51-75%of the registered HRGs attended /participated in the events | More than 75% of the registered HRGs attended /participated in the events | 1 | it was understood that the TI managed some 30% HRGs to attend
Community response to the Program Services
28 | Project is adhering to confidentiality norms. | FSW/MSM /IDU |  |  | Privacy in the clinic and information shared in the counselling sessions are maintained and not shared. | FGD with the 10-15 community members (suggested to conduct at the field). | Between 50-80% participants are not sure of confidentiality norms being adhered at the project level | Between 81 to below100% of the participants are satisfied with privacy and confidentiality at the project level. | 100% of the participants are satisfied with privacy and confidentiality at the project level. | 1 | HRGs are not aware about the confidentialty
29 | Community perception on project services | FSW/MSM /IDU |  |  | Are the community members satisfied with the available services and services meet their demands. | FGD with 10-15 community members (suggested to conduct at the filed level). | Between 50-80% of the participants are convinced with the project services | Between 81 to belwo100% participants are satisfied with the project services. | 100% of the participants are satisfied with the project services. | 1 | almost 50% HRGs are convinced
30 | Adequate supply of commodities(Condoms/Lubricants /Needle and Syringes, drugs) | FSW/MSM /IDU |  |  | Condoms, needle & syringe for IDUs and Lubricants for MSM provided by Project | FGD with 10-15 community members (Suggested to conduct at the filed. If the project is composite conduct the FGD separately). | Between 50-80% participants sure of confidentiality norms being adhered at the project level | Between 81 to belwo100% respondents reported that they are getting the commodities as and when they demand. | 100% of the respondents reported that they are getting the commodities as and when they demand. | 1 | almost 50% HRGs are convinced
31 | Involvement of key stakeholders in programme monitoring | FSW/MSM /IDU |  |  | Ability of the project to involve stakeholders like police, civic health service providers, social development sector officials in addressing the issues relating to project services | One to one interaction with at least 3 stakeholders of the project. (suggested to conduct at the filed). | One stake holders participated in addressing the issues relating to project services | Two stake holders have said S/he has involved in addressing the issues relating to project services. | All the three stake holders have said that they involved in addressing the issues relating to project services. | 2 | Most of them said they are involved in the project
32 | Involvement of Counsellor / ANM | FSW/MSM /IDU |  |  | The counsellor/Nurse should be sensitive while addressing issues relating to community members. | FGD with the 10-15 community members (suggested to conduct at the field level). | Between 50-80% respondents reported that they are satisfied with the counsellor/ANM | Between 81 to belwo100% respondents reported that they are satisfied with the counsellor/ANM | 100% of the respondents reported that they are satisfied with the counsellor/ANM | 2 | Most satisfied with the counsellor
| SECTION 1: BASIC SERVICES | [6 empty] | SECTION 1: TOTAL MARKS OBTAINED |  | 38
| SECTION 2: SUPPORT SERVICES | [6 empty] | SECTION 2: TOTAL MARKS OBTAINED |  | 11
| Total | [8 empty] | 49

## Org capacity
TI -Annual Evaluation Tool (FSW/MSM/IDU -TIs more than 5 years)-2012
Name of the NGO: Voluntary Social Development Organization |  |  | District: South |  | State:Tripura
Organisational Capacity
Sl.No. | Indicators | Mean of verification/observations | Areas of assessment | Score Resulted | Explanation for score | Remarks
1 | All project staff and PE positions have been filled as per project proposal | All NGOs contracted has to appoint the staff within three months from signing of contract. Project proposal, appointment letters / staff attendance sheet during the last year (If a position has been vacated and not filled in within 2 months, give "0" mark for this indicator.) | Recruitment system | 1 | As per proposal
2 | Staff turnover witnessed in the project during the contract period. | Attendance sheets /appointment letters. ( If there is more than 60% of project staff except peer educators have resigned during the year then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Institutional process | 1 | The organision has suffered one staff turn over | The accountant has been found to have joined in April 15
3 | PE turnover witnessed in the project during the contract period | Attendance sheets /appointment letters. ( If there is more than 20% PEs turnover during the contract period then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Administrative system | 0 | 25% Pes turned over has been recorded | Two Pes left the Job during this year
4 | 10% of the ORWs are from the community i.e. either the peer educators have been graduated to become ORWs or the community members are selected as ORWs | This process of selection of community members as ORWs should be atleast one year old. | Staffing | 0 | No orw is from the community
5 | Ratio of PEs to HRG ( a ratio of 1: 60 for FSW,MSM-1:40 for IDUs). | Line listing of HRGs and number of PEs/VPL on board. (A 20% Variation may be considered for HRG Pes ratio as per project proposal). | Staffing | 1 | PE and HRGs ratio are almost as per norms
6 | 50% of the peer educators belong to the age group below 30 years or should match with the high /medium risk HRGs linelisted by the programme | Interact with all the peer educators for core TIs . The peer educators should be recruited at least 6 months and are trained by the project. | Staffing | 0 | All Pes are above the age group of 30
7 | For each set of 250 HRG there is an ORW has been appointed | Registration documents, MIS reprts, ORW records. (A 20% Variation may be considered for HRG PEs/VPL ratio as per project proposal). | Staffing | 1 | As per norms
8 | Job description given to each project staff, atleast staffs are able to describe their job description and the same is reflected in their plans prepared for the programme during last 2 quarters | All project staff do have written job description or available at NGO level. If the programme manager and all ORWs are not able to describe their job responsibilities or the same is not reflected in their plans, the score should be '0' | Institutional Environment | 1 | verified
9 | Attendance/leave register maintained for the project staff | Examine the attendance register is in use/leave register available | Administrative system | 1 | verified
10 | Does the NGO management takes into consideration the community needs/resources into consideration while planning/delivering services through arrangements like availability of programme management body represented by community/ community consultations. | Minutes of the community consultation/ programme management body represented by community members should reflect that such process is at least more than 6 months old, otherwise the score should be '0' | Institutional visioning / shared responsibility. | 1 | the mangement body are involved in project level activities
11 | Induction training / orientation to PE and other staff has been completed by the TI project immedaitely after recruitment. | Training registers/ induction training report | Proper induction in place | 1 | verified
12 | The role of Governing Body members in addressing issues of crisis/stigma/discrimination faced by the community members by networking with stakeholders, by keeping well informed about the issues of HRGs | Meeting with at least 2/3 members of the GB and interview to focus on their role in the programme. Also meet at least the stake holders and assess the role played by the members. If oraganization not playe any role in addressing issues faced by HRGs, score should e '0'. | Understading of role of NGO in developing contusive environmrment. | 1 | The body members are well acquainted about the project
13 | The Project Director attended atleast 80% all the monthly meetings of the TI project duing the year. The PD has attended and initiated action against the areas of improvement based on the minutes. | Attendance of meeting registers and minutes of the meeting. Action taken report based on previous meeting. | Invovement of Project director in project activities. | 1 | verified
14 | Assets purchased under project is codified/marked | Assets register and purchase voucher (All the assets purchased under the project) | Proper assest maintance system | 1 | assets are codified
Total Score |  |  |  | 11

## Finance
TI - ANNUAL EVALUATION -2012
Name of the NGO: Voluntary Social Development Organization |  |  | District:South Tripura |  | State:Tripura
Evaluation Tool for Finance
Sl.No. | Indicators | Key Questions | Methodology to be adopted | Score |  | Score Resulted "0" for No "1" for Yes | Explanation for score | Remarks
|  |  |  | 1 | 0
1 | Budget Utilization | What is the percentage of budget utilized against the release of fund on the proposed activities | Verification of vouchers, SOE, Bank book etc.. | Utilization should be of or above 60% against the release of fund from SACS | Less than 60% of the released fund | 1 | As per norms of evalulation tools. | More than 75% of fund release is utilised.
2 | Pattern of expenditure | Whether the expenditure is as per approved budget in each head | Verification of vouchers, approved budget, SOE, Bank book etc.. | As per the approved budget or No but as per the approval from SACS. | No as per the approval. | 0 | As per norms of evalulation tools. | Approval system is not adequate, it is verified with the vouchers and SOE,Bank details.
3 | Bank Account | Whether a separate bank account maintained for the TI Project at the local bank | Verification of bank book and other related documents | Separate bank account in place for TI project in the project area | No separate account | 1 | As per norms of evalulation tools. | Separate Bank Account operated for TI Project.
4 | Systems of Payment-Verification of Bills and Vouchers ( in case of book keeping is done by software, day wise prints of vouchers and ledgers should be available) | All payments made with proper bills and vouchers and are in place with proper approval. | Verification of vouchers and bills | Vouchers and bills are propoerly maintained and are all with approval. | Inadeqaute and no approval from PD of the TI. | 0 | Approval system is not followed. | in our verification, it has found that there is no any approval system of payment of expenditure.
5 | Systems of Payment-Mode of payments | Mode of payment- cash payment is Rs.5000/- as per revised direction from NACO. | Verification of bank account and vouchers | No cash transaction above Rs.5000/- | Cash transaction for the amount more than Rs.5000/- | 1 | As per norms of evalulation tools. | System of payment as per transaction norms of NACO guidelines.
6 | Systems of Payment-Record keeping | All vouchers are printed and machine numbered Whether the ledger is maintained for vouchers | Verification of vouchers Verification of ledger | Vouchers are printed and machine numbered. Ledgers are maintained properly. | Not in place. | 1 | vouching system is proper but ledger posting needs to develop. | Vouchers are printed and numbering followed and ledgers are maintaining properly.
7 | Systems of booking keeping maintenance | Whether cash book maintained/entry made on daily basis | Verification of cash book and interview of accountant | Cash book is updated | Not updated | 1 | As per norms of evalulation tools. | Cash book and other books are keeping as per guidelines.
8 | Financial reporting-SOEs submitted as per operational guideline | Whether SOEs are submitted to SACS on time in the prescribed format. (refer Operational Guidelines for NGO/CBO PART-II-Annexure 'A' and 'B' | Verification of SOEs and interview of SACS official | SOEs are submitted on time and records for the same is avaialbe. | Irregualr in submission of SOEs. | 1 | As per norms of evalulation tools. | SOE are submitted as per NGO / CBO guidelines.
9 | Financial reporting-Mismatch between physical & financial reporting | Whether any mismatch between financial and physical progress reports | Verification of MIS reports and audit reports | Nil or Negligible mismatch | Huge level of mismatch observed and not justifiable | 1 | As per norms of evalulation tools. | In our random verification we have found very negligible mismatch.
10 | Purchase of drugs for STD treatment (only in cases where the purchase has been approved by SACS) | Whether the guidelines on GMP followed? | Verify the drugs and guidelines for GMP/ purchased under Jan Ausadhi Yojana | As per GMP | Not followed and no genuine explanation for the relapse | 1 | As per norms of evalulation tools. | They are following GMP guidelines.
11 | Compliance to SACS directions | Whether NGO has complied to the audit observations | Verify audit recommendation and action taken bassed on the report | NGO has given adeqaute attention to audit recommendations and actions were taken | No action from NGO side | 1 | As per norms of evalulation tools, | Comply with Internal Audit report & organisation Audit Report during our observation.
12 | Cash in hand | What is the limit for cash in hand in the project. NACO direction is maximum Rs.5000/- | Verify cash book, cash box and interview with accountant and PD. | Normally below Rs.5000/- | No system and at majority of times cash balance is more than Rs.5000/- | 1 | As per norms of evalulation tools. | They are maintaining cash balance as per NACO guidelines.
13 | Procurement system in place | What is the procurement system for purchase of drugs/needles and syringes/fixed assets | Three quotations to be collected | Quotations are in place from three different parties and assessed. | No system in place. | 1 | As per norms of evalulation tools. | The Team have found the procurement system but it needs update.
Total Score | [5 empty] | 11

## Scoring sheet FSW-MSM
Scoring Sheet for FSW/MSM
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 14 | 11 | 78.6
2 | Finance | 13 | 13 | 9 | 69.2
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 11 | 78.5714 | Qualified
2 | Finance | 13 | 11 | 84.6154 | Qualified
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 18 | 54 | 43.2 | 38 | 30.4 | 70.3704
2 | SUPPORT SERVICES | 9 | 27 | 13.5 | 11 | 5.5 | 40.7407
Total |  | 27 | 81 | 56.7 | 49 | 35.9 | 63.3157
Name of the Evaluator

## Scoring sheet-IDU
Scoringn sheet for IDU
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 14 | 11 | 79 (80% Approx.)
2 | Finance | 13 | 13 | 9 | 69 (70% Approx.)
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 11 | 78.5714 |  | Village Development team
2 | Finance | 13 | 11 | 84.6154
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 20 | 60 | 48 | 38 | 30.4 | 63.3333
2 | SUPPORT SERVICES | 9 | 27 | 13.5 | 11 | 5.5 | 40.7407
Total |  | 29 | 87 | 61.5 | 49 | 35.9 | 58.374